## Slide 1: Resource estimation to carry out the instrument installation and cold commissioning
Antonio Bianchi
NSS Installation coordinator
NSS Project Division
www.europeanspallationsource.se
12th September 2018

## Slide 2: Resource discussion during IKON 14 (first 8 instruments)
INSTR. | RESOURCES
BEER | Each staff by NPI suppliers + 2-6 people from HZG (minimum ESS support) Most of the personnel for cave and shielding installation will be provided by NPI suppliers Guide alignment will be part of the contract with manufacturer. For cold and hot commissioning ESS technical groups support
C SPEC | 1 Tech each from TUM & 1 from LLB Lead scientist and Engineer Guide, Chopper, and Experimental Cave will be installed by Manufacturer. Beamline shielding, beam stop, cable routing, monitors, collimators, sample equipment, detectors, and cadmium will be installed by CSPEC team (or subcontracted)
BIFROST | DTU – cave fit-out, LLB – choppers, guides by suppliers. ESS support for heavy work (lifting, rigging, ..) & MCA
MAGIC | Instrument teams within 3 - 4 permanently on site
LOKI | Lead Scientist, Lead Engineer, ESS Integration engineer and maximum ESS effort
ESTIA | ESS support with various expertise equal to 2.6 person years (PY) from ESS employees/contractors (Survey & Alignment, Electric Installation, Mechanic Installation, Craning, Workshop Machining, ICS/MCA, PSS, Plumber, DMSC)
ODIN | Lead Scientist (TUM) , 2 Lead Engineers (TUM and PSI), Chopper and Guide company installation teams. Cave interior company installation team. Minor support from ESS required (Survey, ES&H, integration…)
DREAM | Lead Scientist and Lead Engineer rom JCNS: Mikhail + 1 Engineer + (2 technicians) shared with other JCNS instruments. LLB : (Lead Engineer+ 2 technicians) shared with 4 other LLB instruments
IKON 14

## Slide 3: Resource prediction status
The approved Master Schedule takes into account Instruments teams predictions in term of installation time (in-Bunker components, from Bunker to cave, Exp. Cave and cave fit-out…);
Required resources for instrument installation is still an on-going exercise and it has been partly implemented or not implemented yet from the instruments team;
Manpower can change significantly according to many factors, like instrument class, length, complexity and amount of components, skills of personnel involved, installation environment, etc… etc.

## Slide 4: Resource plan
Even if any instrument installation plan will include the final estimation about the total amount of resources, since now it might be useful to share our thoughts especially about “labour” predictions, in order to identify a reliable “order of magnitude”;
Scope of this estimation is to identify a “range of FTEs” necessary to successfully carry out the Phase 4 according to the defined Master Schedule;
It is also useful to maintain a proper budget to complete the installation and c.c. phase;

## Slide 5: Resource estimation
The resource estimation included in this presentation takes into account only the “Instrument scope of work” as defined since the scope setting meeting and according to the T.A.;
It includes all the instruments W.U. as defined since the scope setting meeting;
The assumptions take into account different parameters, according to the specific work units;
Results significantly different from the range provided in this estimation has to be analysed in detail;

## Slide 6: Assumptions and exclusions
Assumptions
1 FTE equals to 1.800 working hours
The estimation takes into account both installation and cold commissioning (the whole Phase 4)
1st category: all the west sector instruments
2nd category: medium length Instruments Dream, Vespa, Skadi
3rd category: short instruments (Odin, Estia, Loki, Freia)
Exclusions
NSS and In Kind Management staff (Coordinators, Lead Scientist, Lead Engineer)
NSS Technology Group support staff for quality assurance/control
Temporary equipment (it is a labour estimation)
Data Acquisition and Analysis Work Unit (ESS scope)
Vacuum Work Unit (ESS scope)

## Slide 7: Work Unit 1 - Installation of Shielding (and cave structure)
Ex cave shielding (pre-cast blocks) - 4 weeks (160 hours)
Beamline shielding 15m /week (9 weeks in total) - category 1
Beamline shielding 15m /week (4 weeks in total) - category 2
Beamline shielding 15m /week (2 weeks in total) - category 3
Surveying - 2 technicians plus tracker marking limit of shielding and cave footprint - marking before drilling - 80 hours in total west sector

## Slide 8: Work Unit 2 - Installation of Neutron Optics
Light shutter (BBG) and NBEX already installed
Outside the bunker: 130 m - 1st category (13 weeks required)
Outside the bunker: 50 m - 2nd category (5 weeks required)
Outside the bunker: 30 m - 3rd category (3 weeks required)
Prediction: 10 m/week (all inclusive of supports, guides, vacuum housing, alignement...)
Inside the bunker (and feedtrough): 22m (2-3 weeks)

## Slide 9: Work Unit 3 - Installation of Choppers
Assumed 6 choppers in total, n. 3 choppers out of bunker/ n. 3 inside the bunker
1 week /chopper (n. 2 Technicians) mechanical installation (70 hours/week including ICS and control racks)

## Slide 10: Work Unit 4 - Installation of Sample Environment

## Slide 11: Work Unit 5 - Detectors and Beam Monitors
Largely dependent from Instrument category (instrument length not relevant)
Cold commissioning will take more effort than installation (30% installation / 70 % c.c.) Indication from Detector group for c.c. (3 technicians x 6 months)

## Slide 12: Work Unit 7 - Motion Control and Automation
Installation includes cables and control cabinets (cable trays is part of the infrastructure
8 hours / axis for cold commissioning (30 axis average)

## Slide 13: Work Unit 8 - Instruments Specific Technical Equipment
Largely dependent from the specific instrument. In many cases it will require more resources

## Slide 14: Work Unit 9 - Instrument Infrastructure
power, pipes, cable trays, control hutch structure, local cranes…
Instrument length partly relevant…..

## Slide 15: Work Unit 11 - Personnel Safety System
Indication from ICS Division (3 Technicians for 3 months - Skilled personnel)

## Slide 16: Conclusion
Summary - Instrument Installation and cold commissioning (PHASE 4) |  | 1st Category West Sector Instr. |  | 2nd Category Dream Vespa Skadi |  | 3rd Category Odin Estia, Loki Freia | 
 |  | % | Total W.H. | % | Total W.H. | % | Total W.H.
Manpower estimation |  | h | h | h | h | h | h
Management (Lead scientist - Lead Engineer) |  |  |  |  |  |  | 
Work Unit 1 - Shielding |  | 18% | 2840 | 14% | 1780 | 12% | 1320
Work Unit 2 - Neutron Optics |  | 14% | 2200 | 9% | 1140 | 8% | 900
Work Unit 3 - Choppers (n. 6 choppers) |  | 6% | 992 | 8% | 992 | 9% | 992
Work Unit 4 - Sample Environment |  | 4% | 560 | 4% | 560 | 5% | 560
Work Unit 5 - Detectors and Beam Monitors (average complexity) |  | 20% | 3228 | 25% | 3228 | 30% | 3228
Work Unit 6 - Data Acquisition and Analysis (ESS scope) |  | 0% | 0 | 0% | 0 | 0% | 0
Work Unit 7 - Motion Control and Automation |  | 6% | 944 | 7% | 944 | 9% | 944
Work Unit 8 - Instruments Specific Technical Equipment |  | 7% | 1088 | 8% | 1048 | 9% | 1008
Work Unit 9 - Instrument Infrastructure |  | 13% | 2040 | 11% | 1404 | 8% | 864
Work Unit 10 - Vacuum (ESS scope) |  | 0% | 0 | 0% | 0 | 0% | 0
Work Unit 11 - Personnel Safety System |  | 13% | 2080 | 13% | 1600 | 10% | 1120
Overall Amount |  | 100% | 15972 | 100% | 12696 | 100% | 10936
FTE |  |  | 8.87 |  | 7.05 |  | 6.08
Hours |  |  | 15972 |  | 12696 |  | 10936