## Slide 1
Roland Garoby
Technical Director
www.europeanspallationsource.se
18 May 2018
ESS Project Status

## Slide 2: Outline
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 3: Civil construction status

## Slide 4
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
New Bus Stop

## Slide 5: Campus
Labs and Workshops
Offices, auditorium canteen
Entrance Building
Signed construction and financing agreements in February
Now in detailed design before target cost is agreed
Cost of the lease is included in the operations costs

## Slide 6
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 7: Equipment construction is progressing at in-kind partners (e.g. CEA & INFN)…
Medium b elliptical cavities (CEA-Saclay and INFN-Milano)

## Slide 8: some in-kind equipment is already being installed in Lund [e.g ion source from INFN (+ CEA)]…
Accelerator Front End
(Ion Source and LEBT)
… an opportunity for lessons that led to a new
organization for the installation of the infrastructure…

## Slide 9: … and Test infrastructure is operational at some partners’ premises (e.g. Uppsala)
Romea in HNOSS
cryogenics
- liquid helium
- liquid nitrogen
control room
- equipment controls
- data acquisition
radio-frequency (RF) power sources
3 bunkers
with test stands
horizontal cryostat
vertical cryostat
State-of-the-art Equipment
HB package at FREIA
Several Spoke prototypes tested in HNOSS
Preparation of HB validation test (>March)
Preparation of Spoke Prototype test (>May)

## Slide 10: ESS development of high power/ compact/ high efficiency modulator is successful
Electrical schematic of Stacked Multi-Level (SML) modulator
SML prototype
modulator
successfully powered
a Toshiba Klystron
up to 1 MW RF
Happy
Engineers!
12 modulators are in construction in industry
(build-to-print)

## Slide 11: Helium Systems procured by ESS are in commissioning
Helium compressors
and recovery system
ACCP compressors and oil removal system
Helium Recovery System Compressors

## Slide 12
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 13: Equipment construction is progressing at in-kind partners (e.g. ESS-Bilbao, FZJ)…
48 cm
proton beam
Tungsten bricks
Cassette
Cold moderator vessel (FZJ)
Forging of moderator shaft (FZJ)

## Slide 14: ESS procured equipment is being installed (e.g. storage pits in Active cell)
Active cell
Hole before storage pit installation
Lowering of pit A3 into place

## Slide 15
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 16: ESS Control System network
Main Control Room
DMZ
ESS Network
Core Network
CA network
CA network
CA network
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
PVGW
Red: Accelerator + Cryogenics zone
Yellow: Target zone
Orange/Violet: 1 zone/instrument
Blue: CF zone
PVGW: EPICS Process Value Gateway
CA Network: Channel Access (EPICS protocol)
PVGW
PVGW
CA network
CA network
CA network
CA network
CA network
CA network
~ 1.6 106 control points!

## Slide 17: In-kind contributions are materializing and installation has started
PSI IFC card family contribution
IFE control room contribution
Cabling on site
Oxygen Deficiency Hazard system

## Slide 18: First steps of commissioning from the local control room
Recent achievements include controlling the pure Helium storage and parts of the ion source and LEBT from the local control room

## Slide 19
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 20: Construction is 45% complete relative to the current baseline plan
Schedule performance: Few months delay shown in schedule variance and some delay incorporated in baseline changes (total of ~ 12 months); anticipate further large delays - main subject of this review
Cost performance: Good CPI, but already captured significant cost growth in the baseline (58 M€ since 2013) and foresee large cost increases for future work (ref. Completion of Construction Report reviewed at last Annual Review)

## Slide 21: Background
Since establishing the baseline in 2013, we encountered large cost and schedule impacts from ratcheting of radiation safety requirements in aftermath of the Fukushima seismic event and concern over antagonistic threats
  145 M€ cost increase (baseline + forecast changes) identified in ‘Report to European Spallation Source ERIC Council on Completion of Construction’
ESS management is working closely with the ESS Council to secure adequate budget
We have also focused attention on completing the construction project scope with minimal delay in early science

## Slide 22: Addressing the Schedule
Original baseline was established in 2013
  Well before completing preliminary design for most systems
  Only a few In-Kind partnerships in place
  Unaware of eventual ratcheting of requirements for Target Building
We have now reached a point where:
  the detailed scope, requirements, and method of accomplishment are better understood
  in-kind partnerships are established
  contracts with many of our key commercially supplied scope elements are in-place, and
  the uncertainty related to designing the buildings to meet regulatory requirements is nearly behind us
Therefore, we are proposing a new baseline plan to help us manage and track the work going forward
  Reviewing the proposed re-baseline is the purpose of next week review

## Slide 23: Re-baselined Schedule (under review next week)
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float to BOT
Accelerator RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
RSOUP
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed
Will propose reasonable float to establish external milestone commitment

## Slide 24: Main delays for the Accelerator are due to in-kind partners…
New Baseline
2019
2020
2021
ISrc to LEBT
25 Jun '18
ISrc to RFQ/MEBT/DTL1
4 Nov '19
ISrc to DTL4
27 Apr '20
ISrc to Beam Dump (BOD)
8 Feb '21
RBOT
24 May '21
Beam to RFQ/MEBT Delay
18.8 months
Beam to DTL4 Delay
21.8 months
BOD Delay
21.2 months
RBOT Delay
23.9 months
Old Baseline
2019
2020
2021
ISrc to RFQ/MEBT
11 Apr '18
ISrc to DTL4
5 Jul '18
ISrc to Beam Dump (BOD)
30 Apr '19
RBOT
28 May '19

## Slide 25: Main delays for the Target are due to the Target Building, but in-kind contributions are critical…
2018
2019
2020
2021
2022
BOT
Target Building (D02) Access for Monolith Installation
Target RBOT
Monolith and A2T Concrete
Monolith Installation & Testing
Target Integrated Bunker Scope
Bunker Construction and Installation
High Bay Infrastructure Installation
Monolith Area Superstructure
Testing and Readiness Review
NSS RBOT
Target Wheel & MR Installed
Monolith inserts & shutters installed
Final testing and Readiness Review
3 months float
CF D01/D03 Build-out to weather tight
Parallel Works
Ready for parallel bunker and monolith works

## Slide 26: Estimate At Completion (EAC) of the neutron source increases with the new baseline
 | Costs in M€ |  |  |  |  |  | 
Sub-Project | Current BL | Forecast (Feb-18) | Current EAC | Proposed BL | Proposed Forecast | Proposed EAC | Change in EAC
Accelerator | 490.0 | 28.7 | 518.7 | 496.7 | 31.5 | 528.2 | 9.5
Target | 183.6 | 18.7 | 202.3 | 189.7 | 30.5 | 220.2 | 17.9
ICS | 77.4 | 8.2 | 85.6 | 79.3 | 10.0 | 89.3 | 3.7
Total | 751.0 | 55.6 | 806.6 | 765.7 | 72.0 | 837.7 | 31.1
Mitigation actions will be taken to meet our commitment to manage within budget constraint aiming at costs related to:
Installation,
Delays,
Additional items.

## Slide 27: Funding decisions in 2018
AFC.07
Budget Plan 19/20 (R)
Indicative Plan 21-25 (I)
Construction Budget 2019 (I)
10-11 Apr
Council.13
Budget Plan 19/20 (A)
Indicative Plan 21-25 (I)
Commitments from Members for 2019/20 initial ops funding
4-5 June
AFC.08
Constr. budget 2019 (R)
Init ops budget 2019 (R)
Indicative planning 2021-2025 (R)
30-31 Oct
Council.12
Workshop
Budget plan 19/20 (I)
Indicative plan 21-25 (I)
High-Level Document (D)
Sharing Policy (D)
8 Feb
Schedule Review
Focus on re-baselining
Will mostly impact indicative plan 21-25
22-24 May
Annual Review
Project review
Sep
Council.14
Constr. budget 2019 (A)
Init ops budget 2019 (A)
Indicative plan 2021-2025 (A)
Commitments from Members for 2021-2025
Commitments from Members to completion of construction
3-4 Dec
Political decision-making
Minister level

## Slide 28
Status of construction:
  Civil construction
  Accelerator
  Target
  Controls
“New” baseline schedule
Summary

## Slide 29: Summary
ESS construction advances regularly, both at the in-kind partners and in Lund. Progress in testing and fabrication confirm that the planned performance will be met.
Realistic delivery dates from in-kind contributions and delay in the construction of the Target building led to the new baseline schedule.
Budget includes our improved knowledge of costs and the impact of delays.
We look forward to the feedback from next week’s review…
Multiple deliveries from in-kind partners are on critical path…
IKRC will now follow-up.