## Slide 1: Installation Planning Update
Ciprian Plostinar
ESS/CEA-ESSI Coordination Committee Meeting #5
www.europeanspallationsource.se
18 May, 2018

## Slide 2: Key Assumptions
Installation
In-Kind Model
Testing
Commissioning
Ready for Installation Dates (RFI):
Some contractual
Optimised Sequence:
Logic
Safety
Flexibility
Parallel Installation and Commissioning:
Shielding Wall
Others “best estimate”
Safety Measures
Correct Gateways
Suitable Reviews
Realistic time allocation
Relevant Permits
SSM
Hardware
Beam
Key Dependencies
Critical Parameters
Other Divisions
Coordinated Installation of Utilities/Services
Demanding Schedule
No Internal Float

## Slide 3: Accelerator Major Milestones
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021

## Slide 4: ESS Project Timeline
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump (BOD)
Accelerator Ready for Beam on Target (RBOT)
Beam on Target (BOT)
Start Of User Program (SOUP)
End of Construction

## Slide 5: ISrc and LEBT
First major accelerator installation milestone at ESS
Main installation priority for early 2018
Major effort on installation of utilities in the tunnel and the FEB
  This allowed the ISrc and LEBT assembly to proceed as planned (January 2018).
Current focus:
  Cable pulling, cable terminations, rack filling and testing, ISrc HV safety cage, etc.
  Energising and SSM Permits
Current planning forecast:
  Safety Readiness Review: June/July 2018.
  First Beam: July 2018

## Slide 6: ISrc and LEBT Timeline
2017
2018
Sep
Oct
Nov
Dec
2018
Feb
Mar
Apr
May
Jun
Jul
Installation Readiness Review
Sep 15
Delivery to ESS
Dec 12
ISrc and LEBT Assembly Begins at ESS
Jan 16
Assembly
Completed
Feb 16
Energising Permit
Mar 5
SSM Permit
May 28
Start of Beam
Commissioning
Jul 9
Sep 18 - Nov 3
Final Tests in Catania
Nov 6 - Nov 30
ISrc and LEBT Disassembly
Dec 1 - Dec 12
Transport to Lund
Dec 13 - Dec 22
Delivery Acceptance Tests
Jan 16 - Feb 16
ISrc and LEBT Assembly
Apr 9 - Apr 13
HV Safety Cage Installation by ESS
Apr 16 - May 11
PSS0 Installation
May 14 - May 25
PSS0 Validation
May 28 - Jun 22
Hardware Tests
Jun 25 - Jul 6
SRR1
Oct 16 - Dec 22
Utilities Installation - ISrc+LEBT Area
Jan 8 - May 25
Utilities Installation, Cable Pulling and Terminations, Etc. - FEB
Oct 16 - Dec 22
ICS Installation
Jan 8 - May 25
ICS Installation

## Slide 7: Normal Conducting Linac
Major milestones:
  RFQ RFI: September 2018
  MEBT RFI: February 2019
    SSPA for buncher 1: April 2019
    SSPA for bunchers 2,3: August 2019
    Power Converters for MEBT Magnets: July 2019.
  DTL4 RFI: January 2019
  DTL1 RFI: March 2019
  DTL3 RFI: April 2019
  DTL2 RFI: June 2019
  DTL5 RFI: October 2019
RF System Status:
  Delays reported throughout 2017 due to unforeseen funding issues at ESS Bilbao
    These have now been resolved
  Some procurement difficulties, but progress has been made
  Many tenders remain to be placed (uncertainty), but better confidence on delivery dates
  ESS has started the process of procuring critical spares (loads/circulators) -> risk control.
  Important driver for the NC Linac commissioning plan
Shield wall between DTL4 and the Spoke section allows installation to continue in the cold linac while beam commissioning the NC linac.
  This is possible by postponing DTL 5 installation
  Important schedule delay mitigation/flexibility/control

## Slide 8
2018
2021
Today
50 days
20 days
20 days
20 days
20 days
20 days
20 days
80 days
20 days
10 days
5 days
5 days
10 days
10 days
25 days
40 days
50 days
100 days
10 days
60 days
10 days
65 days
10 days
10 days
10 days
10 days
10 days
10 days
95 days
10 days
40 days
10 days
65 days
Tunnel
Gallery
SRR/PSS/Commissioning/Conditioning
Stubs
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
03/09/18 - 09/11/18
RFQ Installation
07/01/19 - 01/02/19
DTL4 Installation
04/02/19 - 01/03/19
MEBT Installation
11/03/19 - 05/04/19
DTL1 Installation
08/04/19 - 03/05/19
DTL3 Installation
10/06/19 - 05/07/19
DTL2 Installation
27/07/20 - 21/08/20
DTL5 Installation
17/12/18 - 05/04/19
Stubs Installation
17/12/18 - 11/01/19
RFDS Support Structure
14/01/19 - 25/01/19
Water Cooling for RF
28/01/19 - 01/02/19
Trays and Cables RF
04/02/19 - 08/02/19
Power to Modulators
11/02/19 - 22/02/19
RFQ Klystron
25/02/19 - 08/03/19
DTL1 Klystron
11/03/19 - 12/04/19
Modulator 1
11/03/19 - 03/05/19
Waveguides
06/05/19 - 12/07/19
Loads and Circulators
25/02/19 - 12/07/19
RF System Commissioning (RFQ and DTL1)
15/07/19 - 26/07/19
PSS1 Validation
29/07/19 - 18/10/19
RF Conditioning (RFQ and DTL1)
21/10/19 - 01/11/19
SRR2
04/11/19 - 31/01/20
Beam Commissioning (ISrc to DTL1)
29/07/19 - 09/08/19
Modulator 2
12/08/19 - 23/08/19
Modulator 3
02/09/19 - 13/09/19
DTL2 Klystron
07/10/19 - 18/10/19
DTL3 Klystron
04/11/19 - 15/11/19
DTL4 Klystron
02/12/19 - 13/12/19
DTL5 Klystron
23/09/19 - 31/01/20
Full NC RF System Commissioning
03/02/20 - 14/02/20
PSS1 Re-Validation
17/02/20 - 10/04/20
RF Conditioning (DTL2, 3, 4)
13/04/20 - 24/04/20
SRR3
27/04/20 - 24/07/20
Beam Commissioning (ISrc to DTL4)

## Slide 9: SC Linac
Four major installations on critical path:
  Cryomodules
    13 SPK CMs, 9 MB CMs and 2 HB CMs to be installed initially
    The rest of the HB CMs to be installed after RBOT date.
    As of today, the earliest installation date of the first cryomodule is end of the 2019.
  Cryogenics Distribution System
    Cryomodule installation can only start after the complete CDS has been commissioned.
  Linac Warm Units
    LWUs will be installed after the cryomodule installation.
    HEBT LWU to be installed first
  RF Power Stations for Spokes
    Delivery and installation: July 2019 to August 2020

## Slide 10: SC Linac – Spoke Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
19/08/19 - 15/11/19
SPK CDS Installation
18/11/19 - 07/08/20
SPK CM Installation
22/06/20 - 25/09/20
SPK LWU Installation
08/01/18 - 23/02/18
SPK RFDS Support Structures
02/04/18 - 27/07/18
SPK Waveguides
16/04/18 - 10/08/18
SPK Loads and Circulators
12/08/19 - 25/09/20
SPK RF Power Stations

## Slide 11: SC Linac – MBL and HBL Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
03/12/18 - 15/11/19
Elliptical CDS Installation
18/11/19 - 01/06/20
MBL CM Installation
11/05/20 - 03/07/20
MBL LWU
01/06/20 - 07/08/20
HBL CM Installation
30/03/20 - 25/09/20
HBL LWU 1-10
05/08/19 - 13/12/19
HBL LWU 11-21
05/03/18 - 21/09/18
MBL/HBL RFDS Support Structures
30/07/18 - 06/09/19
MBL/HBL Waveguides
13/08/18 - 20/09/19
MBL/HBL Loads Circulators
13/08/18 - 27/09/19
MBL Klystrons
22/04/19 - 10/01/20
MBL Modulators

## Slide 12: SC Linac Installation Timeline
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
SPK CDS Installation
SPK CM Installation
SPK LWU Installation
SPK RFDS Support Structures
SPK Waveguides
SPK Loads and Circulators
SPK RF Power Stations
Tunnel
Gallery
Elliptical CDS Installation
MBL CM Installation
MBL LWU
HBL CM Installation
HBL LWU 1-10
HBL LWU 11-21
MBL/HBL RFDS Support Structures
MBL/HBL Waveguides
MBL/HBL Loads Circulators
MBL Klystrons
MBL Modulators

## Slide 13: HEBT, A2T, DMPL
Relatively flexible installation sequence.
  We can adapt to the inherent delivery changes.
For the HEBT, the main installation driver is the availability of the LWU.
  HEBT beam pipe to be installed in 2018 (early).
    Installation Readiness Review passed.
For the DMPL the driver is the Tuning Beam Dump (Target Division delivery)
  Beam Dump System Installed: March 2019
A2T Installation depends on access dates
  A2T is partially part of the Target Building. The planned assumed early access in September 2019, but this dates was recently moved to January 2020. Installation sequence is being reviewed.

## Slide 14: HEBT, A2T, DMPL - Installation Timeline
Tunnel
Gallery
2018
2019
2020
2021
ISrc to LEBT
28/6/2018
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
02/07/18 - 30/11/18
HEBT Spool Pieces (Beam Pipe)
10/12/18 - 19/04/19
HEBT LWUs
22/04/19 - 07/06/19
DMPL LWU
27/05/19 - 27/03/20
DogLeg/A2T LWU

## Slide 15
2018
2021
Today
75 days
10 days
15 days
150 days
10 days
60 days
10 days
65 days
180 days
10 days
40 days
10 days
60 days
25 days
65 days
120 days
290 days
290 days
250 days
141 days
50 days
15 days
20 days
20 days
10 days
75 days
20 days
PSS/SRR
SC Linac, HEBT, A2T
NC Linac
Beam Commissioning
2018
2019
2020
2021
ISrc to DTL1
4/11/2019
ISrc to DTL4
27/4/2020
ISrc to Beam Dump (BOD)
8/2/2021
RBOT
24/5/2021
17/12/18 - 12/07/19
RFQ + DTL 1 RF System
15/07/19 - 26/07/19
PSS1 Validation
29/07/19 - 18/10/19
RFQ, MEBT, DTL1 RF Conditioning
21/10/19 - 01/11/19
SRR2
04/11/19 - 31/01/20
ISrc to DTL1 Beam Commissioning
27/05/19 - 31/01/20
Full NC Linac RF System
03/02/20 - 14/02/20
PSS1 Re-Validation
17/02/20 - 10/04/20
DTL2, 3, 4 RF Conditioning
13/04/20 - 24/04/20
SRR3
27/04/20 - 17/07/20
ISrc to DTL4 Beam Commissioning
20/07/20 - 21/08/20
DTL5 Installation
03/12/18 - 15/11/19
Elliptical CDS Installation
19/08/19 - 15/11/19
SPK CDS Installation
18/11/19 - 07/08/20
SPK CM Installation
18/11/19 - 01/06/20
MBL CM Installation
01/06/20 - 07/08/20
HBL CM Installation
12/08/19 - 13/12/19
HBL1 LWU Installation
16/12/19 - 27/03/20
A2T LWU Installation
30/03/20 - 19/06/20
MBL/HBL2 LWU Installation
22/06/20 - 07/08/20
SPK LWU Installation
10/08/20 - 25/09/20
Final HBL/SPK LWU Installation
12/08/19 - 25/09/20
SPK RF Power Stations
28/09/20 - 16/10/20
Full PSS Validation
19/10/20 - 13/11/20
DTL5 and SC Linac - Warm RF Conditioning
16/11/20 - 11/12/20
CDS and CMs Cooldown and Tests
14/12/20 - 22/01/21
SC Linac - Cold RF Conditioning
25/01/21 - 05/02/21
SRR4
08/02/21 - 07/05/21
ISrc to DMPL Beam Comm.
10/05/21 - 21/05/21
SRR5
ISrc to LEBT
28/6/2018

## Slide 16: Summary
Major re-baselining effort with significant schedule updates.
  First proton beam at ESS this year (Ion Source and LEBT)
  Beam on Dump (BOD) at 570 MeV with the NC linac, SPK, MBL and two unpowered HBL CMs: February 2021
  Accelerator Ready for Beam on Target (RBOT): May 2021.
  Beam on Target (BOT) date is ~one year later. This margin is to be used as schedule float as well as to install the remaining HB CMs.
Multiple delays accounted for:
  Clear critical path to RBOT.
  Many manufacturing contracts signed, but some are still being prepared, so a certain level of uncertainty remains.
Accelerator utilities installation is run by the infrastructure project
  Matches the accelerator installation plan
  Demanding, but not on the critical path
Installation will be a major learning curve
  Significant installation load
  Valuable lessons from the FEB, Ion Source and LEBT installations.