## Slide 1
RF Distribution for Warm Linac
RF Systems Group
Zamudio, 30 May 2018

## Slide 2
Outline
  3D Layout Status
  RFQ and DTL distribution: Rectangular Waveguides and Loads and Circulators.
  MEBT distribution: Coaxial Components
  Structure and Supports: Gallery, Stub and Tunnel
  Others: Power Detectors and Arc Detectors
  Conclusions / ACTIONS

## Slide 3
  3D Layout Status:
  -- Huge effort: I. Barrera (ESS-Bilbao) and Pontus (ESS)
  -- Layout is frozen (minor changes allowed) Good Job!
  -- Finding: 3D models and drawings available in Chess are obsolete:
  Example 1: RF Gallery: ESS-0038136.2. No updated since 2015
  Example 2: Stubs 100/110: ESS-0034986.2 and ESS-0034999.2 No updated since 2016
  Proposed action: Upload the final version of the 3D Model and corresponding drawings to CHESS for the whole RF Warm Linac.

## Slide 4
  2. RFQ and DTL distribution:
  Rectangular Waveguides:
  -- Technical Specifications. CLOSED. Colab. Yogi!!
  -- Documentation: under review of the law officer as a legal requirement before the publication of the tender.
  -- Tender: expected to be published July 2018
  -- Tech. question to ESS? : Update on the air cooling (simulations/actions) of the waveguides in Stubs.
  B) Loads and Circulators:
  -- Tender: Published on late Feb. 2018. 1 Company interested but did not send all documentation in time.
  Therefore process to be declared a “Void tender”
  Next Steps??

## Slide 5
  3.- MEBT distribution: Coaxial Components
  -- Layout Closed: good work . MEBT group involded including Morteza (PSS), RF group (Yogi, Sunesson)
  -- Tender: Not needed. Minor contract
  ACTIONS: 1) Procurement Date: Late June expected
  2) Delivery in Lund: Mid September

## Slide 6
  4. Structure and Supports: Huge Collaboration!!
  Gallery:
    -- Status: ESS-Bilbao working on load calculations in order to finish the documentation required to start the tender procedure.
    -- Questions to ESS:
    1) In order to define the anchorages we should know the thickness and quality of the concrete slab under the gallery floor? Which type of anchorages: Chemical or expansion?
    2) Which is the exact location for the piping / wiring above the structure of the gallery?
  ACTIONS:

## Slide 7
  4. Structure and Supports: Huge Collaboration!!
  B) Stub and Tunnel:
    -- Status: CLOSED. ESS-Bilbao to send ESS (Pontus) final version of the 3D model.
    -- Tender: Ask for a quotation to several companies.
    -- Questions:
    To confirm final locations of the envelopes for wiring and piping in Stub 100/110?
    Update on the mock-up of the Stub for the spokes cavities??
    ACTIONS:

## Slide 8
Outline
  5.- Others: Power Detectors and Arc Detectors
  -- Status:
  --Questions: 1) Type of Arc Detectors / Locations?
  2) Power Detector:??
  GENERAL CONCLUSIONS / ACTIONS: