## Slide 1: Workshop commissioning 2018-10-16 Installation Coordination at ESS
Olle Lagerblad

## Slide 2: Agenda
AD installation Project (Infrastructure and Component installation)
Harmonized ways of working at ESS
  Outline
  The Installation Binder ”Practical Use”
  The Installation Readiness Review (IRR)
  The RAMS ”Practical Use”
  ESS Work Orders ”Mandatory for all installation work”

## Slide 3: AD Installation Project
AD will change the set up for Installation;
  Current approach - Component installation and Infrastructure project
AD Will merge Infra structure project with component installation
Main purposes for the change is;
  Simplify – Reduce the current amount of interfaces
  Clarify – Responsibilities, one AD installation coordinator, uniform implementation of processes
  Clarify – Responsibilities for planning and reporting (Own org and IK part.)
  Use of resources – Improve and coordinate use of common resources
  Release resources for IK delivery of components “expediting”
  Clarify and align Infra project installation planning with component installation
Budget allocation, Infra project budget (WP 15/16 +CR) and WP 98

## Slide 4: Introduction “Project changes over time”
Engineering phase
Design and planning
AD Project
WP x -------------------------- WP z
Construction phase
Installation & Commissioning
AD Project
Installation Commissioning
Mainly Installation and commissioning focus
Components matrixed for installation and testing
The project consist of mainly 2 high level phases
Mainly component focus
Installation & Commissioning matrixed

## Slide 5: Implementation
“Daily stand up” meetings in the buildings
“Daily” meeting in “installation room”
  Principal agenda
    Plan/Comply or explain deviation/Issues (meetings outside)
Weekly Meetings
  Installation detailed working and follow up meetings (weekly)
    Detail planning and organization of installation activities
    Service needs (eg. transportation, storage, tools, workshops)
    Installation binder
    Commissioning
  Installation and commissioning meeting “Information” (Friday)
    Share information
    General presentations
    Status updates
    Safety /quality aspects
    Issues solved/new

## Slide 6: Harmonized ways of working at ESS

## Slide 7: Introduction
ESS is implementing harmonized ”ways of working”
  Installation binder (IB) and Installation Readiness Review (IRR)
  Risk Assessment and Method Statement (RAMS)
  The Work Order process (WO)
  NCR (Non Conformity Report)
Services and support
  Information can be found at ESS Installation web page
  https://confluence.esss.lu.se/category/essinst

## Slide 8: ESS Installation Services

## Slide 9: Interface between In Kind, ESS WP and Installation Package lead
AD installation coordinator
Installation package lead
AD Work package lead
AD Liaison Officers
IK partner
Responsible for;
Installation binder
IRR
Work order
NCR

## Slide 10: Installation Binder
Purpose
  Collect all required documentation to perform site work
  Gathers documentation prepared before and during installation
There is a template, if tab is not applicable N/A
The installation Scope can be split into several IB, depending on:
  Time for the installation - If the installation is performed in different time periods it may be better to create separate binders
  Area - If the work is done in different areas of the building it may be better to create separate binders
  Disciplines / Contractors - If there are several contractors and/or disciplines involved in the installation, it may be better to do separate binders for each contractor (As electrical, mech. or piping)

## Slide 11: Input from Design / Manufacturer
Check by:
Discipline Lead Engineer
QC Engineer
Preparation of Installation Binder
Input from Design
IRR

## Slide 12: Preparation of Installation Documentation
Reviewed by:
Discipline Lead Engineer
QC Engineer
Preparation of Installation Binder
Input from Design
IRR

## Slide 13: Purpose IRR Documentation
The purpose with Installation Readiness Review is to;
review if the necessary preparations have been performed
and the supporting documentation are in place for the upcoming installation.
Good shape – Proceed
Minor things to fix before start – Keep start date
Major things to fix before start – Reschedule installation
Part of package not ready – Split package

## Slide 14: Preparation of Installation Documentation
Installation Certificate of Compliance
Perform Installation
Pre Job Briefing
Test & Inspection
SRR
TRR

## Slide 15: ESS Work Orders
The Work Order (WO) control the release of work and work/safety
  some aspects are:
    No work shall be executed unless it is planed and organized
    Synchronize the work with other parallel work (same area)
    To control plant conditions and equipment
    To plan and organize delimitations and tag outs
    “becomes more and more important when entering in to the test and commissioning phase!”
The Work Order will mainly state:
    Installation activity start and end time
    Summary of the activity
    Documents related to this activity (RAMS)
    Any need for delimitations/tag outs
https://jira.esss.lu.se/servicedesk/customer/portal/11

## Slide 16: Registering WOs
Minor work
6 fields + RAMS (attached)
Normal work
6 fields + link to installation Binder

## Slide 17: Risk Assessment and Method Statement (RAMS)
What’s the purpose with a RAMS?
Identify hazards and associated risks for an activity and determine if sufficient controls are in place (to reduce the risks to an acceptable level)
Who is responsible for preparing the RAMS?
Installation Package Lead for making sure it’s prepared.
What does a RAMS consist of?
The RAMS consists of two parts:
A method statement, i.e. a detailed break down/description of the work to be carried out and material to be used to perform this task
A risk assessment, i.e. identify the risks associated to the work steps detailed in the method statement. Including adjacent risk.

## Slide 18: Questions?