## Slide 1: MPS commissioning at ESS
Szandra Kövecses
Lead Integrator for Machine Protection
www.europeanspallationsource.se
16 October, 2018

## Slide 2: Protection for the NC linac beam commissioning
In order to provide protection for the NC linac beam commissioning,
all relevant MP systems and functions MUST be completely verified and validated
Notes: With and without beam

## Slide 3: What do I mean by relevant?
The machine protection system of systems (MPSoS) is distributed along the linac, target and the neutron instruments.
The relevant ones in this case are the ones that are covering equipment in the NC linac.

## Slide 4: Distribution overview
Notes: MP monitors inputs and stops the beam if a potentially damaging situation is detected

## Slide 5: NC linac distribution overview
Notes: Green: actuators
Blue: Beam monitoring
Orange: other

## Slide 6: Dependencies of MPSID
MPSID
  Insertable Devices
  ID motion control
  ID water cooling
  NTP server
  EPICS
  Technical network
  aso.

## Slide 7: Dependencies on MPSID
ID motion control
  MPSID issues a movement permit which allows movement or blocks it
  The permit is an active signal which closes a NO relay
  Relay has a button that forces it to closed state (ONLY for tests)
MPSID does not block ID/ID motion controller commissioning

## Slide 8: NC linac distribution overview

## Slide 9: Dependencies of FBIS
FBIS
  Timing system
  Ion Source
  Choppers
  BCM
  BLM
  BPM
  LPSRF
  MPSID
  MPSVAC
  MPSMAG
  Aso.

## Slide 10: Dependencies on FBIS
Rewire
Rewire
FSU
High signal
to chop
High signal
to chop
Notes: Timing-magnetron PS
Currently: fiber straight from TS to magnetron PS (keep it for IS+LEBT commissioning)
Final: fiber from TS to FBIS and fiber from FBIS to magnetron PS (NC commissioning), active
Magnetron PS-Magnetron
Current: HV cable from magnetron PS to magnetron
Final: FSU in between. “NO” (IS+LEBT commissioning, tested in lab, administrative work, RAMS aso)
HV interlock
Current: cable from IS and LEBT PLC to HV PS. Current loop
Final: cable from IS and LEBT PLC to FBIS and cable from FBIS to HVPS (NO open switch)
LEBT Chopper
Have to provide 5V to request chopping -> no effect on chopper commissioning
MEBT Chopper
Have to provide a high signal to chop. No effect on chopper commissioning

## Slide 11: When to test MPS?
Non-beam verification and validation
Due to the many interfaces and functions performed by the interaction of systems, MP should be tested late in the hardware (non-beam) commissioning.
Beam verification and validation
The MP tests should be the first tests to be performed during the beam commissioning

## Slide 12: Connect additional equipment to MPS
When the later sections of the linac are installed equipment has to be connected to existing or new MP systems.
When that is done the affected system has to be reverified and revalidated

## Slide 13: Thank you
Questions?
www.europeanspallationsource.se
16 October, 2018