## Slide 1: Beam Commissioning at ESS
Ryoichi Miyamoto
(ESS/AD/BPOD/BP)
Workshop on Testing and Commissioning
16-17 October, 2018

## Slide 2: Outline
Beam commissioning overview
  Planning
  Configuration
  Note on beam physics
Summary

## Slide 3: What I'm doing...
Planning phase
  Identify required activities with beam and their dependencies.
    Primary focus is on beam physics related activities, e.g., RF cavity setting.
    Also including hardware verifications with beam, e.g., diagnostics verifications.
  Define a sequence of the activities based on the dependencies and priorities.
    Have no authority to change the term allocated to a beam commissioning stage. (Only provide feedbacks to the integration, testing, and commissioning planner.)
  Help to develop (or do develop) a procedure of each activity.
  Maintain and update the plan.
Execution phase
  When the beam is available, determine conducted activities based on the plan and other conditions, e.g., availability of subsystems and personnel.
    Availability of the beam itself is determined by the system owners and operations.
  Help to conduct (or do conduct) each activity.
  Is one of the primary stakeholders to permit (the shift leader) to use a new machine configuration and beam parameter envelope.
    In the control room, the shift leader is in charge of these.
  Maintain and update the plan.

## Slide 4: Beam commissioning stages and schedule
Focus now is on the ongoing ISrc-LEBT and the following NC linac stage.
Schedule is driven by deliveries and installations of components. The sequence of beam commissioning activities is laid out to fit to the allocated time.
  No contingency for unexpected interventions.
  Every step has to be well prepared and executed as planned.
  Possible to run out of time (e.g., before starting current ramp-up).
  Doing better (e.g., including realistic contingency) is harder when the plan is not so stable.
Beyond the ISrc-LEBT stage, we use internal and permanent beam stops and diagnostics devices. This allows us to come back to a state of the preceding stages.
  The linac includes a thorough set of permanent diagnostics devices.
Stage | Energy [MeV] | Start date (old) | Start date (baseline) | Start date (update) | Duration [weeks]
ISrc - LEBT | 0.075 | 2017-11-20 | 2018-06-28 | 2018-09-19 | 22
ISrc - DTL1 | 21 | 2018-11-05 | 2019-11-04 | 2019-11-11 | 14
ISrc - DTL4 | 74 | 2019-01-21 | 2020-04-27 | 2020-07-13 | 13
ISrc - dump (BOD) | ~570 | 2019-05-13 | 2021-02-08 | 2021-04-26 | 13
ISrc - target (BOT) | ~1370 | 2019-06-24 | 2022-06-08 | 2022-06-08 | 

## Slide 5: Planning example of commissioning steps: ISrc-LEBT
High-level plan and strategy, in terms of beam physics, has been presented in internal documents (e.g., ESS-0149990 for NC linac) as well as in conferences and workshops.
Steps and sub-steps of the ISrc-LEBT stage has been maintained and updated in Jira.
Steps and sub-steps of the ISrc-DTL1 stage has been developed in Jira.
How to prepare for each sub-step is up to the responsible person.

## Slide 6: Planning example of commissioning sub-steps: ISrc-LEBT
There is a page for each sub-step.

## Slide 7: Beam modes
Mode | Current [mA] | Duration [µs] | Rep [Hz]
Probe | ~6 | ≤ 5 | ≤ 1
Fast tuning | ≤ 62.5 | ≤ 5 | ≤ 14
Slow tuning | ≤ 62.5 | ≤ 50 | ≤ 1
Long pulse verification | ≤ 62.5 | ≤ 2860 | ≤ 1/30
Production | ≤ 62.5 | 2860 | 14
LEBT
(chopper)
RFQ
MEBT
(chopper)
ISrc
< 100 mA
6-70 mA
6-63 mA
6-62.5 mA
5-2860 µs
5-2860 µs
~100 µs
~3000 µs
5-2860 µs
~0.1 µs
~0.1+20 µs
~0.01 µs
~0.01 µs
Notes: .

## Slide 8: Beam stops
Location | Type | Availability | Tuning | Long-pulse | Production
LEBT (inside tank) | FC | Permanent* | Yes | Yes | Yes
LEBT (outside tank) | FC | Temporary* | Yes | Yes | Yes
MEBT (inside tank) | FC | Permanent | Yes | -- | --
DTL2 (intertank) | FC | Permanent | Yes | -- | --
DTL4 (intertank) | FC | Permanent* | Yes | -- | --
Spokes (doublet #1) | Stop | Permanent | Yes | -- | --
Medium-β (doublet #6) | Stop | Permanent | Yes | -- | --
Dump line | Dump | Permanent | Yes | Yes | --
Target | Target | Permanent | Yes | Yes | Yes

## Slide 9: Full list of diagnostics devices (From the lattice synoptic viewer)
 | ISrc | LEBT | RFQ | MEBT | DTL | SPK | MBL | HBL | HEBT | A2T | DmpL | Total
FC |  | 1 |  | 1 | 2 |  |  |  |  |  |  | 4
IBS |  |  |  |  |  | 1 | 1 |  |  |  |  | 2
BCM | 1 | 1 | 1 | 2 | 5 |  | 1 | 1 | 2 | 3 | 2 | 19
FBCM |  |  |  | 1 |  |  |  |  |  |  |  | 1
FBPM |  |  |  | 1 |  |  |  |  |  |  |  | 1
Dpl |  | 1 |  |  |  |  |  |  |  |  |  | 1
BPM |  |  |  | 7 | 15 | 14 | 9 | 21 | 16 | 12 | 4 | 98
BIF |  | 2 |  | 2 |  |  |  |  |  | 1 |  | 5
IPM |  |  |  |  |  | 1 | 3 | 1 |  |  |  | 5
EMU |  | 1 |  | 1 |  |  |  |  |  |  |  | 2
LBM |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 3
WS |  |  |  | 3 |  | 3 | 3 | 1 | 3 | 1 |  | 14
AptM |  |  |  |  |  |  |  |  |  | 3 | 1 | 4
Img |  |  |  |  |  |  |  |  |  | 2 | 1 | 3
nBLM |  |  |  | 4 | 42 | 26 | 2 | 2 | 2 | 4 |  | 82
icBLM |  |  |  |  | 5 | 52 | 36 | 84 | 49 | 34 | 6 | 266

## Slide 10: ISrc- LEBT commissioning configuration (Plan)
Solenoid 1 (Steerer 1)
Chopper
Collimator
Solenoid 2
(Steerer 2)
Iris
- FC
- Allison (H)
- Allison (V)
- Camera (H)
- Camera (V)
- Doppler
- Camera (H)
- Camera (V)
- BCM
Permanent tank
Commissioning tank
Beam stop
- Allison (V)
- Camera (H)
- Camera (V)
- FC
BCM
Source extraction

## Slide 11: ISrc- LEBT commissioning configuration (How we started on 2018-09-19)
Solenoid 1 (Steerer 1)
Chopper
Collimator
Solenoid 2
(Steerer 2)
Iris
- FC
- Allison (H)
- Allison (V)
- Camera (H)
- Camera (V)
- Doppler
- Camera (H)
- Camera (V)
- BCM
Permanent tank
Commissioning tank
Beam stop
- Allison (V)
- Camera (H)
- Camera (V)
- FC
BCM
Source extraction

## Slide 12: ISrc- LEBT commissioning configuration (How we started on 2018-09-19)
Solenoid 1 (Steerer 1)
Chopper
Collimator
Solenoid 2
(Steerer 2)
Iris
- FC
- Allison (H)
- Allison (V)
- Camera (H)
- Camera (V)
- Doppler
- Camera (H)
- Camera (V)
- BCM
Permanent tank
Commissioning tank
Beam stop
- Allison (V)
- Camera (H)
- Camera (V)
- FC
BCM
Source extraction
Running the real beam provides the best lesson, but we need to take balance.
  We should have had agreed on the minimal configuration, beforehand.
Only occasion to use an external stop and diagnostics. We could never come back to this configuration.
Only occasion, besides target, we can test the nominal beam parameters.

## Slide 13: NC linac commissioning configuration (updated)
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
DTL4 FC
ISrc - MEBT, DTL1
ISrc - DTL4
DTL2-3 not installed. DTL4 installed but not powered.
DTL2 FC placed right after DTL1. (With shielding?)
Temporary shield wall at DTL5.
No change from the baseline.

## Slide 14: Limits during the NC linac commissioning (ESS-0118232 under revision)
FC | Energy [MeV] | Ave curr lim [µA] | Probe lim [min/hour] | Slow-tuning lim [min/hour] | Fast-tuning lim [min/hour]
DTL4 | 22 | 8.8 | -- | -- | --
 | 40 | 3.0 | -- | 57 | 41
 | 57 | 1.4 | -- | 26 | 19
 | 74 | 1.2 | -- | 23 | 16
DTL2 | 22 | 8.8E-3 | 17 | 0.1 | 0.1
 | 40 | 3.0E-3 | 6 | 0.0 | 0.0
This configuration (FC shielding + wall) allows the NC linac beam and SC linac installation in parallel.
Prompt dose limit:
  3 µSv/h (supervised area)
  Averaged over 1 hour
Limits in dose and FC itself are comparable. If either is missing, the beam very limited.
Courtesy of K Batkov
DTL4
FC
Notes: Updated numbers for the single layer shielding wall
- 1300 µA, DTL1
- 1.57 µA, DTL4 and 74 MeV

## Slide 15: No special configuration after the NC linac commissioning
The beam is stopped with internal beam stops, tuning dump, or target.
  The tuning dump could bear with the 2.86 ms pulse but only at 1/30 Hz (12.5 kW).
Only available number of cryomodules change over time.
Tuning dump
Target

## Slide 16: Simple and or standard tuning
Standard linac/beamline tuning, requiring a dedicated application:
Linear optics verification
  Polarity check
  Beam based alignment
  Trajectory correction
RF phase and amplitude setting
Transverse matching with 3+ profile measurements
For beam transports and RFQ, many adjustments are done with a simple parameter(s) scan:
LEBT
  Iris verification
  Chopper verification
RFQ
  Amplitude scan
  Matching with LEBT solenoids scan
MEBT
  Chopper verification
  Collimator positioning
A2T (including dogleg)
  Achromatic condition verification
  Cross-over point verification
  Raster verification
Online beam physics application and diagnostics devices are keys to efficient beam commissioning.
Further details on tuning were presented in the past conference, workshops, and reviews.

## Slide 17: Could-be-challenging tuning (Excluding operational challenges such as protection)
ISrc optimization
  Unlike H- machines, we need to balance the current and beam quality.
Optics tuning of the non-periodic MEBT
Twiss and emittance reconstruction with a quad or cavity scan
  Space charge and beam loss require extra care.
Matching at the frequency jump
  Frequency jump at the SPK-MBL interface is the weakest point of our linac and requires a smooth matching. But, there is no nearly direct longitudinal measurement.
Beam loss mitigation
  We don't have the obvious beam loss cause of H- stripping.

## Slide 18: Summary (and questions)
Status of planning beam commissioning activities and their sequence:
  For the ISrc-LEBT stage, the developed plan is being executed and also updated to adopt to situation.
  For the NC linac stage, plan is being detailed.
  For the SC linac stage (starting in ~2.5 years), due to a resource limitation, we only have very high-level plan (and studies).
  Is there a rule of thumb for contingency of the beam commissioning?
  How detail we plan for each activity.
    Controlled document vs piece of code.
The schedules of the stages beyond the ISrc-LEBT are aggressive but using internal and permanent beam stops and diagnostics allow to come back and repeat the process in any given point, later.
  On the contrary, the ISrc-LEBT stage is unique.
  Comments/suggestions on this strategy?

## Slide 19: Backup

## Slide 20: ISrc- LEBT operations configuration
Solenoid 1 (Steerer 1)
Chopper
Collimator
Solenoid 2
(Steerer 2)
Iris
- FC
- Allison (H)
- Allison (V)
- Camera (H)
- Camera (V)
- Doppler
- Camera (H)
- Camera (V)
- BCM
Permanent tank
BCM
Source extraction

## Slide 21: NC linac commissioning configuration (baseline)
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
DTL4 FC
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
DTL4 FC
ISrc - MEBT, DTL1
ISrc - DTL4
DTL1-4 installed but only DTL1 powered.
MEBT and DTL2 FCs at their nominal locations.
Temporary shield wall + DTL4 FC with shielding at DTL5.
DTL1-4 powered.
MEBT and DTL2 FCs at their nominal locations.
Temporary shield wall + DTL4 FC with shielding at DTL5.