## Slide 1: A few commissioning experiences from a few hadron facilities (SNS, RHIC, AGS Booster, LANL PSR)
Thomas Shea
ESS

## Slide 2: Outline
Testing and commissioning overview – SNS v. ESS
Stories and Lessons, organized loosely by theme
  Integration
  Protection
  Verification
  Concurrent Development
  Human performance
End game and Organization

## Slide 3: Vertical Testing to interfaces then Horizontal Testing across interfaces
Beamline device
Signal Processing
Buffering
Shielding
configuration
beam interlock
Machine Protection Interfaces:
post mortem
cabling
component state
device health
Accelerator Interfaces:
Controls network
Timing/event
RF reference
Low-latency data
Also:
Power
Alignment
Cooling
EMI
Radiation

## Slide 4
Run #1: - RFQ at LBNL (2.5 MeV), Jan 25th through Feb 2002 - beam stop for design beam power
Run #2: - Front End at LBNL (2.5 MeV), Apr 4 to May 31, 2002 - beam stop for design beam power
Run #3: - Front End at ORNL (2.5 MeV), Nov 5, 2002 to Jan 31, 2003 - beam stop for design beam power
Run #4: - Front End, DTL tank 1, D-Plate (7.5 MeV), Aug 26 to Nov 17, 2003 - beam stop and radiation shield for design beam power
Run #5: - Front End & DTL tank 1,2,3 (39 MeV) Spring 2004 - Beam stop and radiation shield for reduced beam power (50us, 1Hz)
Run #6 : - Front End, DTL, CCL modules 1,2,3 (158 MeV) Fall 2004 - Beam stop and radiation shield for reduced beam power (50us, 1Hz)
Run #7 : - Front End, DTL, CCL, SCL (1 GeV), Aug 2005
Run #8 : - Front End, DTL, CCL, SCL, Ring (1 GeV), Feb 2006
Run #9 : - Front End, DTL, CCL , SCL, Ring, Target (1 GeV), April 28, 2006
2002
2003
2004
2005
2006
2
1
4
3
5
7
8
9
6
SNS commissioning ran in parallel with installation and testing

## Slide 5
2002
2003
2004
2005
2006
2
1
4
3
5
7
8
9
6
Awake at Night
2019
2018
2017
Source/
LEBT
RFQ/MEBT/DTL1
DTL 2-4
DTL5
+ Spokes
+ Medium Beta
SNS
ESS
Source/LEBT at Catania
Elliptical
Deployment at scale: superconducting linac devices
DTL 1
MEBT
improve
improve
2020
2021
2022
In the past, ESS appeared too compressed.
Now, I think that it looks achievable and similar to RHIC and SNS.
To target
Comparison

## Slide 6: Story time!
Notes: Not compete by any measure. Just a few vignettes to highlight experiences, both good and bad.

## Slide 7: Integration: SNS @LBNL Beam Physics and Systems meet at the Application Layer
Electrodes - LBNL
Electronics, NAD software - LANL
Cables & install - LBNL
Channel Access
the orbit app worked live from ORNL - simply initialize with the Process Variable names
EPICS screen
app
Network Attached Devices:
1 week to integrate all MEBT diagnostics at LBNL (from 4 labs) with timing and EPICS screens
* W. Blokland, 2001
“99% complete is 100% failure” *

## Slide 8: Integration Lessons re: Controls
Use of EPICS allowed modular deployment with a mature (but quite simple) control system toolkit
  Installation and vertical integration of network-attached devices performed rapidly and independently
  Minimal coordination needed (just check in at daily standup meeting)
Compared to RHIC
  RHIC commissioned the controls toolkit with the systems – painful!
  But RHIC controls started with some useful features that SNS lacked: triggered, continuous data acquisition; post-mortem; service-layer to manage device collections
Both:
  Built-in self test was very valuable
  Early availability of final timing and MPS systems was critical

## Slide 9: Integration Challenges: Electromagnetic Interference @ SNS
System | Signal level | Frequency Range | Comments on Noise
BCM | Tens of mV into 50 ohms | Few Hz to hundreds of MHz | Must heavily filter waveform and baseline subtract to reduce noise to few percent.
Loss | Hundreds of pA | < 35kHz | Noise on fast channel = 30% beam loss. Slow channel OK.
Faraday Cup/ Beam Stops | Hundreds of mV | DC – few MHz | Same issues as BCM low frequency range, but stronger signal.
Wire Scanners | microAmps | < 40 kHz | Noisy waveforms, but requirements exceeded by analysis and averaging
BPM | Ten mV into 50 ohms | Few MHz around RF (402.5 and 805 MHz) | Near 402.5 MHz RF systems, measure 805 MHz, and vise versa
c. 2004, In order of decreasing impact. Efforts focused on BCM and Loss systems
Notes: The lower frequency devices (DC through super-audio) are the most challenging. Many inductively coupled sources of interference, including switch-mode modulators.
Most BCMs could have been lower bandwidth devices with better S/N.

## Slide 10: Protection: Commission with safe “probe” pulses
  Specify performance with low current, short pulse (“safe”) beam such that beam can be lost most anywhere without causing damage
  Bonus: Allows tuning RF without impact of beam loading
  ESS probe beam will be critical for MPS commissioning
SNS vector receiver < 1 µs
1990 BNL Linac to Booster position electronics
(analog processing at twice RF frequency)
200 ns pulse
RHIC sextant, first turn: Orders of magnitude below nominal
Self triggering very helpful
Notes: devices happed to perform OK with safe beam, but in retrospect, more emphasis on this regime might help.

## Slide 11: Verification with beam: Difference Orbits in RHIC
Quickly verify optics and BPMs
Difference orbit: App uses online model, live and saved BPM readbacks, kick strength is free parameter, …
Recommendation: System owners lead system commissioning with beam, supported by machine commissioning/ops team. Then handoff.
SNS verified with beam in 7 sections
RHIC rings verified with beam in virtually one go
Notes: Similar in SNS and other machines
BNL linac to booster: orbit correction app provided similar function, nearly on day 1.

## Slide 12: Concurrent Development: SNS BPM Position/Phase Measurement
1.8 deg. at Berkeley, 2002
0.1 deg. at ORNL, 2 years later
“We know that BPMs in proton linacs don’t work”*
Worked even embedded within DTL
Measure harmonic away from RF (like @BNL Linac to Booster line)
Vector receivers (I-Q at SNS): retain phase
* R. Siemann, 2000
Results:
Scrap dedicated phase monitors
Didn’t really need measurements with energy degrader-faraday cups for DTL tuning
Diagnostics engineers helped design LLRF
With automated tuning apps, 8 hours reduced to ~30 min
Notes: Still kept many wire scanners and also built the energy degrader faraday cups just in case.

## Slide 13: Concurrent Development: Old School
There, I fixed it.
Phase measurement system in a week … at LANL in the 1980s
Formal procedures are necessary, but should support some use cases from the “good old days”
  Allow agility where appropriate
Good asset management can help
  LANL (1980s), AGS Booster (1990)
  Very limited data/document management
  RHIC/SNS (1990s/2000s)
  Better:
  Global database (required for deployment at scale),
  Primitive document management
  Inconsistently applied
ESS risks a step backward with lack of data-driven approach; heavy, document-driven configuration management

## Slide 14: Human Performance
Configuration errors
  Mitigate with thorough verification before beam
Shortcuts under pressure
  Noise filters on SNS machine protect inputs: now a suspected contributor to SC cavity degradation -> fixed this and also deployed differential BCM
Commission early and often, but not too often
  Usually enough staff to install and integrate systems, then support operations phase
  24 by 7 commissioning can add too much peak load -> burnout
RHIC commissioning, Aug 16, 1999 Owl shift summary loglook entry:
“…BPM reading in general
were difficult to interpret since some BPMS read data from other BPMs/plans/rings. We corrected the large orbit deviation at yo9-bv1… No progress, however, at the main Losses…”

## Slide 15: End Game: Integrated Accelerator, Target and Neutron Instruments

## Slide 16: Some considerations for ESS compared to short pulse sources
1. Ion Source and RFQ produces proton pulses with some current fluctuation
Accelerator and Beam Transport
Two dominant causes of neutron intensity fluctuation
2. Raster System scans proton beam across target; moderator coupling is position dependent
Low loss (< 1%) acceleration and transport Low energy variation (+/-1.5 %) allowed
Rotating target (but controls are simpler than existing chopper controls)
Long Pulse source couples machine and neutron instruments
Pulse by pulse modulation requires full timing system functionality

## Slide 17: Early Operations and Performance Ramp
RHIC highest priority: gradual accumulation of integrated luminosity
SNS chose to ramp power rapidly rather than staying conservative. Shook out issues during a period when lower availability was tolerated. Only a few years of this will be tolerated by user community: work fast!
Functionality: The minimum for commissioning may not be enough for this phase and there is limited time for new development.
  First proton functionality
  Roadmap to full functionality, back by design work during construction phase

## Slide 18: Organization
SNS had area managers, RHIC did not (topical management). Both ways worked for commissioning
All: Daily standup very important to coordinate physical work
RHIC and SNS: Weekly meeting with machine director and work package managers
  Line aligned with project
  Rapid decisions
Managing the end game
  SNS rolled partners off too early. Partner engagement through commissioning aligns motivation with project goals
  Instruments saw no need to share data with control room. User engagement may soften transition to operations
Recognize that the organization is being commissioned

## Slide 19: thanks
Particular thanks to many Beam Diagnostics and Beam Physics colleagues at BNL, LANL, LBNL, and ORNL.
Input from: M. Plum, J. Galambos, A. Aleksandrov, W. Blokland, A Shishlo, A. Zhukov, T. Satogata, S. Assadi, J. Staples, A. Ratti, J. Power, A. Jason, D. Purcell, C. Deibele, T. McManamy, C. Goetz, R. Witkover