## Sheet1
| PLAT FORM | SYSTEM | LABEL | DETAIL | UNIT COST | BUDGET | RESPONSIBLE | RESPONSIBLE |  | READY BY 1st |  |  | NEEDED FOR …. [needed by DATE, POSSIBLE, SPECIFIC, LATER]
[7 empty] | BUDGET | EXECUTION |  |  |  |  | LOKI | SKADI | ESTIA | FREIA
| INSTR | cold commissioning complete |  | TG5 Date | [8 empty] | Q1/22 | Q1/21 | Q1/19 | Q2/23
| INSTR | hot commissioning complete |  | TG6 Date | [8 empty] | Q1/23 | Q2/22 | Q2/21 | Q3/24
| CHECKED | date checked by instrument
ID | PLATFORM | SYSTEM | LABEL | DETAIL | UNIT COST | BUDGET | RESPONSIBLE | RESPONSIBLE2 | EARLY/LATE (preops) | READY BY 1st | Start date | LEAD TIME | LOKI | SKADI | ESTIA | FREIA | Notes | Instrument index | See AH6 | For selecting multiple instruments, type y where needed in "include" column then sort or filter on column AE.
FL0001 | FLUCO | Humidity chamber SPEC |  | Hum. cham. wide angle | 100 | NSS | SAD |  |  | 21/Q3 | [7 empty] | 32752 | FALSE | N.b. if using the read-only link, download and save a copy to change this
FL0002 | FLUCO | Humidity chamber SANS |  |  | 120 | NSS | SAD |  |  | 21/Q3 |  |  | Q3/22 | 21/Q3 |  |  |  | 32755 | TRUE | Instrument | include (y/n) | index
FL0003 | FLUCO | Humidity REF |  |  | 100 | OPS | SAD |  |  | LATER |  |  |  | POSSIBLE | LATER | POSSIBLE |  | 32766 | TRUE | LOKI | y | 1
FL0004 | FLUCO | Humidifier |  |  | 50 | NSS | NMX | NMX |  | 22/Q1 | [7 empty] | 32752 | FALSE | SKADI | y | 2
FL0005 | FLUCO | HPLC pump incl flow cell, 4 channel, switch |  |  | 60 | FUNDED ? | LOKI | LOKI (SAD integ.) |  | 21/Q3 |  |  | SPECIFIC |  |  |  |  | 32753 | TRUE | ESTIA | y | 4
FL0006 | FLUCO | HPLC pump, 4 channel, switch |  |  | 15 | NSS | ESTIA | (SAD) |  | 21/Q1 |  |  |  |  | SPECIFIC |  |  | 32756 | TRUE | FREIA | y | 8
FL0007 | FLUCO | HPLC pump, 4 channel, switch |  |  | 55 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE | NMX | n | 16
FL0008 | FLUCO | injection system, syringe pump |  |  | 40 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE | MAGIC | n | 32
FL0009 | FLUCO | injection system, syringe pump |  |  | 40 | NSS | ESTIA | (SAD) |  | 21/Q1 |  |  |  |  | SPECIFIC |  |  | 32756 | TRUE | DREAM | n | 64
FL0010 | FLUCO | injection system, syringe pump |  |  | 40 | NSS | SAD | SAD |  | 21/Q3 |  |  |  | 21/Q3 |  | Q1/23 |  | 32762 | TRUE | HEIMDAL | n | 128
FL0011 | FLUCO | stopped flow systems |  |  | 120 | NSS | SAD | SAD |  | 20/Q3 |  |  | POSSIBLE | 20/Q3 | LATER | Q1/23 |  | 32767 | TRUE | BEER | n | 256
FL0012 | FLUCO | rotating sample holder |  |  | tbd | NSS | LOKI | (SAD) |  | 21/Q3 |  |  | Q3/21 | POSSIBLE |  |  |  | 32755 | TRUE | ODIN | n | 512
FL0013 | FLUCO | shear cell couette |  |  | 20 | NSS | SAD |  |  | 21/Q3 |  |  | Q3/22 | 21/Q3 | LATER |  |  | 32759 | TRUE | CSPEC | n | 1024
FL0014 | FLUCO | shear cell plate plate |  |  | 20 | NSS | SAD |  |  | 21/Q3 |  |  | Q3/22 | 21/Q3 | LATER |  |  | 32759 | TRUE | TREX | n | 2048
FL0015 | FLUCO | rheometer |  |  | 250 | NSS | SAD |  |  | 21/Q3 |  |  | Q3/22 | 21/Q3 |  | Q1/23 |  | 32763 | TRUE | BIFROST | n | 4096
FL0016 | FLUCO | gas processing #1 |  |  | 200 | NSS | SAD | EE |  | 21/Q1 |  |  | possible | possible | LATER | Q1/23 |  | 32767 | TRUE | MIRACLES | n | 8192
FL0017 | FLUCO | gas processing #2 |  |  | 200 | NSS | SAD | EE |  | 21/Q1 |  |  | possible | possible | LATER | Q1/23 |  | 32767 | TRUE | VESPA | n | 16384
FL0018 | FLUCO | vacuum box |  |  | 30 | NSS | SAD | SAD |  | 00EARLY | [5 empty] | LATER |  | 32760 | TRUE |  | 15
FL0022 | FLUCO | Julabo-type chiller / heater #4 |  | REF | 17 | NSS | ESTIA | (SAD) |  | 21/Q1 |  |  |  |  | SPECIFIC |  |  | 32756 | TRUE
FL0023 | FLUCO | Julabo-type chiller / heater #4 |  | REF | 17 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0024 | FLUCO | gas blower (thermal jet) |  |  | 150 | NSS | SAD | SAD |  | 21/Q3 |  |  | Q3/22 | 21/Q3 |  |  |  | 32755 | TRUE
FL0026 | FLUCO | Bio furnace 8 positions |  |  | 125 | OPS | MIRACLES |  |  | 23/Q1 | [7 empty] | 32752 | FALSE
FL0027 | FLUCO | SANS changer some samples |  | indiv T-Ctrl. In-Kind RUC | 50 | NSS | SAD | RUC |  | 00EARLY |  |  | Q3/21 | 21/Q3 |  |  |  | 32755 | TRUE
FL0028 | FLUCO | SANS changer incl. quartz cuvettes |  | thermalised, mulitple samples | tbc | NSS | LOKI | (SAD) |  | 20/Q2 |  |  | 20/Q2 |  |  |  |  | 32753 | TRUE
FL0029 | FLUCO | SANS changer incl. quartz cuvettes |  | ind. thermalised, multiple samples | tbc | NSS | SKADI |  |  | 20/Q3 |  |  |  | SPECIFIC |  |  |  | 32754 | TRUE
FL0030 | FLUCO | sample changer (translation table) |  | incl sample holder | 31 | NSS | ESTIA |  |  | 21/Q1 |  |  |  |  | Q2/21 |  |  | 32756 | TRUE
FL0030 | FLUCO | sample changer (chain drive?) |  |  | tbd | NSS | ESTIA | (SAD) |  | 21/Q2 |  |  |  |  | Q2/21 |  |  | 32756 | TRUE
FL0031 | FLUCO | Solid liquid & liquid liquid cells |  |  | 60 | NSS | ESTIA | (SAD) |  | 21/Q1 |  |  |  |  | Q2/21 | Q1/23 |  | 32764 | TRUE
FL0032 | FLUCO | troughs Langmuir |  |  | 55 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0033 | FLUCO | troughs air-liquid |  |  | 40 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0034 | FLUCO | troughs Langmuir |  |  | 55 | OPS | FREIA |  |  | 24/Q2 | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0035 | FLUCO | troughs air-liquid |  |  | 40 | OPS | FREIA |  |  | 24/Q2 | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0036 | FLUCO | overflowing cylinder |  |  | 35 | OPS | FREIA |  |  | LATER | [5 empty] | SPECIFIC |  | 32760 | TRUE
FL0037 | FLUCO | potentiostat |  |  | 30 | OPS | ESTIA |  |  | 22/Q3 |  |  |  |  | Q1/23 | LATER |  | 32764 | TRUE
FL0038 | FLUCO | reaction cells |  |  | tbc | EXTERN | MIRACLES |  |  | 25/Q1 | [7 empty] | 32752 | FALSE
FL0039 | FLUCO | in-situ light scattering |  |  | 120 | EXTERN | SAD |  |  | 25/Q1 |  |  |  | POSSIBLE | LATER |  |  | 32758 | TRUE
FL0040 | FLUCO | in-situ gas absorption |  |  | 250 | EXTERN | SAD |  |  | 25/Q1 | [7 empty] | 32752 | FALSE
FL0041 | FLUCO | in-situ thermal analysis meas. |  |  | 100 | EXTERN | SAD |  |  | 25/Q1 | [7 empty] | 32752 | FALSE
FL0042 | FLUCO | Kerr effect add -on |  |  | 25 | EXTERN | ESTIA |  |  | LATER |  |  |  |  | LATER |  |  | 32756 | TRUE
FL0043 | FLUCO | Laser Pump Probe System |  |  | 200 | NSS | SAD | EE |  | 00EARLY |  |  |  | POSSIBLE | LATER |  |  | 32758 | TRUE
FL0044 | FLUCO | Ortho-Para-hydrogen Generator |  |  | 100 | OPS | SAD |  |  | 23/Q1 | [7 empty] | 32752 | FALSE
FL0045 | FLUCO | shear cell - confined geometry |  | Polymers in confinement - VR Grant |  | FUNDED | VR | AJJ |  | 21/Q1 |  |  | POSSIBLE | POSSIBLE | POSSIBLE | POSSIBLE |  | 32767 | TRUE
FL0046 | FLUCO | Flexiprobe #1 - NNNN |  |  |  | FUNDED | VERBUND | SAD | [9 empty] | 32752 | FALSE
FLxxxx | FLUCO | SANS changer incl. quartz cuvettes |  | non-thermalised | tbc | NSS | LOKI | SAD |  | 20/Q2 |  |  | 20/Q2 |  |  |  |  | 32753 | TRUE
FLxxxx | FLUCO | SANS changer incl. quartz cuvettes |  | non-thermalised | tbc | NSS | SKADI | SKADI |  | 20/Q3 |  |  |  | SPECIFIC |  |  |  | 32754 | TRUE
FLxxxx | FLUCO | stopped flow systems |  |  | 100 | NSS | SKADI | SKADI/LOKI shared |  | 20/Q3 |  |  | POSSIBLE | 20/Q3 | LATER | Q1/23 |  | 32767 | TRUE
M0001 | OTHER | Robotic sample changer (mail in) |  |  | tbd | TBC | HEIMDAL |  |  | 25/Q1 | [7 empty] | 32752 | FALSE
M0002 | OTHER | Robotic sample changer (mail in) |  |  |  | OPS | DREAM | [10 empty] | 32752 | FALSE
M0003 | MESI | Robotic Modular Platform | incl. MCA |  |  | NSS | SAD |  |  | 00EARLY | [7 empty] | 32752 | FALSE
P0001 | PREMP | Diamond Anvil Cell System | PRESSURE | incl collab. R&D | 150 | NSS | SAD | SAD |  | 21/Q1 |  |  | POSSIBLE | possible |  |  |  | 32755 | TRUE
P0002 | PREMP | Paris-Edinburgh Cell | PRESSURE |  | 200 | NSS | SAD |  |  | 21/Q1 | [7 empty] | 32752 | FALSE
P0003 | PREMP | Clamp cell < 1.5GPa | PRESSURE |  | 50 | NSS | SAD |  |  | 21/Q2 |  |  |  | POSSIBLE |  |  |  | 32754 | TRUE
P0004 | PREMP | Gas cell < 0.7GPa | PRESSURE |  | 50 | NSS | SAD |  |  | 21/Q2 | [7 empty] | 32752 | FALSE
P0005 | PREMP | Raman system | PRESSURE | for high pressure | 50 | NSS | SAD | SAD |  | 22/Q3 | [6 empty] | might not be the same system | 32752 | FALSE
P0006 | PREMP | Portable laser heating | PRESSURE |  | 150 | NSS | SAD |  |  | 23/Q1 |  |  |  |  | POSSIBLE | LATER |  | 32764 | TRUE
P0007 | PREMP | Corrosive gas manifold | PRESSURE |  | 50 | NSS | SAD |  |  | 23/Q4 |  |  |  |  | POSSIBLE |  |  | 32756 | TRUE
P0008 | PREMP | Pressure cell low temperature | PRESSURE |  | tbc | OPS | ESTIA |  |  | LATER |  |  |  |  | LATER |  |  | 32756 | TRUE
P0009 | PREMP | portable stress rig | MP |  | 50 | NSS | SAD |  |  | 23/Q1 |  |  | possible | POSSIBLE |  | POSSIBLE |  | 32763 | TRUE
P0010 | PREMP | stress strain rig | MP |  | 300 | NSS | SAD | (HZG/BEER) |  | 21/Q1 | [6 empty] | needs to be covered by ESS if not EXTERNAL | 32752 | FALSE
P0011 | PREMP | dilatometer | MP |  | 400 | NSS | SAD | (BEER) |  | 22/Q1 | [7 empty] | 32752 | FALSE
P0012 | PREMP | stir welding | MP |  | 200 | OPS | BEER | (BEER) |  | 23/Q1 | [7 empty] | 32752 | FALSE
P0013 | PREMP | gleeble | MP |  | 1000 | EXTERN | BEER |  |  | 22/Q3 | [7 empty] | 32752 | FALSE
P0014 | OTHER | kinematic mount | ALIGN | R&D available | tbd | NSS | SAD | SAD |  | 00EARLY |  |  |  |  | Q1/21 |  |  | 32756 | TRUE
P0015 | OTHER | kinematic mount, laser tracker | ALIGN |  | 8 | NSS | ESTIA |  |  | 21/Q1 |  |  |  |  | SPECIFIC |  |  | 32756 | TRUE
P0016 | OTHER | kinematic mount, laser tracker | ALIGN |  | 38 | NSS | VESPA |  |  | 23/Q2 | [7 empty] | 32752 | FALSE
P0017 | OTHER | laser interferometer alignment | ALIGN | for liquid surface | 35 | OPS | FREIA |  |  | 23/Q1 | [5 empty] | SPECIFIC |  | 32760 | TRUE
T0001 | TEFI | Horizontal 11T cryomagnet | MAGNET | Split coil, SANS/refl focused | 450 | NSS | SAD |  | Early | 22/Q1 | 19/Q1 | 3-4 yr |  | Q1/23 | possible |  |  | 32758 | TRUE
T0002 | TEFI | 2.5T Warm bore cryomagnet | MAGNET | incl . Changer | 335 | NSS | SAD | FR/LLB | early | 22/Q1 | 19/Q1 | 3 yr | Q3/22 |  | Q1/22 |  |  | 32757 | TRUE
T0003 | TEFI | Vertical 8T cryomagnet | MAGNET | large opening | 1000 | NSS | SAD | FR/LLB | early | 22/Q2 | 17/Q3 | 3-4 yr |  |  | Q1/23 |  | optimsed first for Magic | 32756 | TRUE
T0004 | TEFI | Vertical 15T cryomagnet | MAGNET | split coil (used) | 50 | NSS | SAD | DE? | early | 21/Q1 | 17/Q3 | 1yr | [5 empty] | 32752 | FALSE
T0005 | TEFI | Vertical 5T cryomagnet | MAGNET | split coil (used) | tbd | NSS | SAD | DE? | early | 21/Q1 | 20/Q1 | 1yr | [5 empty] | 32752 | FALSE
T0006 | TEFI | Vertical hybrid cryomagnet | MAGNET | LTc - HTc | 2000 | EXTERN | BIFROST |  | late | 24/Q2 |  | 4yr | [5 empty] | 32752 | FALSE
T0007 | TEFI | Pulsed Magnet | MAGNET |  | tbd | EXTERN | SAD |  | late | LATER |  | 3-4year |  | possible | possible | LATER |  | 32766 | TRUE
T0008 | TEFI | 1T Electromagnet | MAGNET |  | 50 | NSS | SAD | JULICH/ SAD | early | 21/Q1 | 19/Q3 | 18 months | Q3/22 |  | Q2/21 |  |  | 32757 | TRUE
T0009 | TEFI | 2.5T Warm bore cryomagnet #2 | MAGNET | Small footprint | 280 | NSS | SAD | FR/LLB | early | 22/Q3 | 20/Q3 | 24 month | LATER | LATER |  | LATER |  | 32763 | TRUE
T0010 | TEFI | 5T Warm bore cryomagnet | MAGNET |  | 400 | NSS | SAD | FR/LLB | early | 22/Q3 | 20/Q3 | 3-4 yr | LATER | LATER |  | LATER |  | 32763 | TRUE
T0011 | TEFI | 3D Helmholtz electromagnet | MAGNET | Low priority | 100 | OPS | SAD |  | late | 22/Q3 |  | 2 yr |  |  | Q4/24 |  |  | 32756 | TRUE
T0012 | TEFI | 3D Cryomagnet | MAGNET | Low priority | 400 | OPS | SAD |  | early | 21/Q1 |  | 3-4year |  |  | Q4/24 |  |  | 32756 | TRUE
T0013 | TEFI | CryoStream & linear changer | CRYO |  | tbc | OPS | DREAM |  | (late) | 21/Q1 |  |  |  |  | POSSIBLE |  |  | 32756 | TRUE
T0014 | TEFI | CryoStream & robotics | CRYO |  | 40 | NSS | NMX | NMX |  | 22/Q1 |  |  |  |  | POSSIBLE |  |  | 32756 | TRUE
T0015 | TEFI | FlowCryostat #1 | CRYO |  | 20 | NSS | ESTIA | ESTIA | (early) | 21/Q1 |  | 1yr |  |  | Q2/21 |  |  | 32756 | TRUE
T0016 | TEFI | FlowCryostat #2 | CRYO |  | 20 | OPS | ESTIA |  | (late) | LATER |  | 1yr |  |  | SPECIFIC |  |  | 32756 | TRUE
T0017 | TEFI | FlowCryostat #3 | CRYO |  | 20 | OPS | ESTIA |  | (late) | LATER |  | 1yr |  |  | SPECIFIC |  |  | 32756 | TRUE
T0018 | TEFI | HT add-on for flow cryostat | CRYO |  | 20 | OPS | ESTIA |  | (late) | 22/Q4 |  |  |  |  | SPECIFIC |  |  | 32756 | TRUE
T0019 | TEFI | Dry Cryostat #1 PTR, CCR | CRYO |  | 100 | NSS | SAD | FR/LLB | early | 21/Q1 | 18/Q3 | 24 month | Q3/22 | possible |  |  |  | 32755 | TRUE
T0020 | TEFI | Dry Cryostat #2 PTR, CCR | CRYO | low background | 100 | NSS | SAD | FR/LLB | late | 22/Q1 | 20/Q1 | 24 month | [5 empty] | 32752 | FALSE
T0021 | TEFI | Dry Cryostat #3 spec. geom. | CRYO | top loading | 100 | NSS | VESPA | VESPA | (late) | 23/Q2 |  | 24 month | [5 empty] | 32752 | FALSE
T0022 | TEFI | Wet Cryostat OC #1 | CRYO | Tmin < 2 K | 50 | NSS | SAD | FR/LLB | early | 21/Q1 | 19/Q1 | 2 yr | Q3/22 | Q1/23 |  |  |  | 32755 | TRUE
T0023 | TEFI | Wet Cryostat OC #2 | CRYO | Tmin < 2 K | 50 | NSS | SAD | FR/LLB | early | 21/Q1 | 19/Q1 |  | Q3/22 | Q1/23 |  |  |  | 32755 | TRUE
T0024 | TEFI | 3He / 4He Dilution Fridge #1 | ULT | Tmin < 0.1 K | 250 | NSS | SAD | FR/LLB | early | 21/Q1 | 18/Q3 |  |  | possible | POSSIBLE |  |  | 32758 | TRUE
T0025 | TEFI | 3He / 4He Dilution Fridge #2 | ULT | Tmin < 0.1 K | 250 | NSS | SAD | FR/LLB | early | 21/Q1 | 18/Q3 |  |  | possible | POSSIBLE |  |  | 32758 | TRUE
T0026 | TEFI | 3He Sorption Fridge | ULT | Tmin < 0.5 K | 150 | NSS | SAD | FR/LLB | early | 21/Q1 | 19/Q1 | 24 month |  | possible | POSSIBLE |  |  | 32758 | TRUE
T0027 | TEFI | CryoFurnace #1 general | CRYOFURNACE | Tmax > 600K | 50 | NSS | SAD | FR/LLB | early | 21/Q4 | 19/Q4 | 24 months | Q3/22 |  | POSSIBLE |  |  | 32757 | TRUE
T0028 | TEFI | CryoFurnace #2 diffraction | CRYOFURNACE | Tmax > 600K | 50 | NSS | MAGIC | LLB | (early) | 21/Q1 | [7 empty] | 32752 | FALSE
T0029 | TEFI | CryoFurnace #3 incl 20 changer | CRYOFURNACE | 4K < T < 800K | 300 | NSS | DREAM | JULICH | (early) | 21/Q1 |  |  |  |  | POSSIBLE |  |  | 32756 | TRUE
T0030 | TEFI | CryoFurnace #4 incl 6 changer | CRYOFURNACE | 4K < T < 600K | 150 | NSS | CSPEC | tbd | (early) | 21/Q1 | [7 empty] | 32752 | FALSE
T0031 | TEFI | CryoFurnace #5 incl 20 changer | CRYOFURNACE | 4K < T < 800K | 300 | OPS | HEIMDAL |  | (late) | 25/Q1 |  |  |  |  | POSSIBLE |  |  | 32756 | TRUE
T0032 | TEFI | CryoFurnace #6 incl 6 changer | CRYOFURNACE | 4K < T < 600K | 150 | OPS | MIRACLES |  | (late) | 23/Q1 | [7 empty] | 32752 | FALSE
T0033 | TEFI | CryoFurnace #7, spectrometer | CRYOFURNACE | Tmax > 600K | 60 | NSS | TREX | LLB? | (early) | 21/Q4 | [7 empty] | 32752 | FALSE
T0034 | TEFI | CryoFurnace #8, spectrometer | CRYOSTAT | 1.5 < T < 300K | 60 | NSS | BIFROST |  | (early) | 21/Q4 | [7 empty] | 32752 | FALSE
T0035 | TEFI | HT Vacuum Furnace #1 | FURNACE |  | 40 | NSS | SAD | LLB/TUM? | early | 21/Q1 | 19/Q1 | 24 month | possible | possible | Q4/24 |  |  | 32759 | TRUE
T0036 | TEFI | HT Vacuum Furnace #2 | FURNACE |  | 40 | NSS | SAD | LLB/TUM? | early | 21/Q1 | 19/Q1 | 24 month | possible | possible | Q4/24 |  |  | 32759 | TRUE
T0037 | TEFI | IR Furnace | FURNACE |  | 50 | NSS | SAD | LLB/TUM? | early | 21/Q2 | 19/Q2 | 24 month | possible | possible | possible | LATER |  | 32767 | TRUE
T0038 | TEFI | 6 kV HV supply #1 | HV |  | 25 | NSS | SAD |  | early | 21/Q2 | 19/Q3 | 18 months |  | Q1/22 | Q4/24 |  |  | 32758 | TRUE
T0039 | TEFI | 6 kV HV supply #2 | HV |  | 25 | NSS | SAD |  | early | 21/Q2 | 19/Q3 | 18 months |  | Q1/22 | Q1/24 |  |  | 32758 | TRUE
T0040 | TEFI | 6 kV HV supply #3 | HV |  | 25 | OPS | SAD | FR/LLB? | early | LATER |  |  |  | Q1/22 | Q1/23 |  |  | 32758 | TRUE
T0041 | TEFI | peltier sub-cryostat stick |  | in-situ add on | 125 | NSS | SAD | RUC | early | 00EARLY | [7 empty] | 32752 | FALSE
T0042 | TEFI | in situ AC susceptiblity |  | in-situ add on | 30 | NSS | SAD | SAD | early | 00EARLY | [7 empty] | 32752 | FALSE
T0043 | TEFI | electrostatic levitator |  |  | tbd | OPS | TREX |  | late | 24/Q3 | [6 empty] | could potentially be pooled | 32752 | FALSE
T0044 | TEFI | aerodynamic levitator |  |  | tbd | TBD | DREAM |  | late | TBD | [7 empty] | 32752 | FALSE
T0045 | TEFI | LHe vessels / equipment |  | INFRASTR. | 250 | NSS | SAD | SAD | early | 21/Q1 | 18/Q3 | 24 month | [5 empty] | 32752 | FALSE
T0046 | TEFI | vacuum equipment |  | INFRASTR. | 300 | SLA VAC | VAC | VAC | (early) | 21/Q1 | [7 empty] | 32752 | FALSE
T0047 | TEFI | 3He Sorption Fridge |  |  | 150 | NSS | CSPEC | [10 empty] | 32752 | FALSE
T0048 | TEFI | Vertical split pair for spectroscopy | MAGNET | >14T low background | 500 | [12 empty] | 32752 | FALSE