## Slide 1: Linac Warm Units - Update (Beam Transport Modules)
Richard Smith
STFC Daresbury Laboratory
November 2018

## Slide 2: STFC
UK Astronomy Technology Centre
Edinburgh, Scotland
Polaris House
Swindon, Wiltshire
Chilbolton Observatory
Stockbridge, Hampshire
Daresbury Laboratory
Sci-Tech Daresbury Warrington, Cheshire
Rutherford Appleton Laboratory
Harwell Didcot, Oxfordshire
Boulby Underground Laboratory
North Yorkshire
Notes: The science and technology facilities council are one of Europe's largest research organisations. Employs 1934 staff mostly based across the six sites in the UK.

## Slide 3: STFC, Daresbury Laboratory
Notes: At Daresbury Laboratory there are approximately 700 employees working with over 120 different research organisations.

## Slide 4: Project Team

## Slide 5: Core Project Team
Paul Aden
  Project manager
Keith Middleman
  Deputy PM, Vacuum Work Package Manager
Neil Geddes
  Project Sponsor
Richard Smith
  Project Engineer
Olly Poyntz-Wright
  Mechanical Engineer
Danish Naeem
  Quality & Mechanical Engineer
Alan Muir, Philip Craine, Ken Davies,
  Mechanical Design Engineers
George Miller, Luke Bayden, Tom Cornes, Dave Coleman, Ninad Pattalwar, Stuart Wildes
  Core Technicians
Notes: The team is expanding to cope with the work and the processing that is required

## Slide 6: Overview of the scope

## Slide 7: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  52 Beam pipe modules
  74 Linac Warm Units
  3 Differential pumping systems
  4 mobile installation cleanrooms
Notes: Over the next four years we have been asked to delivery …

## Slide 8: Typical LWU Design
Aluminium slotted girder
BPM on entrance or exit
Semi–kinematic
girder adjustment
Pedestals
Quadrupole Magnets
Fiducials, laser tracker alignment
-100µm Accuracy
Built in lifting points
Low Particulate Chamber
- ISO 5 or better

## Slide 9
2 LWU Prototypes delivered
Notes: One unit in the tunnel and one at the RATS storage facility

## Slide 10: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  52 Dummy Cryo Modules
  74 Linac Warm Units
  3 Differential pumping systems
  4 mobile installation cleanrooms
Notes: Over the next four years we have been asked to delivery …

## Slide 11
22 DCM (6 metre) + all stands delivered
Notes: All stands for the tunnel have been delivered

## Slide 12
12 more DCM ready to ship

## Slide 13: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  52 Dummy Cryo Modules
  74 Linac Warm Units
  3 Differential pumping systems
  4 mobile installation cleanrooms
Notes: Over the next four years we have been asked to delivery …

## Slide 14
First elliptical vessels received at STFC…
Notes: Vessels from two different suppliers, ITL and Kurt J Lesker

## Slide 15
…cleaned, baked and vacuum tested…
… to discover they leaked!

## Slide 16
However, not at the BPM region
(Issues are identifiable and fixable)
Notes: Leaks discovered on the upper flange weld on one vessel…. And bellows on another. This was due to poor bracing on the bellows during transit (lessons learned).

## Slide 17: BTM WP Scope
Date | LWUs
26/01/2019 | 1
25/07/2019 | 30
21/01/2020 | 27
19/07/2020 | 16
First Magnet pair not due until Jan
LWU Milestones
Notes: Over the next four years we have been asked to delivery …

## Slide 18
However, not at the BPM region
(lessons to be learned!)
All LWU pedestals manufactured
Notes: Ready to be shipped, to be delivered Jan/Feb

## Slide 19: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  52 Dummy Cryo Modules
  74 Linac Warm Units
  3 Differential pumping systems
  4 mobile installation cleanrooms
Notes: Over the next four years we have been asked to delivery …

## Slide 20: Differential Pumping Sections
Low energy pumping system
Notes: Designs for the differential pumping stations are complete and ready to order

## Slide 21: Differential Pumping Sections
High energy pumping system
Notes: Designs for the differential pumping stations are complete and ready to order

## Slide 22: BTM WP Scope
To design, procurement and assemble;
  2 Prototypes
  52 Dummy Cryo Modules
  74 Linac Warm Units
  3 Differential pumping systems
  4 mobile installation cleanrooms

## Slide 23
However, not at the BPM region
(lessons to be learned!)
All LWU pedestals manufactured
2 Mobile cleanrooms delivered…
…2 more before year end
Notes: Two clean rooms have been delivered.. One is at the RATS storage facility and one is ready to be unboxed and signed off this week

## Slide 24: Schedule

## Slide 25: Schedule
BTM Assembly
2015 | 2016 | 2017 | 2018 | 2019 | 2020
Magnet Deliveries
Installation Cleanrooms
Prototype 1
Prototype 2
BPM Deliveries
BTM Design
BP Assembly
LWU Assembly
Tunnel available (May 2017)
LWU by
March 2020
CDR
Prototype Cleanrooms
CDR 2

## Slide 26: Overview
LWUs
LWUs & Beam Pipe
LWUs & Beam Pipe
LWUs
LWUs & Beam Pipe
Differential Pumping System
Differential Pumping System
Beam Pipe
Notes: What STFC are delivering

## Slide 27: Progress
Total length to process 480m
Total shipped 204m (42.5%)
Notes: Progress by length

## Slide 28: Milestones in TA
Deliverables | Final Delivery Deadline
ESS Vacuum Laboratory consisting of (see Chapter 2.1): [PTF] Particle Test Facility [GCF] Gauge Calibration Facility [OGF] Outgassing Facility [VIF] Vacuum Integration Facility technical data as specified in [PTF], [GCF], [OGF], [VIF] | 01 July 2015
Relevant Technical data package for PDR. See 4.4.2.1 | 2015 (Pre-PDR)
Qty 3 x Dummy Test Chambers | March 2016
Qty 1 x 1st Prototype | June 2016
Qty 1 x 2nd Prototype | August 2016
Technical data package as specified for 1st CDR. See 4.4.2.2 | CDR, June 2016
Technical data package as specified for 2st CDR. See 4.4.2.2 | CDR, July 2018
Qty 3 x Mobile Clean Rooms | July 2018
Qty 57 x Beam Pipe Units | July 2019
Qty 71 x LWUs | April 2020
Qty 2 x Differential Pumping Systems | April 2020
Qty 2 x Dipole Chambers | April 2020
Technical data package as specified for SAR. See 4.4.3.2. | SAR, minus 5 weeks
Delivery of Final Report and documentation package for Supply. See 4.4.5 and 4.4.6 | 31 December 2020
Vacuum Technician Support during installation at STFC site. See 4.1.2.1.6 | 2018-2019, dates to be agreed

## Slide 29: ESS visit
Notes: In September we welcomed some of the ESS vacuum group for 3 weeks

## Slide 30: ESS Visit - Deliverable
Extremely productive three weeks:
  Design reviews
  Mobile Cleanroom sign off
  Vacuum assembly work
  Mechanical Assembly work
  Cleanroom operation
  Flange assembly discussions
  Plus some rather enjoyable social events

## Slide 31
ESS Visit to STFC
Notes: Fabio, Kristell and Ralf from ESS vacuum group discussing survey and alignment of the magnets and LWU’s with Ryan. Using a module from Daresbury’s compact linear accelerator as an example.

## Slide 32
ESS Vacuum Group in the STFC Cleanrooms
Notes: The team from ESS was shown the procedure for cleaning and particle counting the vessels in the clean room. Operates at ISO 3 class (static) Kristell is using a lance to blow filtered nitrogen into the vessel and Tom is positioning the counter head near the exit.

## Slide 33
Vacuum Group in the clean assembly area
Notes: Assembly procedures

## Slide 34
Vac Lab Processing procedures
Notes: Initial cleaning phase once the vessels are received from the manufacturer. Years of vacuum cleaning expertise at Daresbury has enabled the process to be refined.

## Slide 35
ETC LWU Mechanical Build
Notes: The vacuum team from ESS were shown how to assemble a complete LWU from the ground up.

## Slide 36
Notes: Snapshot of Fabio and Kristell assembling the support structure for the LWU and preparing an LWU for processing.

## Slide 37
Sampled the Great British Weather
Notes: No trip to the UK is complete without sampling the fine British weather.

## Slide 38
Knowledge transfer between teams
Notes: The Daresbury technicians are going to spend time with ESS vacuum group at ESS

## Slide 39: LWU to cryo-module connection

## Slide 40
LWU to Cryo-module bellows connection
Notes: STFC have put a lot of though into finding the optimal method of connecting the two modules that limits particulate generation that could contaminate the accelerator.

## Slide 41
Using VR to view LWU to Cryo-module
Notes: STFC technicians visualising the bellows to cryo-module connection in VR and the limited room to manoeuvre

## Slide 42
Using VR to view LWU to Cryo-module

## Slide 43
LWU to Cryo-module mock-up
Notes: We created a physical mock-up of the connection to allow us to trial different methods and tooling that would help create a low particulate vacuum connection

## Slide 44
LWU to Cryo-module - tests ongoing
Notes: The vacuum team from ESS also took part in some of the trials… this work is ongoing (XYZ table to be tested soon)

## Slide 45: Shock and vibration accelerometer logger

## Slide 46
Shock and vibration accelerometer logger
Notes: We fitted a SLAM stick on one of the dummy cryo-module racks before it was shipped to ESS and recorded the shock and vibration data during its journey. This helps us determine what conditions to expect when shipping more sensitive equipment that may be on the LWU’s and provide additional bracing to potentially unstable loads (magnets)

## Slide 47
Notes: Events in the first 3 hours of its journey from Daresbury laboratory.. Loading, smooth motorways and smaller windy roads before waiting at the port in Hull

## Slide 48: Shock and vibration during transport
Initial observations show some 10G+ shock events.
Possible causes:
  Poor road surface (pot holes)?
  Crates sliding on the trailer bed (insufficient strapping)?
  Handled with limited care at the ports (loading/unloading)?
Notes: Run the test again with the next batch of DCM’s but utilising a dedicated air ride trailer. No switching to another trailer during transit which doubles the handling and potential chances for damages.

## Slide 49: Shock and vibration during transport
Actions and potential solutions
  Re-run the test using ‘air ride’ suspension trailer (DCM’s)
  Same trailer from Daresbury to Lund
  Design temporary bracing (magnets) for transport
Notes: Run the test again with the next batch of DCM’s but utilising a dedicated air ride trailer. No switching to another trailer during transit which doubles the handling and potential chances for damages. Cavoflex springs successfully used to safely transport accelerator modules from Daresbury to Romania.

## Slide 50: Shock and vibration during transport
Damping system in the crate (Cavoflex)
Notes: Run the test again with the next batch of DCM’s but utilising a dedicated air ride trailer. No switching to another trailer during transit which doubles the handling and potential chances for damages. Cavoflex springs successfully used to safely transport accelerator modules from Daresbury to Romania.

## Slide 51: Final summary
Progressing well
First LWU due to be delivered early 2019 (30 to follow)
Pedestals and remaining DCM delivered early 2019
All mobile clean rooms signed off by end of this year
Spending time at IK partners facility highly advisable
Help refine bellows to Cryomodule connection
  *Likewise.. installation methods of interfacing BI?
Transport method to be optimised
240m vessels remain to be processed
A lot of work still to do - busy 2019
Notes: Run the test again with the next batch of DCM’s but utilising a dedicated air ride trailer. No switching to another trailer during transit which doubles the handling and potential chances for damages.