## Slide 1: Infrastructure Project and Component Installation Accelerator Project
Olle Lagerblad
Installation Lead Infrastructure Project
Dep. Installation Coordinator Accelerator Project
European Spallation Source ERIC
2018-11-20

## Slide 2: Overview
Agenda
Background
Vision and Strategy
In the pipeline
Scope of Work
Organization
Ways of Communicating
Ways of Working
  Overview, IB
  WO
  RAMS, I-NCR
The goal
Summary

## Slide 3: Background
The Infra Project started with the Front End Building (FEB) installation, a lessons learned (LL) on the work was performed. The outcome gave the need to improve:
  design and installation documents
    EIS project handbook/installation support function/build ability review
  material definition and management
    Plan for early procurement and definition of needed material “BOM”
    Use more of the same “standardized”, Use relevant material in required functions
  control and follow-up (design and project)
    Installation room/follow-up matrixes/ reports to stakeholders/ planning and coordination's meetings/ meeting structure
  management involvement and support
    Trough steering comity and cross functional working group
  better defined roles, responsibilities and processes
    Role and responsibility descriptions in the project

## Slide 4: Vision and Strategy
The Vision
  Contribute to, and use ESS “harmonized” way off working
  Identify key resources to relevant tasks, build competence for ESS
  Develop concepts and requirements within ESS and use ext. contractors for time critical bulk work
  Develop and refine processes “usability”
  Work across the divisions to improve communication and cooperation
  Use the power in the organization – if we work together
The Strategy
  Use Skanska org for installation of Mech. Infra structure
  Project Baseline design hand-over to Detail design NCF/ SPOKE, completed
  Detailed design through external contractor - for Piping and Raceways, started
  The work is done in a phased approach to support AD component installation
  The target is to mobilize the installation contractors at 7 Jan, start installation at 14 Jan

## Slide 5: In the Pipeline
Design for G01 & G02
  Cable trays and pipes
  Cable routing and termination (NCL and SPOKE)
  All grounding design (components not included)
  Power distribution
  Baseline M-beta and H-beta Piping and raceways
Installation
  STUB cable conduits and Waveguides
  All cable trays and pipes in G01 and G02
  Cable pulling and termination NCL
  Gas pipe installation for BI

## Slide 6: Scope of Work for Installation
The Scope of Work for Installation
Harmonized ways of working at ESS
Supervise and coordinate all installation activities
Planning, short term on site and long term
Execution and follow up on Division or Main project level
Coordinate and manage support activities
AD installation coordinator
Installation package lead
AD Work package lead
AD Liaison Officers
IK partner
Responsible for
Installation binder
Installation Readiness Review
Work order
Installation Non-Conformity Reports
Interface between: In-Kind – ESS WP – Installation Package Lead

## Slide 7: Scope of Work for Installation
The Scope of Work for the Installation of Infrastructure project
Components Installation Packages
  WP3, 4, 5, 6, 7, 8, 10, 11, 12
  Installation Package Lead (IPL) assigned by Work Package
  IPL supported by Installation Organization
Infrastructure Installation Packages
  Process and Piping
    Cooling water and Drainage Systems
    Pressurized Air
    Gas Systems
  Electrical
    Cable Raceways and Conduits,
    Electrical Power Distribution and Grounding
    Racks and Rack cooling,
    Cable coordination, Pulling Termination and verification
  Assign Installation Package Leads

## Slide 8: Installation Organization at Infrastructure and Accelerator
PM
Peo Gustavsson
PA/PC/Admin.
Ciprian/Fredrik
Design
Anton L
Installation
Olle L
Testing (SAT1)
Inigo A
QA/QC
Björn R
Electrical DD
High V / Low V
Jonas W
Electrical IPL TBD
Process & Pipe IPL TBD
CM/DM/Change mgt
Patrik W
Civil
CF Pre Ops
Civil IPL TBD
Electrical
TBD
Cabel DB
Design, installation and test follow up
Process&Pipe DD
Piero V
Process
Anton L
OSH
Nic E
System Design Owner
Frithiof J
System Design Owner
Anton L
Mechanical
Machanical IPL TBD
Component IPL Kristifer Falkland
Steering comity
John H
Roland G
Ken
Ralf T
Mikael J
Installation
Components IPL
Technicians
Service and Technical Support
Transportation
Lifting, Scaffolding
Rigging
Storage
Laydown Areas
Procurement
Boring &Drilling
Temporary services, H2O, Power, Comp air.
Alignment
Work Shop
Integration
Electrical IPL
Area Coordinators
Civil IPL
Process & Pipes IPL
Mechanical IPL

## Slide 9: Ways of Communicating
Daily
  War room meetings
    Plan
    Comply or explain deviations
    Issues
  Stand up meeting on site
Weekly
  Installation detailed working and follow up meetings
    Detail planning and organization of installation activities
    Service needs (eg. transportation, storage, tools, workshops)
    Installation binder
    Commissioning
  Installation and commissioning meeting “Information”
    Share information
    General presentations
    Status updates
    Safety /quality aspects
    Issues solved/new
Once
  Preliminary Design Review
  Critical Design Review
  Installation Readiness Reviews
    Design Data
    Time plan and installation sequence
    Temporary Services
    Safety
    Quality
    Feedback from Manufacturer
  Test Reediness Review

## Slide 10: Ways of Working with Installation
“The project are here to supervise and coordinate all installation activities, planning, execution and follow up, on Division or Main project level”
  Preparation and Planning
    Installation Binder
    Risk Assessment and Method Statement (RAMS)
    Work Order
  Installation Readiness Review
  Installation (Perform your Work)
    Pre-Job
  Test Readiness Review
    Documentation handover
    Close down site activities
    Work Review
  Safety Readiness Review
  *Detailed information to be found on: https://confluence.esss.lu.se/category/essinst
  Chess document “ESS-0102864 - ESS Procedure for Preparation for Installation and Installation”
Input from Design
Preparation of IB
IRR
Installation
Test and Inspection
TRR
SRR

## Slide 11: Ways of Working with Installation
The Work Order (WO) control the release of work and work/safety:
  What/Who/How/Where/When
  No work shall be executed unless it is planed and organized
  Synchronize the work with other parallel work (same area)
  To control plant conditions and equipment
  To plan and organize delimitations and tag outs
The Work Order will mainly state:
  Installation activity start and end time
  Summary of the activity
  Documents related to this activity (RAMS)
  Any need for delimitations/tag outs
  https://jira.esss.lu.se/servicedesk/customer/portal/11

## Slide 12: Ways of Working with Installation
Risk Assessment and Method Statement (RAMS)
  What’s the purpose with a RAMS?
    Identify hazards and associated risks for an activity and determine if sufficient controls are in place (to reduce the risks to an acceptable level)
  Who is responsible for preparing the RAMS?
    Installation Package Lead for making sure it’s prepared
    Help and support from Safety and Installation Orgnization
  What does a RAMS consist of?
    The RAMS consists of two parts:
    A method statement, i.e. a detailed break down/description of the work to be carried out and material to be used to perform this task
    A risk assessment, i.e. identify the risks associated to the work steps detailed in the method statement. Including adjacent risk.
Installation Non-Conformity
RAMS: https://confluence.esss.lu.se/pages/viewpage.action?pageId=265308713
I-NCR: https://confluence.esss.lu.se/display/QUAL

## Slide 13: The goal
High level ESS Objectives 2019
  RFQ, MEBT and DTL 1 installed in the tunnel
  Conditioning and commissioning of the RFQ, MEBT and DTL1 started
There are 3 critical paths, which feeds SRR 3 & 4;
  RFQ – DTL 4 Beam on temporary dump, “Warm Linac”, 2020 June/July
  DTL5 – Beam on Dump “Cold Linac”, 2021 April/May
  Dump to Target, 2021 July/Aug RBOT, (2022 June BOT)

## Slide 14: Summary
The project covers the infrastructure and accelerator components installation
The project are here to supervise and coordinate all installation activities, planning, execution and follow up, on Division or Main project level
Organization staring to form and being put into place
Ways of working “harmonized” with installation at ESS being established
There will be a lot of installations starting to happened in the coming 6 months