## Procurrement
icBLM: procurement plan, installation time windows for DTL1 icBLM | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com | [18 empty] | Learn about the Pro version >
[Company Name]
| Project Start Date | 2019-01-01 |  |  |  |  | Display Week | 10 | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38
| Project Lead | [7 empty] | 2019-03-04 | [6 empty] | 2019-03-11 | [6 empty] | 2019-03-18 | [6 empty] | 2019-03-25 | [6 empty] | 2019-04-01 | [6 empty] | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05 | [6 empty] | 2019-08-12 | [6 empty] | 2019-08-19 | [6 empty] | 2019-08-26 | [6 empty] | 2019-09-02 | [6 empty] | 2019-09-09 | [6 empty] | 2019-09-16
 | time axis 2019-03-04 to 2019-09-22
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-03-04 to 2019-09-22
1 | Accelerator schedule - from TB28, 17.1.2019
1.1 | DTL1 installation - tank installation |  |  | 2019-08-19 | 2019-09-15 | 28 | 0% | 20
1.2 | MPS - final integration test (ICS) |  |  | 2019-10-30 | 2019-11-26 | 28 | 0% | 20
1.3 | RFQ/MEBT/DTL1 RF Conditioning window |  |  | 2019-10-28 | 2019-12-22 | 56 | 0% | 40
1.4 | Beam Commissioing: ISr to DTL1 |  |  | 2019-12-16 | 2020-03-22 | 98 | 0% | 70
2 | icBLM installation time slots
2.1 | Detetors (short cables, PPs?, support) in tunnel
2.1.1 | DTL1 detectors (1 det) |  |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
2.2 | Electronics in racks - installation time window | [6 empty] | 0
2.2.1 | DTL1 detectors (1 det) |  |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
2.3 | NOTE: in SCL only 2/3 of detectors ready for first protons (1 per LWU): detectors and cables install, but not tested
3 | icBLM reviews
3.1 | PDR1 | / |  | 2017-07-10 | 2017-07-11 | 2 | 100% | 2
3.2 | CDR1 | / |  | 2019-02-13 | 2019-02-13 | 1 | 0% | 1
4 | Detectors (285)
4.1 | Procurrement (production and QA tests) | ESS BI |  | 2014-07-16 | 2017-07-03 | 1083 | 100% | 774
4.2 | Acceptance tests - 3 detectors | ESS BI |  | 2017-11-10 | 2017-11-11 | 2 | 100% | 1
4.3 | RFI - 3 det | / |  | 2017-11-12 | 2017-11-12 | 1 | 100% | 0
4.4 | Acceptance tests - 282 detectors (6 detectors per day) - resoucrce problem | ESS BI |  | 2019-03-13 | 2019-04-28 | 47 | 0.1% | 33
4.5 | RFI - 282 det | / |  | 2019-04-28 | 2019-04-28 | 1 | 0.1% | 0
4.6 | installation at DTL1 (1 det) | ESS BI |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
5 | Electronics
5.1 | CAENels, Pico4 | [6 empty] | 0
5.1.1 | Procurrement - 8 boards | ESS BI |  | 2018-08-08 | 2018-10-30 | 84 | 100% | 60
5.1.2 | QA tests - 8 boards (time window) - unclear end date (integration on ifc140 issues) | ESS BI |  | 2019-01-15 | 2019-02-12 | 28 | 50% | 21
5.1.3 | RFI - 8 boards | / |  | 2019-02-13 | 2019-02-13 | 1 | 0% | 1
5.1.4 | procurment process preparation | ESS BI |  | 2019-02-14 | 2019-03-13 | 28 | 0% | 20
5.1.5 | Procurement - 92 boards | ESS BI |  | 2019-03-14 | 2019-06-05 | 84 | 0% | 60
5.1.6 | QA tests - 92 boards (6 per day) - resource problem | ESS BI |  | 2019-06-06 | 2019-06-21 | 16 | 0% | 12
5.1.7 | RFI - 92 boards | / |  | 2019-06-22 | 2019-06-22 | 1 | 0% | 0
5.1.8 | Installation for DTL (1 det) | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
5.2 | Crates
5.2.1 | procurement by ICS, availablity unclera (on response from ICS) | ESS ICS
5.2.2 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
5.3 | Short signal cables, connect. & PPs - rack side
5.3.1 | final design - clear TBD | ESS BI |  | 2019-01-01 | 2019-03-13 | 28 | 50% | 52
5.3.2 | production/procurremnt | ESS BI (WUT) |  | 2019-03-14 | 2019-06-05 | 84 | 0% | 60
5.3.3 | Installation for DTL1 det. - time winow | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
5.4 | Short signal cables, connect. & cable supports - detector side
5.4.1 | pin layout | ESS BI |  | 2019-02-14 | 2019-03-13 | 28 | 0% | 20
5.4.2 | PP (or cable support?) design and integration to 3D model - lack of reources | ESS BI |  | 2019-02-14 | 2019-04-10 | 56 | 0% | 40
5.4.3 | procurment process preparation | ESS BI |  | 2019-04-11 | 2019-05-08 | 28 | 0% | 20
5.4.4 | procurement/production | ESS BI |  | 2019-05-09 | 2019-07-31 | 84 | 0% | 60
5.4.5 | RFI | / |  | 2019-08-01 | 2019-08-01 | 1 | 0% | 1
5.4.6 | Installation for DTL1 det. - time winodw | ESS BI |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
5.5 | Long signal cables, connectors
5.5.1 | procurement | ESS Infrastructure
5.5.2 | ready for connection in DTL1 - dates unclear, this what is in P6 now, though pulling cables is the current focus, so changes likely | ESS Infrastructure |  | 2019-09-30 | 2019-10-14 | 0 | 0% | 11
5.6 | HV PS system (ISEG)
5.6.1 | procurment process preparation | ESS BI |  | 2019-02-14 | 2019-02-27 | 14 | 0% | 10
5.6.2 | Procurement | ESS BI |  | 2019-02-28 | 2019-05-22 | 84 | 0% | 60
5.6.3 | QA Test | ESS BI |  | 2019-05-23 | 2019-05-29 | 7 | 0% | 5
5.6.4 | RFI | / |  | 2019-05-30 | 2019-05-30 | 1 | 0% | 1
5.6.5 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
5.7 | Short HV cable connections (daisy chain) - detector side
5.7.1 | procurment - ongoing | ESS Infrastructure
5.7.2 | Installation for DTL1 det. - not required | ESS Infrastructure
5.8 | Etheract crate & modules
5.8.1 | procurement by ICS - availablity unclear | ESS ICS
5.8.2 | Installation for DTL1 det. - time window | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
5.9 | Short cables in Ethercat crate connections - rack side
5.9.1 | procurment process preparation | ESS BI |  | 2019-02-14 | 2019-02-27 | 14 | 0% | 10
5.9.2 | procurement/production | ESS BI |  | 2019-02-28 | 2019-03-13 | 14 | 0% | 10
5.9.3 | RFI | / |  | 2019-03-14 | 2019-03-14 | 1 | 0% | 1
5.9.4 | Installation for DTL1 det. - time winodw | ESS BI (WUT) |  | 2019-06-10 | 2019-06-30 | 21 | 0% | 15
6 | Detector mechanical support
6.1 | for DTL1 detector
6.1.1 | Design & integration - resource problem | ESS BI |  | 2019-02-14 | 2019-04-10 | 56 | 0% | 40
6.1.2 | procurment process preparation | ESS BI |  | 2019-04-11 | 2019-04-24 | 14 | 0% | 10
6.1.3 | Procurement | ESS BI |  | 2019-04-25 | 2019-07-17 | 84 | 0% | 60
6.1.4 | installation at DTL1 (1 det) - exact dates to be coordinated with Infrastructure, here assuming isntallation together with detectors | ESS BI/Infrastucture |  | 2019-09-07 | 2019-09-13 | 7 | 0% | 5
7 | System tests
7.1 | Vertical integration tests - time windows
7.1.1 | in the lab | ESS BI/ICS/LTU |  | 2019-06-01 | 2019-08-23 | 84 | 0% | 60
7.1.2 | tests after installation (with DTL1 det.) and connecting short cables on detcetor side | ESS BI/ICS/LTU |  | 2019-10-15 | 2019-10-25 | 10 | 0% | 9
TEMPLATE ROWS
See the Help worksheet to learn how to use these template rows. You can hide these rows before printing.
1 | [ Level 1 Task, Category, or Phase ]
1.1 | . [ Level 2 Task ] |  |  |  | - |  | 0% | 0
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  | 0% | 0
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  | 0% | 0
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.