## Sheet1
Responses to Recommendations from the 18th t-TAC Meeting
Topic | TAC Recommendation | Target Project Response to TAC Recommendation
General comments relevant for Target | General TAC comments: (1) The ESS TSS (Target Safety System) is a critical system for the facility. Given its importance, then a dedicated review of the TSS with experts who have built and operated such systems is recommended. | (1) The TSS design, starting in 2013, passed the Preliminary Design Review (PDR) in Feb 2016, with a review committee that included two external subject matter experts, one on safety system design and implementation and the other on facility radiation safety and analysis. Currently, the Target Safety System is undergoing a Critical Design Review (CDR) process, divided in three parts. The review committee has both members internal to the ESS organisation and several from other existing and similar facilities. The first part took place 10 Dec 2018, the second part in conjunction with TAC#19 (including a cTAC member) on 8-9 Apr 2019, and the third part is scheduled in May 2019. Also, there will be an entirely independent review of the TSS design, performed by a Swedish subject matter expert company, Safetech Engineering. This external review will also be finalised during May 2019.
Target Station Accident Analyses | tTAC comments: (2) - The design philosophy and the methodology used fort dose calculations provides a solid basis fo licensing. (3) - Search for additional bounding cases. (4) - Searching for methods to reduce the workoad is understood by the committee but might not be possible. (5) - Ask existing facilities how they dealt with the problem of facility accident analysis. They may have methods, codes, etc. that can help. tTAC recommendation: None. | (2) OK. (3) The latest updates of the accident analysis (AA) reports has utilised this opportunity. The hydrogen deflagration scenario (AA9), the earthquake scenario (AA14), and the global target station fire scenario (AA23), all refer to other AA reports and their underlying dose calculations. (4) The current status for this matter is that two software packages are under development for facilitating the dose calculations. One is being developed by Lloyd's Register and is quality assured for final calculations used as basis for the facility licensing, and the other, developed in a collaboration with the Institute of Modern Physics, Chinese Academy of Sciences, is purposed for high throughput calculations during preparatory analysis iterations. (5) Unfortunately, the common response we get on such inquiries is that these other facilities are not mandated to perform facility accident analyses to the same depth and breadth as we have concluded necessary for ESS. This is often due to the lack of similar levels of inventory present at the facilities, or in some cases, due to a long operational record that can be used in place of analysis.
Monolith Inner Shielding | tTAC comments: (6) - A leak in the monolith inner shielding could potentially shutdown (end of life) the facility. Therefore it’s imperative that the best possible design and fabrication solution is sought. (7) - All water systems will leak sooner or later (8) - Proposed design for sealing cooling paths is challenging from a fabrication standpoint. (9) - The committee has concerns regarding what chould be done if there is in fact a water leak during operation. (10) - Stainless steel is expensive. Using carbon steel bulk shielding (improved thermal conductivity) with stainless cooling pipes is a possibility. (11) - Relief grooves along the weld length could reduce the residual stresses. (12) - The cooling channel design path is complicated and the cover plate to seal the channels requires kilometres of seal welds. • This technical issue has been addressed in other similar facilities; design options that could improve the chance of success may be available (13) - Weld inspection will be time consuming and somewhat difficult (14) - In FEM calculation to evaluate the stress concentration, take account of a sort of notch shape effect around welded parts between block and lid plate. (15) - Consider irradiation effect to evaluate the fracture toughness and fatigue strength on the welding; IASCC. tTAC recommendation: (16) Rec.1. Consider other possible design options for the cooling channels and cover plates. (17) Rec.2. Prepare for leakage of water systems inside the monolith and work on mitigation plans (repair or replacement) in case it happens. | (6) through (17) is addressed in special tTAC topic presented on 11 Apr 2019.
Beam lines alignment | tTAC comments: (18) - With the existing design of the port block and neutron beam inserts the alignment scheme is complex but seems feasible and well thought through. (19) - The system is complex and the committee is concerned that the time taken to perform survey and alignment present a significant schedule risk. (20) - Welding of the port block to the monolith vessel appears to be difficult as proposed. (21) - Continue to think about realignment scenarios, especially as the bunker continues to become more crowded. tTAC recommendation: (22) Rec.3. Be aware of the number of alignment tasks and the impact on schedule | (18) With this confirmative assessment feedback, the ESS Target team will continue to plan for and perform the component aligment as set forth. (19) The Target sub-project recognises this schedule risk and is continuously monitors the development and is working with mitigative measures. (20) The Target sub-project plans to engage with companies specialised in advanced field welding for improving the design in terms of implementability. (21) Realignment scenarios will be part of the initial operations phase of the ESS. Further detailed planning of this phase will be done the coming years. (22) The design teams as well as the installation teams, including the survey and alignment professionals, are continuously working with the planning and the procedures in order to find the most efficient installation sequence and with the aim to minimise eventual impact impact on the overall schedule.
Waste management | tTAC comments: (23) - Dose rate from the He filters is hard to estimate, but may be high. (24) - The filter pack replacement process may impose unnecessary dose to personnel. Technology can reduce the time (quick release flanges, etc.). (25) - Current design of the change process requires opening the loop to change the filters, potentially resulting in particulate contamination. (26) - Duplicate filters with a valve could allow cool down time before changing a filter. (27) - Procedures/equipment to control the spread of contamination from the He filters should be developed. (28) - Waste water transport by pipes has been re-assessed; transport tank(s) will be used instead. This is good for multiple reasons. (29) - This philosophy for the waste water is also implemented at J-PARC & ISIS. (30) - Storing waste water locally avoids mixing low activity water with high activity and allows segregation into separate waste streams. (31) - Consider tritium treatment, which will be released unexpectedly from everywhere once contaminated. tTAC recommendation: (32) - Rec.4. Consider building a second filter system for alternate operation, allowing decay time for used filters. (33) - Rec.5. Look at changing the entire cartridge and not just the filter, avoiding opening the vessel until the filter has decayed, and open it in an area where you can control contamination, etc. (34) - Rec.6. Proceed with the design to remove waste water piping. | (23) It is a known disadvantage that the actual inventories of filters are difficult to estimate, and therefore the emitted doses will be unknown until actual operation experience can be gained. The approach for the ESS helium-cooling loop filters has been to make provisions for the conservatively high estimation of erroded radioactive material mass from the target tungsten, i.e. 10 g/y, and in addition up to 1000 g/y non-active crud, for the dimensioning of the filters, aiming at a replacement interval of one year for 5 MW operation. (24) Different technical solutions has been studied, and we believe that we have chosen a sufficiently good option. However, at present that solution does not incorporate quick release flanges. But it does not exclude the possibility to install such equipment at a later stage, should the operation experience define that need. (25) This is a known issue, that has been considered when selecting the design solution. The design has incorporated the possibility to establish an underpressure for minimising the spread of contamination. (26) The helium-cooling loop design does not contain duplicated filters, mainly due to space constraints. (27) See response to comment (25). (28), (29), (30) This confirms/justifies the selected approach for handling of waste water. (31) For the helium-cooling loop purification system, hydrogen/tritium getters are used to continuously keep the tritium inventory to a minimum. The purification can also be operated for an extended period, with no beam on target, to further reduce the tritium content of the coolant, e.g. before a filter exchange. (32) The current design contains three helium filters in parallel, but without isolation valves due to pressure loss constraints. However, one possibility that may be pursued during the first years of beam power ramp-up and before increasing the accelerator capacity from 3 MW to 5 MW, is to disconnect one of the three filter with blind flanges. (33) This is essentially the option that has been incorporated in the design of the helium-cooling loop filter solution. (34) This recommendation confirms/justifies the selected approach for handling of waste water from the ESS Target Station.
Interplay between controls, MPS, TSS and control room | tTAC comments: (35) - The TSS can be viewed as the equivalent of a rupture disk in a pressure system. (36) - Setting TSS trip levels at safety level values means that any systems which cannot reach the performance required will prevent accelerator operation. (e.g. problems with the helium blowers that limits the helium flow rate). (37) - The responsibility for setting the TSS trip levels was not clear. They will have to be set without any significant operational experience. (38) - Complex synchronization between the accelerator and particular sectors of the target does not seem to be necessary. (39) - Setting TSS limits for true safety cases seems to be reasonable in order to not tamper with a system that acts as “last line of defense”. (40) - For example: during commissioning it could be necessary to operate the helium blower at low flow in order to get temperature readings on the target at the kW level. For these conditions it may be required to over ride the TSS if you really need that data. (41) - Review the requirements for data which needs to be shared between Controls, MPS, TSS and the Control Room and only implement those which are essential for commissioning and early operations. More functionality can be added later as needed. (42) - Keep TSS as simple and slim as possible but talk to SSM to determine if override mode during commissioning is possible to allow learning about system behavior at very low beam power level. Maybe this requires hardware interlock to not allow higher beam power tTAC recommendation: (43) - Rec.7. Establish who is responsible for authorizing the TSS trip levels. | (35) The analogy between TSS and a rupture disk is recognised. (36) The conflict between TSS trip limits and facility availability is recognised and the matter is being worked. However, safety shall and will in all situations take priority over availability. (37) It is true that the limits have to be set without any operational experience. Therefore, the approach by the design team is to postulate assumingly reasonable trip limits which are then justified to be sufficient, by analysis. (38) We disagree with this comment that synchronisation would not be necessary. Instead, we believe that there are several reasons for keeping records on how much beam and with which characterisics has been put on individual sectors. And also to be able to inhibit beam on certain sectors. (39) This comment is interpreted to indicate that the existing approach to determine TSS limits based on the results from the accident analyses is appropriate. (40) Our assessment is that the benefit of operating the helium blowers at low flow in order to get temperature readings on the target at low power accelerator operation cannot be justified due to the massive analysis efforts that would be needed to allow overriding the TSS trip points. Additionally, testing of the wheel monitoring system is being done prior to installation to calibrate the system. (41) There is an interface control document between the TSS and the TSS Monitoring System which determines the interface between TSS and EPICS. It is possible to send signals from the TSS Operationally classed PLC (Gateway PLC) into EPICS. It is reasonable to start by sending a short-list of information - this is easily expanded in the future. There is no information passed from EPICS into the TSS. There is an interface between MPS and TSS - there will be one-way communication to the FBIS of the TSS status. The details of the interface and the associated document describing it are under development. There is no information passed from MPS into the TSS. (42) Keeping the TSS as simple and straightforward as possible is part of the design approach for the TSS. However, we are not discussing with SSM the possiblity to override the safety system during commissioning. This is seen as unadvisable. The TSS does not monitor beam power. There is no hardware interlock in the accelerator to not allow higher beam power. (43) With reference to the response to item (37) above, the TSS trip limits are postulated and verified based on analysis. The authorisation of the trip limits would therefore, by logic, be the TSS owner.
Suggestions for tTAC19 | (44) - Rec.8. An update on delivery of key components, such as the target and the reflector, would be good. (45) - Rec.9. Follow up on the inner shielding, including the selected design and progress, would be useful. (46) - Rec.10. An update on the plant areas (water cooling plant, filter areas, etc.) and the active handling would be useful. | (44) For TAC#19 there will be a specific presentation on the progress of the Target Wheel. (45) For TAC#19 there will be a specific presentation following up the design and manufacture of the monolith inner shielding. (46) For TAC#19 there will be a specific presentation of the plant areas and active handling of equipment therein.