## Slide 1: TAC 19 Installation and commissioning 2019
Karl Vestin
Philippe Rabis
www.europeanspallationsource.se
2019-04-11

## Slide 2: Glossary
BCM - Beam Current Monitor
BI - ESS Beam Instrumentation group
BLM - Beam Loss Monitor
BPM - Beam Position Monitor
CCDB - Controls Configuration DataBase
CDR - Critical Design Review
CEA - Commissariat à l’Énergie Atomique et aux Énergies Alternatives - in-kind partner
DTL - Drift Tube Linac
FAT - Factory Acceptance Test
FC - Faraday Cup
FEB - Front End Building
FIT - Final Integration Test
INFN - Istituto Nazionale di Fisica Nucleare - in-kind partner
LLRF - Low Level RF
LPS - Local Protection System
MEBT - Medium Energy Beam Transport
NCL - Normal Conducting LINAC
NPM - Non-invasive Profile Monitor
PDR - Preliminary Design Review
RFQ - RadioFrequency Quadropole
SAR - Systems Acceptance Test
SAT - Site Acceptance Test
SIT - Site Integration Test TS2 - Test Stand 2 at ESS - Klystrons and cryomodules

## Slide 3: ICS work package 10: Accelerator Integration
Main role for work package 10 is to deliver control systems for the accelerator of the ESS facility
  Daily work with multiple stakeholders of the accelerator division through:
    control systems for a large diversity of technologies and disciplines: RF, Beam Instruments, Cryogenics plants, Cryogenics of cold linac, Water cooling systems, Vacuum, Magnets and power supplies
    Located in different sections of the accelerator: MEBT, RFQ, DTL, Super Conducting Linac and Beam delivery systems
  Where a key word is: integration, integration..
  Numerous interfaces and stakeholders: internal and external

## Slide 4: Achievements (MEBT)
Supporting ESS Bilbao and establishing a sound and reliable relationship with in-kind partner
Work beyond original scope to ensure that MEBT is ready for installation with the required control systems architecture; special focus on instruments
  Wire Scanners
  Emittance Measurement Units
  Longitudinal Bunch Monitor
  Neutron Beam Loss Monitors
  Non Invasive Profile Monitors
  Beam Current Monitors
  Beam Position Monitors
  Scrapers
  Faraday Cup

## Slide 5: Achievements (MEBT)
Complete system vertical integration tests at ESS Bilbao in collaboration with ESS control and Diagnostics team
MEBT SAR in 2019-03 passed with recommendations, no show stopper

## Slide 6: Achievements
RFQ:
  Support to CEA for the supply of the control systems (including familiarisation with PLC factory, interfaces, tests, CCDB)
  Water cooling skid installed (2018)
DTL:
  CDR DTL control systems at INFN Legnaro passed successfully with no major issue (end 2018-10)
  HW equipment now delivered to in-kind partner (INFN) as per contract with some delays
Beam instruments :
  Constant development of several instruments supported by IFC cards during 2018
  CDR for DTL FC (2018)
  CDR NPM and BLM successfully passed (collaboration with BI department and CEA) early 2019
  Successful collaboration with BI for preparation of instrument tests at J-Parc

## Slide 7: Achievements
Cryogenics:
  Support for PLC based control systems in order to deliver as per schedule Accelerator Cryogenics Plant and Test & Instrument Cryoplant.
  Successful collaboration with Cryogenics team and equipment provider (Linde, Air Liquide) (EPICS integration)
TS2:
  Support to TS2 for PLC control sytems as per schedule
RF group:
  CDR LLRF ESS Bilbao (support to RF team) early 2019
  Ongoing development of LLRF systems and RF LPS (SIM and FIM) including development of FPGA firmware (completed)

## Slide 8: Installation plan for 2019 - 2020
2019
Today
Q1
Q2
Q3
Q4
Q1 2020
Q2
Q3
Q4
DTL1 RF System Operational
11 Oct, 2019
RFQ RF System Operational
9 Aug, 2019
MEBT RF System Operational
11 Nov, 2019
Start of Beam Commissioning (Isrc to DTL1)
17 Feb, 2020
Start of Beam Commissioning (Isrc to DTL4)
28 Sep, 2020
RFQ IRR
21 Mar, 2019
RFQ TRR
29 Jul, 2019
MEBT IRR
15 Jul, 2019
MEBT TRR
14 Oct, 2019
DTL1 IRR
16 Sep, 2019
DTL1 TRR
25 Nov, 2019
DTLs 2, 3, 4 IRR
9 Mar, 2020
RFQ/MEBT/DTL1 RF Conditioning TRR
16 Dec, 2019
DTLs 2, 3, 4 RF Conditioning TRR
8 Jun, 2020
RFQ
May 20 - Sep 13
17 wks
RFQ Assembly
May 20 - Jun 28
6 wks
RFQ Local Hardware Tests
Jul 1 - Jul 26
4 wks
RFQ Infrastructure Work Completion
Jul 29 - Aug 9
RFQ Integrated Hardware Tests
Aug 12 - Sep 13
5 wks
MEBT
Aug 12 - Dec 27
20 wks
MEBT Assembly
Aug 12 - Sep 20
6 wks
MEBT Infrastructure Work Completion
Sep 23 - Oct 4
MEBT Local Hardware Tests
Oct 7 - Oct 25
3 wks
MEBT Integrated Hardware Tests
Oct 28 - Dec 27
9 wks
DTL1
Oct 7 - Dec 27
12 wks
DTL1 Installation
Oct 7 - Nov 1
4 wks
DTL1 Infrastructure Work Completion
Nov 4 - Nov 15
DTL1 Local Hardware Tests
Nov 18 - Nov 29
DTL1 Integrated Hardware Tests
Dec 2 - Dec 27
4 wks
PSS Validation (ICS)
Sep 30 - Oct 25
4 wks
MPS Final Integration Tests (ICS)
Dec 30 - Jan 24
4 wks
RFQ/MEBT/DTL1 RF Conditioning Window
Dec 30 - Feb 14
7 wks
SRR2
Feb 3 - Feb 14
Beam Commissioning (ISrc to DTL1)
Feb 17 - May 15
DTLs 2, 3, 4 Installation Window
May 18 - Jul 31
DTLs 2, 3, 4 RF Conditioning Window
Aug 3 - Sep 25
SRR3
Sep 14 - Sep 25
Beam Commissioning (ISrc to DTL4)
Sep 28 - Dec 25

## Slide 9: Key challenges
High number of parallel activities
  Resource constraints
  High technical risk
Many different stakeholders
  Difficult to get unambiguous prioritization

## Slide 10: Methodology for 2019
Methodology and strategy for 2019:
  Establish agreed scope and priorities with all stakeholders
  Regular sessions with stakeholders to review activities, deliverables and plan, cross functional:
    AD Project support meeting
    Accelerator sections (warm linac) installation meeting
    Overall installation plan and milestones (high level)
    Specific discipline reviews:
      Beam instruments
      RF group
  Assign system owners and focal points: work package 10 and stakeholder sides
  Hardware and integration monthly resources allocation boards to ensure adequate resource allocation

## Slide 11: Methodology for 2019
Dedicated super conducting linac project focused meeting
Align and continously re-align work package 10 activities plan with AD installation and development (beam instruments) plan
Use of the same supporting work tools, i.e.
  Jointly accessible and updated Primaver P6 acivity plans
  Common activity table in Jira
Regular stakeholder coordination meetings (see following slides for proposal under preparation/discussion)

## Slide 12: Normal conducting linac stakeholder meeting
Coordination of common activities towards the beam commissioning steps
from the RFQ up to DTL5
Machine directorate based approach to get things installed, tested and ready for beam
Strong involvement of in-kind partners for direct exchange
Definition of dependencies and feedback into and from the P6 planning
Align strategies and priorities for one machine section
Communication of progress, issues and blockers

## Slide 13: Normal conducting linac stakeholder meeting (ICS proposal)
Procurements
--------------
--------------
--------------
Tasks
--------------
--------------
--------------
Issues
--------------
--------------
--------------
The stakeholder forum creates a set of tasks, procurements and issues that taken as a whole generates a meaningful result.
The forum occurs at the beginning of each program increment and contains representatives for all members (see below).
Vacuum group
Beam diagnostics
Radio frequency
Test stand 2
Cryo group
NCL group
SCL group
Protection system group
Hardware and integration group
Program increment. Time boxed 2-3 months.
Notes: KRISTINA

## Slide 14: Resource situation
The hardware and integration group had an unfortunately high attrition rate in 2018
The situation seems to have stabilized
Recruitment and procurement of consultancy services has now brought the number of integrators back in line with staffing plan
Ongoing recruitments and procurements will add:
  Additional 2 FTE employees
  Additional 2-4 FTE consultants to meet the resource peek expecetd in 2019 - 2020
  A complete offsite team of 5 FTE to support the control system development for the cryomodules and cryo distributions system for the SCL

## Slide 15: Thank you!
Thank you for your attention