## Slide 2: Project and Experiment Safety Support (PESS)
Simon Marsh, Yves Loertscher, Owain Williams

## Slide 3: PESS - Context
Aim: to support the full variety of projects being conducted at CERN from an occupational, environmental and process safety perspective
PESS (Project and Experiment Safety Support) offered as a service to project leaders
Initially offered as a voluntary service. Increasingly all new projects are handled through PESS
The PESS service is currently supporting 100 projects, across the full range of CERN’s activities

## Slide 4: Approach
A single point of contact between the project and the specialists
Focus on early involvement
Acoustics
Asbestos / lead
Chemical
Civil / structural
Confined spaces
Cryogenics
Electrical
Emergency / evacuation
Ergonomics
Environmental protection
Events
Fire prevention
HVAC
Laser
Legionella
ODH
Mechanical
CERN Conventional Safety Disciplines
Projects divided into different Types, so as to provide the appropriate level of support
A standard checklist for identifying relevant safety domains
“Cradle to Grave” support for the project

## Slide 5: Project Types
Due to the wide variety of projects at CERN, the following categorisation is used within the PESS activity:
  Type 1 – Offices and Tertiary Buildings
  Type 2 – Industrial Installations
  Type 3 – Experiments, Beam, and Underground Facilities
  Type 4 – Studies

## Slide 6: Project Initiation
PESS Coordination team informed of a project
“Coffee chat” between PESS coordination and the Project Leader
Project Type decided, and a Correspondent appointed
Formal Launch Safety Discussion (involving the HSE Correspondent, back-up, Project Leader, Project Safety Officer (PSO), Departmental Safety Office (DSO) representative)
Major Safety Implications (MSI) can be declared for projects with significant hazards to people, the environment, or the reputation of the Organization.

## Slide 7: Project Support
Two general approaches:
Type 1 and Type 2: Q&A Approach
Consultation with the relevant specialists on points raised in the Launch Safety Discussion
Continued dialogue between the correspondent and project leader (and PSO/DSO) throughout the project, as required
A final project “reception” to verify that the correct procedures have been followed, and identify any outstanding issues.
Type 3 and MSI: Detailed Approach
A detailed document produced for project leaders, giving safety requirements and solutions for each safety domain
Continued dialogue between the correspondent and project leader (and PSO/DSO) throughout the project
A final project “reception” to verify that the correct procedures have been followed, and identify any outstanding issues.
Safety clearance issued for MSI projects, subject to HSE requirements being met

## Slide 8: Type 1 Team – Offices and Tertiary Buildings
Largely based on standard rules and regulations
A core team has ownership over the activity, with specialisms relevant to Type 1 projects:
  Emergency and evacuation
  Ergonomics
  Building inspection
Each project is assigned to a particular correspondent within the team
Projects are regularly reviewed by the team, allowing progress reports, and mutual support
Q&A approach with the project leader (and PSO/DSO).

## Slide 9: Type 2 Projects – Industrial Installations (current approach)
Largely based on standard rules and regulations, but often with more complexities and higher profile
No dedicated team
A variety of correspondents, with specialisms relevant to Type 2 projects (electrical, mechanical, civil, noise, worksite, etc.)
One correspondent appointed to each project, with a Q&A role with the project leader (and PSO/DSO).
For projects with Major Safety Implications (MSI), they follow the detailed approach, plus the requirement for HSE clearance at commissioning.

## Slide 10: Type 3 Projects – Experiments, Beam, and Underground Facilities
Usually more bespoke, and sometimes difficult to fully ‘shoehorn’ into standard rules and regulations
No dedicated team, but a variety of correspondents, with specialisms relevant to Type 3 projects.
One correspondent appointed to each project.
A detailed approach is taken, to support the Project Leader and the PSO/DSO.
Where the project has Major Safety Implications (MSI), HSE clearance is required at commissioning.

## Slide 11: Type 4 Projects – Studies
Generally very complex projects, involving new (or not yet existing) technology
Completely bespoke approach
A single correspondent assigned to the project, but any number of specialists could be involved directly over a long period of time

## Slide 12: PESS Improvement Activity in 2019
Motivations:
Increasing the efficiency and effectiveness of project support, to support 100+ projects with current resource constraints
Improve consistency and quality of support given
Preventing situations where safety concerns are identified late in the process, causing costly delays or undesirable compromises
Building in flexibility to deal with project scope changes
Learning lessons in the process, and applying them

## Slide 13: PESS Improvement Activity in 2019
Approach:
Identification of key “themes” for improvement:
  Streamlining project identification and kick-off
  Improved ‘front-end loading’
  Improvements to how projects are supported for each of the main Types
  Tailoring the process, so that the outcome is practical advice for project leaders/PSOs to follow, rather than “throwing the rulebook”

## Slide 14: Example: Type 2 Team
A fast, agile, team of specialists handling Type 2 projects, in weekly or fortnightly working meetings
The aim will be to take on the benefits gained from the Type 1 team, but adapted to the more complex Type 2 projects
The team will be made up of a core group of specialists of the most common safety domains found in Type 2 projects, with involvement from other specialists as required

## Slide 15: Key Features of the Type 2 Team
A “working meeting” with direct involvement of specialists, avoiding the need for the circulation of documents
Launch Safety Discussions are done in the meeting
Progress and Lessons Learned will be captured, with the aim to identify problems early, and prevent reoccurrence of past difficulties.