## Slide 1: Welcome and ESS/NSS Project update
Shane Kennedy
Deputy Director for Science
and NSS Project Leader
www.europeanspallationsource.se
Joint STAP meeting: Users & Samples/Sample Environment, 2-3 April 2019
45´

## Slide 2: 2018 ESS project highlights
Established new ESS-wide baseline plan to improve coordination, communication, execution, and tracking of work
Handed-over klystron gallery and two more buildings from construction partner to ESS
Structural design of Target Building and Instrument Halls no longer on critical path
Formed new Infrastructure Subproject to be ready for Accelerator equipment deliveries and commissioning
Began commissioning Ion Source and LEBT and three helium cryo-plants
Installed Active Cell infrastructure embedded in buildings - waste pits, Active Cell liner

## Slide 3: NSS Project scope: 15 neutron instruments + test beamline + support labs
ESS Instrument Layout (September 2017)
ESS In-Kind Partners also collaborate on sample environment, data management, lab fitout (D04, D08, E03 & E04) etc.
ESS Lead Partners for instrument construction
ODIN
DREAM
NMX
MIRACLES
T-REX
MAGIC
BIFROST
HEIMDAL
FREIA
LOKI
VESPA
ESTIA
SKADI
+
+
C-SPEC
+
Nuclear Physics Institute
BEER
Test Beam Line
D07
D08
D04
E03
E04

## Slide 4: Schedule Overview

## Slide 5: ESS Summary Schedule and Critical Path for Remaining Work
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker and Test Beam Line RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
RSOUP
Instrument Hall Access for Start of Installation
Hi-Beta Install
1.3 GeV Capability Installed
BOT - Beam on Target
FS - ‘First Science’
SOUP - Start of User Programme
EOC - End of Construction project
RXXX - Ready for XXX
CF, Target, and NSS (Bunker) teams holding zero-float Critical path to BOT
Float to Accelerator RBOT reduced from 14 months to 11 months due to IK delivery slippage
Red line indicates critical path
FS
FS added in response to rebaseling review

## Slide 6: Rebaseline schedule for Neutron Beam Instruments (V4.1, 29th November 2018)
Preliminary Design
Detailed Design
Manufacturing & Procurement
Installation & Integration
Hot Commissioning/Early science
Operation
2016 2017 2018 2019 2020 2021 2022 2023 2024 2025 2026
* NBI = Neutron Beam Instrument
West sector
North sector
East and South sectors
Current date
First access to NSS bldg (E01)
SOUP
(3NBI*)
BOT
&
HC
8NBI* in User Program
March 2023:
First Science (FS) with expert teams on any instrument above
Review progress of first 3 NBI for SOUP, implement backup plan if needed.
aligned with accelerator ramp up (ESS-0420218)
FS
First 3 NBI selected for SOUP: DREAM, LOKI & ODIN (best chance for early impact, as agreed by NSS, SAC and Council)
Back-up instruments (for risk of late access to D01 & D03) BEER, CSPEC, MAGIC or BIFROST, ESTIA

## Slide 7: Budget Overview

## Slide 8: Available contingency is more than forecast increases, but little remains for unforeseen items
Forecast increases are less than available contingency, but leaves only 39 M€ for unforeseen items
Item | M€
Available Budget, i.e. Total Project Cost (TPC)* | 2210
Budget at Completion (BAC) (No contingency) | 2044
Contingency available (TPC- BAC) | 166
Estimate-at-Completion (EAC) | 2171
Forecast Increase (EAC-BAC) | 127
* Per Council resolution 13.06.a assumes full initial funding (1843 M€2013 plus additional host state contribution) plus additional 135 M€2013 based on unforeseen costs for handling seismic and antagonistic threat requirements
ESS Project is 58 % complete
A new round of cost reduction measures is underway (decisions due in April)

## Slide 9: Construction project : NSS performance 2019 progress (to end of February)
SV -0,9 M€ & SPI = 0,99
  IK instrument projects progressing without signed TA.
CV 1.5 M€ & CPI = 1,02
SPI & CPI of ‘cash’ components are within variance reporting thresholds
~ 222 M€ by IK partners
- In part treated as cash IK
NSS budget = 361 M€
NSS Project is 27.1 % complete Cash Spent = 78.03 M€
In Kind Spent = 13.67 M€
Manufacturing &
Procurement
NSS Contingency
Estimated need = 28.64 M€
Available funds = 22.96 M€
Shortfall (EAC – BAC) = 5.68 M€
Notes: 91,7
338,04
---
Variance analysis thresholds at subproject level (Level 2):
Cumulative Cost Variance threshold: CPI < 0.95 and CV < - 0.5 M€
Cum Schedule Variance threshold: SPI < 0.95 and SV < - 0.5 M€
Note: These values are fairly tight since we have re-baselined each year

## Slide 10: Recent & upcoming activities

## Slide 11: NSS Major Procurements: Neutron bunker & Common guide shielding
Shielding work packages
1. Neutron Bunker (Total Budget = 18 M€)
Bunker shielding material changed from steel/HDPE to Heavy Concrete
Bunker wall thickness unchanged (at 3.5 m)
Bunker roof is now stepped (from 1.5 m -> 1.0 m) & 30 % lighter.
2. Common Guide shielding (Cost Est. ~ 10 M€)
Scope set to 9 neutron instruments Instruments (more may join)
Concept: 50-70 cm concrete + 0-20 cm steel inner
Neutronics & mechanical design advancing to PDR & costing (Jan 2019)

## Slide 12: Next Six Months: •First 8 instruments move into manufacturing* •Prepare to install 4 instruments in E01
2018-2019 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
LOKI |  |  |  |  |  |  |  |  |  |  |  | 
SKADI |  |  |  |  |  |  |  |  |  |  |  | 
ESTIA |  |  |  |  |  |  |  |  |  |  |  | 
FREIA |  |  |  |  |  |  |  |  |  |  |  | 
NMX |  |  |  |  |  |  |  |  |  |  |  | 
MAGIC |  |  |  |  |  |  |  |  |  |  |  | 
HEIMDAL |  |  |  |  |  |  |  |  |  |  |  | 
DREAM |  |  |  |  |  |  |  |  |  |  |  | 
BEER |  |  |  |  |  |  |  |  |  |  |  | 
ODIN |  |  |  |  |  |  |  |  |  |  |  | 
CSPEC |  |  |  |  |  |  |  |  |  |  |  | 
BIFROST |  |  |  |  |  |  |  |  |  |  |  | 
MIRACLES |  |  |  |  |  |  |  |  |  |  |  | 
T-REX |  |  |  |  |  |  |  |  |  |  |  | 
VESPA |  |  |  |  |  |  |  |  |  |  |  | 
TG2 passed
Final TG3
* Seven NBOA already in manufacturing
s
Sub-TG4
s
21
Intermediate Design Review
ILL-ESS User Meeting
Council-14
IKON16
ICB11
SAC22
ICB12
IKRC16
IKRC16
IKRC16
SAC21
29
IKON17
STAP
18-19
16-17
3-4
DMSC STAP
10-11
1-3
8
s
s
Subsystem TG3 (intermediate)
s
s
s
s
s
s
S
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
s
12
8

## Slide 13: Preparing to start Installation in E01 & E02 in 2019
BEER cave (E01), September
BIFROST cave (E01), December
NMX cave (E01), November
NBOA Integration (E01), December
CSPEC guides (E02), December
E04
E03
Fit-out of labs & workshops
(E03 & E04), starts in 2020

## Slide 14: NSS Summary
NSS major goal for 2019 is start installation in E01 & E02/1
NSS Project is 27% complete & is on budget (EAC within 2 % of BAC)
All instruments are now in detailed design & manufacturing has commenced (7 NBOA + ODIN choppers)
Bunker is now in manufacturing
Common shielding project is ready to move to detailed design and manufacturing for 5 instruments
Accelerator ramp-up and operation plans agreed with Accelerator, Target, ICS & ES&H
Design of common beam monitor systems has commenced (by ESS - Detector Group)
Initial Operations Budget is under review as we settle contributions from ESS member states
- reductions are likely to impact plans for further capital investment (Instruments 16-22, Instrument 1-15 upgrades, SEE etc.)