## Slide 1: DRAM updates
Thomas Holm Rod
Feb 1st, 2019

## Slide 2: In brief
Staff. Two new group members and one new secondment
  ➡️ Started to reorganize work (agile project organization)
Dev. Projects. Current projects, primarily in house:
  Ready for operation of LoKI (DONKI)
  sci++ project (C++ library for experimental data sets)
  Computational Diffraction Environment (CoDE) / Visualization in Python (VisPy)
Diffraction. Started collaboration with ILL and LLB as well as in house CoDE project.
Instrument data scientists. Started pilot project
Milestones. More or less on track.
External funding.
  Last SINE2020 WP10 workshop in May
  PaNOSC started
  AMEN VR project funded
  PARADISE H2020 project submitted
Stakeholders. Challenges from reflectometry stap & annual review

## Slide 3: Staff
3 local Mantid developers (+ 1 ½ @ ISIS)
Diffraction user expert
Spectroscopy user expert
Full-time McStas expert
Many people, but also large scope:
13 (ESS) + 7 (IKC) head counts
11.5 (ESS) + 5 (IKC) FTEs
8 different instruments
4 EU work packages (SINE2020 + PaNOSC)
3 VR projects
Céline is a pilot instrument data scientist for diffraction
Simon W looks after spectroscopy
Wojtek looks after large-scale structures
=> In the process of reorganizing how we work

## Slide 4: Updated timeline diagram - delays in core development - recruitment is still pretty much on track
Andrew Sazonov
(15th December)
Mads Bertelsen
(2nd January, 2019)

## Slide 5
Plann. | Antici. | Description | Status
’18-07 | ’19-05 | SasView ready for SOUP (aka SasView 5 released). SasView compliant with non-functional and functional requirements. | Delayed. SasView 5 demonstrated and tested at codecamp at ESS in September. ⍺-version presented at SAS2018 in October at dedicated workshop for ~40 persons. β1- and β2-version released. Final release expected in May.
’18-08 | ’19-05 | FullProf development begun. Collaboration with ILL kicked off | Delayed but started. Had ILL meeting in December. Two persons will visit ILL for a week in May to get collaboration started. LLB collaboration started in parallel.
’18-Q3 | ’18-11 | Recruitment of 2 persons for Mantid, 1 for SpinW, and 1 for analysis in general. | ✅ Neil, Igor, Simon W and Andrew Sazonov recruited (+ Mads for PaNOSC)
’18-09 | ’18-09 | Office move. | ✅ Presumably completed – now with curtains!
’18-09 | ’18-08 | Reduction on the fly. Data can be reduced on the fly for SANS2D for acceptance test but only low flux. | ✅ Demonstrated on local setup reading data from kafka stream.
’18-10 |  | Data reduction from NeXus. Data reduction of test workflow available from NeXus files. | ✅ have been possible for a long time
’18-11 | ’19-04 | Integration of reduction and analysis services. Data can be reduced and analyzed on the fly for limited flux for instrument(s) chosen for acceptance test. | ✅ Works, although not with Kafka
DRAM Time line and milestones (Fall 2018)
- Version: March 2018
Notes: SasView:
Serious QA (Richard Heenan) at codecamp revealed several bugs. Thus, only alpha version will be used at codecamp.
Proper resolution function for ToF is not implemented (version 5.1)
Lessons-learned for next STAP meeting
Fullprof:
We do not get the feeling that the diffraction group at ILL is embracing the collaboration or open sourcing the software. We have not been able to setup a meeting so far, they have a lot of requirements for such a collaboration. Scientific computing group has not been involved.
Conclusion:
1) We should collaborate with ILL diffraction group but not rely on this collaboration

## Slide 6: DRAM Timeline and milestones (2019) - Version: March 2019
Planned | Anticipated | Description
’19-01 | ’19-05 | PaNOSC recruit(s) started. Linda Udby and Peter Willendrup seconded. ✅ 1 person recruited.
’19-02 |  | ✅ Data view integrated. Data on detector can be live-visualized with EC (Widget from Mantid).
’19-03 |  | ✅ Reduction view integrated. Reduced data can be live-visualized with EC (Widget from Mantid).
’19-05 |  | Software performance and integration testing validated. Data can be reduced and analyzed on the fly for expected flux of LoKI when in full operation Post batch processing can be performed on CPH cluster
’19-06 |  | Proof of operation (reduction). Data can be reduced on the fly for expected flux of LoKI when in full operation. Data are received from DAQ & Streaming system. Data can be post rereduced on cluster Need to be able to define the scaling parameter for the architecture rather than actually physically demonstrate
’19-09 |  | SINE2020 completed

## Slide 7: DRAM Timeline and milestones (2020 and beyond) - Version: March 2019
Planned | Description
’19-12 | LoKI data reduction & analysis ready for operation
’20-12 | ESTIA data reduction & analysis ready for operation
’20-12 | QENS data analysis ready for operation
’21-06 | ODIN data reduction & analysis ready for operation
’21-12 | BEER, DREAM, MAGIC data reduction & analysis ready for operation
’21-12 | CSPEC & BIFROST data reduction & analysis ready for operation
Planned | Latest possible start for Instrument Data Scientist (Cold Commissionig)
’22-01 | ESTIA
’22-01 | ODIN
’22-01 | BEER
’22-01 | CSPEC
’22-06 | BIFROST
’22-06 | LoKI
’22-07 | DREAM
’22-07 Beam On Target
Very tentative!

## Slide 8: DMSC integration milestones – on track (v.5 – April 2018)
Start procurement
DMSC ready for BOI
1. Cph server room
2. Lund server room
Procurement complete
Server room tested and validated
Hardware and link
installed and configured
4. Experiment Control
3. DAQ & Streaming
5. Data Reduction
CUB ready for installation
File writer complete
BrightnESS complete
Data available for
reduction and analysis
Proof of
exp. Control
of DAQ
Data reduced on the fly
Proof of Operation
Integration of
Analysis & reduction software
Proof of Operation
DAQ & Exp.Control
Integrated on
test beamline
V20 closes
CUB
access date
6. Data Analysis
V20 epics &timing
networks available
Data set and rate defined for acceptance testing
Data view
integrated
Reduction view
integrated
DMSC hardware installed in CUB
NeXus file definition ready
Data available
in Scicat
SINE2020 ends
Software performance &
Integration testing validated
External dep
Data processing for some flux
Data processing for expected flux
Batch post-processing
Full integration
0. DMSC
Mantid data views in NICOS
SANS2d
LoKI McStas
Notes: Add figures from Torben and GitHub

## Slide 9: DMSC integration milestones – on track (v.5 – April 2018)
Start procurement
DMSC ready for BOI
1. Cph server room
2. Lund server room
Procurement complete
Server room tested and validated
Hardware and link
installed and configured
4. Experiment Control
3. DAQ & Streaming
5. Data Reduction
CUB ready for installation
File writer complete
BrightnESS complete
Data available for
reduction and analysis
Proof of
exp. Control
of DAQ
Data reduced on the fly
Proof of Operation
Integration of
Analysis & reduction software
Proof of Operation
DAQ & Exp.Control
Integrated on
test beamline
V20 closes
CUB
access date
6. Data Analysis
V20 epics &timing
networks available
Data set and rate defined for acceptance testing
Data view
integrated
Reduction view
integrated
DMSC hardware installed in CUB
NeXus file definition ready
Data available
in Scicat
SINE2020 ends
Software performance &
Integration testing validated
External dep
Data processing for some flux
Data processing for expected flux
Batch post-processing
Full integration
0. DMSC
Mantid data views in NICOS
SANS2d
LoKI McStas
Notes: Add figures from Torben and GitHub

## Slide 10: Testing - Feedback from previous STAP
Testing:
For LoKI tests are performed for SANS2D data and LoKI McStas data at full flux and scaled SANS2D data (we have a NeXus streamer)
This model for testing will be used for all instruments
Have repository with updated instrument models
Have started collaboration with SAD to simulate impact of sample environments

## Slide 11: Mantid Team
Neil Vaytet
Igor Gudich
Will also train the rest of DRAM group in developing / contributing to Mantid

## Slide 12: The need for redesigning / refactoring the Mantid core
... and it is still not sufficiently flexible

## Slide 13: DataSet aka sci++
C++ library designed for handling experimental multi-dimensional datasets
Handles units, variance, and histograms
DREAM is used as driver
  To which extend can we avoid MPI?
Suggest to run sci++ independently of Mantid even though Mantid is the primary driver
Looking for opportunities to off-lift the burden of maintenance

## Slide 14: Reflectometry STAP
Reflectometry STAP. The STAP was advised that resources for data management and software were reduced. The STAP did not recognize ESS’s decision to invest resources in a new specular reflectometry data analysis software tool as compelling. The NIST REFL1D specular reflectometry analysis tool is widely used, robust, correct and supported by a team of software engineers. The STAP questions why reinvent the wheel?
Report in response: ESS policy to support all techniques with analysis software, realities of SINE2020 and in kind contributions. Ensure we have maintainable software when needed. The alternative would be to just install refl1d, which would not have made users happy.
Up-prioritised GUI work, have mockups for reflectometry work (resulted in up-prioritising similar work for diffraction). Created reference user group.

## Slide 15: Comparing SasView/SANS and BornAgain/reflectometry
Ver | Date | 
5.0 Demo | Sep 2018 | Code camp
5.0 alpha | Oct 2019 | SAS2018
5.0 beta1 | Oct 2019 | 
5.0 beta2 | Feb 2019 | 
5.0 released | May 2019? | 
Still some missing features
Still technical debt, e.g. single point of failure
Ver | Date | Features (simplified)
1.11 | Mar 2018 | Refl in Core
1.12 | May 2018 | Refl in GUI
1.13 | Oct 2018 | Fitting in GUI
1.14 | Dec 2018 | More fitting
1.15 | Feb 2019 | TOF in Core
Still some missing features
Need more user involvement - created reference user group

## Slide 16: Example of reflectometry mockup

## Slide 17: Diffraction
Powder diffraction (ILL) | Single crystal diffraction (LLB) | Computational Diffraction Env (CoDE)
Got some agreement to get collaboration started Céline and Andrew will visit ILL for a week in May to work jointly with Juan on CrysFML First objectives: ESS line profiles | Have had mutual ESS-LLB visits LLB developed library which replicates some functionality of CCSL, which they will now open source Will hook library into CoDE library | Python environment for diffraction Harmonized interface to different diffraction libraries, e.g. Fullprof and CCTBX Can use joint technologies across diffraction and spectroscopy, e.g. Atomic Simulation Environment (ASE), vtki for visualization, Avogadro for crystal visualization, etc. Links to sci++ and PaNOSC WP4 Enable us to assess specific technologies without involving partners and external libraries (e.g. for 2D Rietveld). I.e. we can collaborate without relying on it.
Established diffraction team
(Andrew, Céline, Piotr, Neil)

## Slide 18: STAP recommendations
STAP | Response
Data and Reduction views in NICOS at the next STAP meeting | Data View in NICOS but some documentation is still missing.
mitigate at-scale unkowns that have plagued previous generation facilities | NeXus streamer: real data, scaled real data and McStas simulations, V20. Have McStas instrument model repo.
Recruit the Data Scientists as soon as possible in 2020 | Pilot project with Céline for diffraction. Also have persons looking after large-scale structures and spectroscopy, but not necessarily instrument data scientists. Imaging? Ongoing.
Aspire to have a general look and feel independently of instrument (UX) | We aspire, but only have limited control of software across techniques. Ongoing.
Have clear and detailed requirements for the instrument teams software demands for the period 2021-2023 (commissioning needs through to steady state operations) | Have pretty good requirements, but still evolving. Ongoing.
take a leadership role for powder and single crystal diffraction, running user workshops to define a long-term strategy | have only run one user workshop so far on single crystal diffraction, but this should be an ongoing activity in the coming years. We have started collaboration with ILL and LLB and started our own in house project.
Carefully manage instrument team- and User community- expectations of longer-term analysis and modelling provision | Ongoing.

## Slide 19: PARADISE

## Slide 20: In brief
Staff. Two new group members and one new secondment
  ➡️ Started to reorganize work (agile project organization)
Dev. Projects. Current projects, primarily in house:
  Ready for operation of LoKI (DONKI)
  sci++ project (C++ library for experimental data sets)
  Computational Diffraction Environment (CoDE) / Visualization in Python (VisPy)
Diffraction. Started collaboration with ILL and LLB as well as in house CoDE project.
Instrument data scientists. Started pilot project
Milestones. More or less on track.
External funding.
  Last SINE2020 WP10 workshop in May
  PaNOSC started
  AMEN VR project funded
  PARADISE H2020 project submitted
Stakeholders. Challenges from reflectometry stap & annual review

## Slide 21: BornAgain vs FZJ - Commits at GitHub
Refl1d
BornAgain