## Slide 1: Ion Source and LEBT Transition from Installation to Testing and Commissioning
Alejandro Garcia Sosa
European Spallation Source
Lessons Learned - August 28, 2019

## Slide 2: Outline
Issues
  ISRC Coils
  Grounding
  LEBT Solenoids
  LEBT Chopper
  IRIS
  ISRC Repeller
  Magnetron
Conclusions
Top 3 issues

## Slide 3: ISRC Coils
Wrong connections
Found out when readouts from coils 1 and 3 were linked

## Slide 4: Issues: Grounding
Electrical Panel
Electronics rack

## Slide 5
Single-phase Model of HV platform Power Distribution
Isolation transformer
Phase and Neutral HV cables
Electrical Panel Surge Suppressor
Phase and Neutral LV cable to Electronics rack
Grounding wire to platform
Power Supply w/ internal Surge Suppressor
FUG HV Power Supply (100 kV DC)
Spark generator
HV platform

## Slide 6
Single-phase Model of HV platform Power Distribution
(Simulation model, including sensors and energy estimators)

## Slide 7
Current HV cables:- 20m long cable
Zoom at arcing instant
Electronics rack
Electrical Panel

## Slide 8
Shorten HV cables only:- 5m long cable
Zoom at arcing instant
Electronics rack
Electrical Panel

## Slide 9
Current HV cables (20m long) + Foil on GND link + EMC filter
Zoom at arcing instant
Electronics rack
Electrical Panel

## Slide 10: EMC grounding

## Slide 11
HV Power Supply
Isolation Transformer
Racks
Pads provide access to
the mesh beneath the concrete
Enclosed Cable tray for
Isolation transformer cables.
Enclosed Cable tray for
HV power supply cables
Pad
Pad
Pad
Pad
Tunnel
FEB090

## Slide 12: Issues: LEBT Solenoids
LEBT Solenoids have an issue in the connectors of the cooling circuit that make them prone to leak
Corrector magnets use single polarity PS. Polarity is switched using relays that have their own set of issues
Polarities of H1 V1 were swapped.
Sol 1 and 2 had opposite polarities

## Slide 13: LEBT Solenoid 2 water leak
LEBT Sol 2 water leak
Hard to access given this design
Water cleanliness issues already apparent

## Slide 14: Issues: LEBT Chopper
Commissioning of the chopper started on March 5
Issues reaching the nominal voltage during testing

## Slide 15
27Ω
1nF
27Ω
HV Switch
HTS 151-03 GSM Behlke
HV Power Supply
ML12N25 Glassman
Interface
HVS module
LV module
TTL
Fast/Slow Alarm
Fast Beam Stop
Chopper Enable
Fault
Voltage Reference
V / I Monitor
Reshasped
HV module
RF 35
Caburn Feedthrough
20 meters

## Slide 16: Chopper testing setup
Not enough power outlets in the tunnel!
Installation setup by IK-partner does not fit our reality and needs!

## Slide 17: Issues: IRIS
IRIS could never be tested on site by IK or ESS
Need to transfer the controls standard from Geobrick to Beckhoff (EtherCAT)
Need to remove the IRIS for disassembly and debugging.

## Slide 18: Issues: IRIS
Wrong pinout in connector #6
Some pins are crimped, some are soldered

## Slide 19: ISRC Repeller
Repeller failed due to a resistive connection
Surprise! Actual parts installed do not match drawings!

## Slide 20: Magnetron issues
Fault: Over-voltage
Major operation just to access the issue: Traced to a burned cable

## Slide 21: Conclusions
Extensive debugging and troubleshooting of all systems
This could be avoided by allocating sufficient time for local and integrated tests of each system
This had a significant impact on the time available for testing and commissioning of the ISRC & LEBT
Lack of spares

## Slide 22: Top 3 Issues that we need to improve
 | Issue | Comments
1. | Compartmentalized nature of work at ESS | Should work together at one team, one machine.
2. | Excessive bureaucracy and volatile rules | Creates confusion and adds delay
3. | Lack a comprehensive acceptance test and review of components from IK-partners | Issues are known but accountability and IK-agreement follow-up still an issue

## Slide 23: Thank you! Questions?

## Slide 24
BACKUP SLIDES

## Slide 25: 3D Model

## Slide 26: 3D Model

## Slide 27: Top view of ISRC & LEBT
PSS0 Entry
Connection to grounding
mesh in the floor
Ion source
water cooling
Connection to
wall grounding

## Slide 28: Ion Source + LEBT
December 2017 – LEBT and source shipped from Catania to Lund
January 2018 to May 2018 – Installations in the tunnel
July 2018 – Safety Readiness Review
September 2018 – Start of commissioning
November 2018 to January 2019 – Sparks from the High Voltage cause damages to a few power supplies, new work with grounding required
February 2019 – Commissioning restarts
July 2019 – End of commissioning and start of RFQ installations
Installation and Commissioning timeline

## Slide 29: LEBT-RFQ lattice interface

## Slide 30: Ion Source
Microwave Discharge Ion Source (MDIS)
30
Waveguide
3 Solenoids
Plasma chamber
Gas injection
High voltage insulator
Extraction electrodes
Pumping ports
50 cm
Notes: The Ion Source of ESS is a Microwave Discharge Ion Source. These sources produce high currents of singly charged ions with low emittance. A stepped matching transformer is used to allow smooth transition between the waveguide and plasma chamber impedances. An extraction system with a repeller electrode is employed to limit the back-streaming electrons. Microwave Discharge sources differ from ECR sources in the sense that they operate slightly off-resonance and the plasma is not completely confined by the magnetic field. Also, ECR sources have an additional hexapole field surrounding the plasma chamber to further confine the plasma and obtain ions of high charge states.

## Slide 31: The ion source sits inside a 75 kV high voltage platform
Waveguide
3 Solenoids
Magnetron head
Electronics rack
Ceramic insulators
Electrical panel
Notes: The ion source sits inside a high-voltage platform biased at 75 kV DC during operation. This setup provides the voltage difference to ground that allows the extraction of protons from the source plasma. In this picture you can see the HV platform with all its doors open and the ceiling panels removed. You can also see the high-voltage insulators, the electronics rack, the electrical panel, the magnetron head, the waveguide and the coils of the Ion source with the plasma chamber inside.

## Slide 32: The Low Energy Beam Transport (LEBT) matches the beam to the RFQ input
Ion Source
– creates the H+ beam
Iris
– controls the current
Chopper and collimator
– controls the pulse length
Solenoid
– focuses the beam
Notes: The LEBT matches the beam to the entrance of the RFQ. In the LEBT, immediately after the ion source and extraction electrodes, we have a small tank with vacuum ports for turbopumps, vacuum gauges and a Residual Gas Analyzer (RGA). We have two solenoids for beam focusing, the iris, which is a moveable aperture to control the beam current, and also a diagnostics tank where the Chopper is. The chopper discards the tails of the beam pulse into the collimator, just before the entrance of the RFQ.

## Slide 33: Using simulations, we can simulate the beam transport through the LEBT
H+
H3+
H2+
Notes: Using IBSimu we can simulate the beam transport through the LEBT. Here we can see a very divergent beam scraping at the 1st solenoid, the blade of the IRIS, the chopper and then the 2nd solenoid, arriving to the collimator with a beam that has a very high proton ratio, while other species like H2+ and H3+ are left behind.