## Sheet1
General Beamline systems
Power installed
Beamline primary network switch, enclosure and cable routing designed and installed
Primary network switch connected to Comms room
H01 Server room Connection commissioned & verified.
Routing to main areas designed and installed depends on build out schedule
Detector back end
Motion control
Choppers
Sample area & Staging /preparation area/ Control cabin / offices / labs
Control Cabin screens and clients installed & commissioned
Timing system installation
Timing system routing designed
Location of components wrt device requireing timing infomation
Installation of cables and EVRs (containing devices)
testing and verification of timing signal
Routing to main areas designed and then installed depends on build out schedule
Detector front end
Motion control
Choppers
Sample area & Staging /preparation area/ Control cabin / offices / labs
Motion systems either per system or per area | (Timing system actually required for mca generally?)
Cable tray and network infrastructure installed
Control infrastructure installed and connected.
System ‘A' installation complete
System ‘A’ Integration
[5 empty] | EPICS Integration of PLC montion controller Integration through to NICOS | Much complexity is hidden in theis phase
Verification of control via NICOS
Complete after end to end test
Chopper systems | (Integration and commissioning before closure of shielding)
Cable tray and network infrastructure installed
Control infrastructure CHIC installed and connected.
Timing system installation complete
Timing system / CHIC system verification
System ‘A' installation complete
System ‘A’ integration
[7 empty] | EPICS Integration of CHIC Integration through to NICOS | Much complexity is hidden in theis phase
Verification of control via NICOS
Complete after end to end test
Detector and monitor systems (treat monitors and detectors the same?)
Ancillary system design complete - link to some SAT / FAT / CDR
Ancillary system integration design complete - link to SAT?
Detector ancillary systems installation complete
Detector ancillary systems integration complete
Detector electronics design complete
Detector network design complete
conduit and network infrastructure installed.
Network and Timing system installation complete
Detector electronics installed and cabled
Detector panel ‘A’ Installed
|  | Panel position surveyed. |  |  |  | EFUs installed with network connection.
kafka cluster installed and commissioned
Topics defined? - too detailed - need naming convention generally here
Detector DAQ / EFU commissioning test with source?
Storage system commissioning
File writer commissioning complete
Software requirements
Requirements -
Surveyed positions for
Chopper axis positions
Guide geometry & alignment
sample position
detector panel positions / offsets of active area for surveyed positions
individual pixel / voxel locations can be derived
Monitor positions
Surveyed L1 and L2 flightpaths
geometry co-ordinates to follow mantid convention with z as beam direction - thus R,T,P will work directly
Pre calibrations either lab or part of cold commissioning
Chopper axis geometry and slit positions from lab tests
Motor calibration of steps / mm and sense - (part of cold commissioning of motion axis)
Chopper geometry pre calibration
Development requirements
Formulism for effieciency correction
EPICS names IOCS
Timing system
Requirements for instrument specific control components collected - Instrument Software Project - IDS
Development & Integration of integration if instrument specific controls components complete
Control program commissioning complete
Requirements for instrument specific data reduction collected - Instrument Software Project - IDS
Development of data reduction and corrections - post BOT for actual meaning
data reduction commissioning and verification
Hot Commissioning