## Sheet1
|  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
West Sector | BEER | [29 empty] | Staff required for Tollgates, ESS interfaces, general instrument support etc
Staff required during installation and cold commisioning
|  | Sample environment Integration |  | 2020 Q4: 0.1; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.1; 2023 Q2: 0.2; 2024 Q2: 0.3; 2024 Q4: 0.1 |  |  |  | Staff required for Hot commisioning
|  | Neutron chopper integration |  | 2020 Q2: 0; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.5; 2021 Q4: 0.2; 2022 Q1: 0; 2022 Q2: 0; 2022 Q3: 0.5; 2024 Q4: 0.1 |  |  |  | Staff required for start of user programme
|  | Detector system controls integration |  | 2020 Q2: 0.1; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0; 2021 Q4: 0; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2024 Q4: 0.1
|  | Motion control integration |  | 2021 Q2: 0.5; 2021 Q3: 0.5; 2022 Q2: 0; 2022 Q3: 0.5; 2022 Q4: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q1: 0.2; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q4: 0.1
|  | Network and infrastructure integration | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.1
| CSPEC | [28 empty] | 150 | hours per months
|  | Sample environment Integration |  | 2020 Q4: 0.1; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.1; 2023 Q2: 0.2; 2024 Q2: 0.3; 2024 Q3: 0.1; 2024 Q4: 0.1 |  |  | 0.1 | FTE equals | 15 | hours per month or | 45 | hours per quarter
|  | Neutron chopper integration |  | 2020 Q2: 0; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.5; 2021 Q4: 0.2; 2022 Q1: 0; 2022 Q2: 0; 2022 Q3: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1 |  |  | 0.5 | FTE equals | 75 | hours per month or | 225 | hours per quarter
|  | Detector system controls integration |  | 2020 Q2: 0.1; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0; 2021 Q4: 0; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1 |  |  | 1 | FTE equals | 150 | hours per month or | 450 | hours per quarter
|  | Motion control integration |  | 2021 Q2: 0.5; 2021 Q3: 0.5; 2022 Q2: 0; 2022 Q3: 0.5; 2022 Q4: 0.5 |  |  | 2 | FTE equals | 300 | hours per month or | 900 | hours per quarter
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q1: 0.2; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.1
TREX
|  | Sample environment Integration |  | 2023 Q2: 0.1; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2022 Q4: 0; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0; 2024 Q4: 0
|  | Detector system controls integration |  | 2022 Q4: 0.1; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0; 2024 Q2: 0; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Motion control integration |  | 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q4: 0
|  | Innstrument control (HMI) and DAQ integration |  | 2023 Q3: 0.2; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2022 Q4: 0.1; 2023 Q1: 0.1; 2023 Q2: 0.1; 2023 Q3: 0.1; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.5; 2024 Q4: 0.5
HEIMDAL
|  | Sample environment Integration |  | 2023 Q2: 0.1; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2022 Q4: 0; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0; 2024 Q4: 0
|  | Detector system controls integration |  | 2022 Q4: 0.1; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0; 2024 Q2: 0; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Motion control integration |  | 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q4: 0
|  | Innstrument control (HMI) and DAQ integration |  | 2023 Q3: 0.2; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2022 Q4: 0.1; 2023 Q1: 0.1; 2023 Q2: 0.1; 2023 Q3: 0.1; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.5; 2024 Q4: 0.5
NMX
|  | Sample environment Integration |  | 2023 Q2: 0.1; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2022 Q4: 0; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0; 2024 Q4: 0
|  | Detector system controls integration |  | 2022 Q4: 0.1; 2023 Q1: 0.2; 2023 Q2: 0.5; 2023 Q3: 0.2; 2023 Q4: 0; 2024 Q2: 0; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Motion control integration |  | 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q4: 0
|  | Innstrument control (HMI) and DAQ integration |  | 2023 Q3: 0.2; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q2: 0.5; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2022 Q4: 0.1; 2023 Q1: 0.1; 2023 Q2: 0.1; 2023 Q3: 0.1; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.5; 2024 Q4: 0.5
BIFROST
|  | Sample environment Integration |  | 2020 Q4: 0.1; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.1; 2023 Q2: 0.2; 2024 Q2: 0.3
|  | Neutron chopper integration |  | 2020 Q2: 0; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.5; 2021 Q4: 0.2; 2022 Q1: 0; 2022 Q2: 0; 2022 Q3: 0.5
|  | Detector system controls integration |  | 2020 Q2: 0.1; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0; 2021 Q4: 0; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5
|  | Motion control integration |  | 2021 Q2: 0.5; 2021 Q3: 0.5; 2022 Q2: 0; 2022 Q3: 0.5; 2022 Q4: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q1: 0.2; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 0.5; 2023 Q4: 0.5
|  | Network and infrastructure integration | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0
MAGIC
|  | Sample environment Integration |  | 2020 Q4: 0.1; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.1; 2023 Q2: 0.2; 2024 Q2: 0.3; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2020 Q2: 0; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0.2; 2021 Q3: 0.5; 2021 Q4: 0.2; 2022 Q1: 0; 2022 Q2: 0; 2022 Q3: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Detector system controls integration |  | 2020 Q2: 0.1; 2020 Q3: 0.2; 2020 Q4: 0.5; 2021 Q1: 0.2; 2021 Q2: 0; 2021 Q4: 0; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Motion control integration |  | 2021 Q2: 0.5; 2021 Q3: 0.5; 2022 Q2: 0; 2022 Q3: 0.5; 2022 Q4: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q1: 0.2; 2021 Q2: 0.5; 2021 Q3: 0.5; 2021 Q4: 0.5; 2022 Q1: 0.5; 2022 Q2: 0.5; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 0.5; 2023 Q4: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.1
MRACLES
|  | Sample environment Integration |  | 2024 Q1: 0.1; 2024 Q2: 0.2; 2024 Q3: 0.2; 2024 Q4: 0.2
|  | Neutron chopper integration |  | 2023 Q3: 0; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0.2; 2024 Q4: 0.5
|  | Detector system controls integration |  | 2023 Q3: 0.1; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0
|  | Motion control integration |  | 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2024 Q2: 0.2; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2023 Q3: 0.1; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
North Sector | LOKI
|  | Sample environment Integration |  | 2021 Q4: 0.1; 2022 Q1: 0.2; 2022 Q2: 0.2; 2022 Q3: 0.2; 2023 Q3: 0.2; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2021 Q2: 0; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.2; 2022 Q2: 0.2; 2022 Q3: 0.5; 2022 Q4: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Detector system controls integration |  | 2021 Q2: 0.1; 2021 Q3: 0.2; 2021 Q4: 0.5; 2022 Q1: 0.2; 2022 Q2: 0; 2022 Q4: 0.5; 2023 Q1: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Motion control integration |  | 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2022 Q1: 0.2; 2022 Q2: 0.5; 2022 Q3: 0.5; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1; 2023 Q4: 0.5; 2024 Q1: 0.5; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration | [10 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1
FREIA
|  | Sample environment Integration |  | 2024 Q2: 0.1; 2024 Q3: 0.2; 2024 Q4: 0.2 | 0.2
|  | Neutron chopper integration |  | 2023 Q4: 0; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.2; 2024 Q4: 0.2 | 0.5
|  | Detector system controls integration |  | 2023 Q4: 0.1; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.2; 2024 Q4: 0
|  | Motion control integration |  | 2024 Q4: 0.5 | 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2024 Q3: 0.2; 2024 Q4: 0.5 | 0.5
|  | Network and infrastructure integration |  | 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1 | 0.1
East & South | ODIN
|  | Sample environment Integration |  | 2022 Q1: 0.1; 2022 Q2: 0.2; 2023 Q2: 0.2; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2021 Q3: 0; 2021 Q4: 0.3; 2022 Q1: 0.5; 2022 Q2: 0.3; 2022 Q3: 0.5; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Detector system controls integration |  | 2021 Q3: 0.1; 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q2: 0.2; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Motion control integration |  | 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q4: 0.1
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q3: 0.2; 2021 Q4: 0.2; 2022 Q1: 0.3; 2022 Q2: 0.3; 2022 Q3: 1; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 0.5; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration |  | 2021 Q3: 0.1; 2021 Q4: 0.1; 2022 Q1: 0.1; 2022 Q2: 0.1; 2022 Q3: 0; 2022 Q4: 0; 2023 Q1: 0; 2023 Q2: 0; 2023 Q3: 0; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
DREAM
|  | Sample environment Integration |  | 2022 Q1: 0.1; 2022 Q2: 0.2; 2022 Q3: 0.1; 2023 Q3: 0.2; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2021 Q3: 0; 2021 Q4: 0.3; 2022 Q1: 0.5; 2022 Q2: 0.3; 2022 Q3: 0; 2022 Q4: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Detector system controls integration |  | 2021 Q3: 0.1; 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q2: 0.2; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Motion control integration |  | 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q3: 0; 2022 Q4: 0.5; 2023 Q1: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q3: 0.2; 2021 Q4: 0.2; 2022 Q1: 0.3; 2022 Q2: 0.3; 2022 Q3: 0.5; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1; 2023 Q4: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration |  | 2021 Q3: 0.1; 2021 Q4: 0.1; 2022 Q1: 0.1; 2022 Q2: 0.1; 2022 Q3: 0.5; 2022 Q4: 0; 2023 Q1: 0; 2023 Q2: 0; 2023 Q3: 0; 2023 Q4: 0; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
ESTIA
|  | Sample environment Integration |  | 2022 Q1: 0.1; 2022 Q2: 0.2; 2022 Q3: 0.1; 2023 Q3: 0.2; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2021 Q3: 0; 2021 Q4: 0.3; 2022 Q1: 0.5; 2022 Q2: 0.3; 2022 Q3: 0; 2022 Q4: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Detector system controls integration |  | 2021 Q3: 0.1; 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q2: 0.2; 2022 Q3: 0.5; 2022 Q4: 0.5; 2023 Q1: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Motion control integration |  | 2021 Q4: 0.2; 2022 Q1: 0.5; 2022 Q3: 0; 2022 Q4: 0.5; 2023 Q1: 0.5
|  | Innstrument control (HMI) and DAQ integration |  | 2021 Q3: 0.2; 2021 Q4: 0.2; 2022 Q1: 0.3; 2022 Q2: 0.3; 2022 Q3: 0.5; 2022 Q4: 1; 2023 Q1: 1; 2023 Q2: 1; 2023 Q3: 1; 2023 Q4: 0.5; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
|  | Network and infrastructure integration |  | 2021 Q3: 0.1; 2021 Q4: 0.1; 2022 Q1: 0.1; 2022 Q2: 0.1; 2022 Q3: 0.5; 2022 Q4: 0; 2023 Q1: 0; 2023 Q2: 0; 2023 Q3: 0; 2023 Q4: 0; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.1
SKADI
|  | Sample environment Integration |  | 2024 Q2: 0.1; 2024 Q3: 0.2; 2024 Q4: 0.1
|  | Neutron chopper integration |  | 2023 Q4: 0; 2024 Q1: 0.3; 2024 Q2: 0.5; 2024 Q3: 0.3; 2024 Q4: 0
|  | Detector system controls integration |  | 2023 Q4: 0.1; 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q3: 0.2; 2024 Q4: 0.5
|  | Motion control integration |  | 2024 Q1: 0.2; 2024 Q2: 0.5; 2024 Q4: 0
|  | Innstrument control (HMI) and DAQ integration |  | 2023 Q4: 0.2; 2024 Q1: 0.2; 2024 Q2: 0.3; 2024 Q3: 0.3; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.1; 2024 Q4: 0.5
VESPA
|  | Sample environment Integration |  | 2024 Q1: 0.1; 2024 Q2: 0.2; 2024 Q3: 0.1; 2024 Q4: 0.5
|  | Neutron chopper integration |  | 2023 Q3: 0; 2023 Q4: 0.3; 2024 Q1: 0.5; 2024 Q2: 0.3; 2024 Q3: 0; 2024 Q4: 0
|  | Detector system controls integration |  | 2023 Q3: 0.1; 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q2: 0.2; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Motion control integration |  | 2023 Q4: 0.2; 2024 Q1: 0.5; 2024 Q3: 0; 2024 Q4: 0
|  | Innstrument control (HMI) and DAQ integration |  | 2023 Q3: 0.2; 2023 Q4: 0.2; 2024 Q1: 0.3; 2024 Q2: 0.3; 2024 Q3: 0.5; 2024 Q4: 0.5
|  | Network and infrastructure integration |  | 2023 Q3: 0.1; 2023 Q4: 0.1; 2024 Q1: 0.1; 2024 Q2: 0.1; 2024 Q3: 0.5; 2024 Q4: 0.5
| INSTRUMENT PROJECTS SUB-TOTAL | [26 empty] | Average
|  | Sample environment Integration |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 0.4 | 0.8 | 0.8 | 0.8 | 2.1 | 2.5 | 1.2 | 0.4 | 0 | 0 | 1.3 | 1.2 | 0.7 | 1.1 | 3.6 | 2.8 | 2 | 1.3208 | 7.925 | 855.9
|  | Neutron chopper integration |  | 1 | 1 | 1 | 1 | 1 | 0 | 0.8 | 2 | 0.8 | 0.8 | 2.2 | 2.2 | 1.7 | 1.1 | 3 | 1.5 | 0.6 | 1.5 | 0.6 | 1.2 | 3.3 | 2.4 | 1.3 | 1.4 | 1.3917 | 8.35 | 901.8
|  | Detector system controls integration |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.4 | 0.8 | 2 | 0.8 | 0.1 | 0.5 | 1.1 | 3.7 | 2.6 | 3.5 | 4.3 | 2.1 | 1.5 | 0.8 | 0.7 | 1.7 | 1.7 | 3 | 3.2 | 1.75 | 10.5 | 1134
|  | Motion control integration |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0.6 | 1.5 | 0.5 | 2.5 | 3.5 | 1.5 | 0 | 0 | 1.8 | 2.2 | 0.5 | 0.5 | 1 | 1.0042 | 6.025 | 650.7
|  | Innstrument control (HMI) and DAQ integration |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0.8 | 2 | 2.6 | 2.6 | 3.1 | 3.4 | 6.5 | 8 | 8 | 8 | 6.3 | 5.5 | 2.8 | 2.6 | 3.6 | 4.2 | 3.6667 | 22 | 2376
|  | Network and infrastructure integration |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.4 | 0.4 | 0.4 | 0.5 | 0.8 | 0.8 | 2.4 | 2.4 | 1.1 | 0.3 | 0.3 | 0.3 | 0.5 | 0.8 | 1.4 | 1.1 | 2.9 | 3.4 | 1.0917 | 6.55 | 707.4
6625.8
|  |  |  | 2019 Q4: Y tot; 2020 Q1: Y cost; 2020 Q4: Y tot; 2021 Q1: Y cost; 2021 Q4: Y tot; 2022 Q1: Y cost; 2022 Q4: Y tot; 2023 Q1: Y cost; 2023 Q4: Y tot; 2024 Q1: Y cost; 2024 Q4: Y tot | Y cost |  | Total Req | Current staff in NSS
|  | Sample environment Integration |  | 2019 Q4: 1.5; 2020 Q1: 162; 2020 Q4: 1.1; 2021 Q1: 118.8; 2021 Q4: 1.125; 2022 Q1: 121.5; 2022 Q4: 1.025; 2023 Q1: 110.7; 2023 Q4: 0.8; 2024 Q1: 86.4; 2024 Q4: 2.375 | 256.5 |  | 855.9 | 648
|  | Neutron chopper integration |  | 2019 Q4: 1; 2020 Q1: 108; 2020 Q4: 0.95; 2021 Q1: 102.6; 2021 Q4: 1.5; 2022 Q1: 162; 2022 Q4: 1.825; 2023 Q1: 197.1; 2023 Q4: 0.975; 2024 Q1: 105.3; 2024 Q4: 2.1 | 226.8 |  | 901.8
|  | Detector system controls integration |  | 2019 Q4: 1.5; 2020 Q1: 162; 2020 Q4: 1.175; 2021 Q1: 126.9; 2021 Q4: 0.625; 2022 Q1: 67.5; 2022 Q4: 3.525; 2023 Q1: 380.7; 2023 Q4: 1.275; 2024 Q1: 137.7; 2024 Q4: 2.4 | 259.2 |  | 1134
|  | Motion control integration |  | 2019 Q4: 1; 2020 Q1: 108; 2020 Q4: 0.25; 2021 Q1: 27; 2021 Q4: 0.9; 2022 Q1: 97.2; 2022 Q4: 2; 2023 Q1: 216; 2023 Q4: 0.825; 2024 Q1: 89.1; 2024 Q4: 1.05 | 113.4 |  | 650.7 | 648
|  | Innstrument control (HMI) and DAQ integration |  | 2019 Q4: 3; 2020 Q1: 324; 2020 Q4: 1.5; 2021 Q1: 162; 2021 Q4: 2; 2022 Q1: 216; 2022 Q4: 5.25; 2023 Q1: 567; 2023 Q4: 6.95; 2024 Q1: 750.6; 2024 Q4: 3.3 | 356.4 |  | 2376 | 2376
|  | Network and infrastructure integration |  | 2019 Q4: 1; 2020 Q1: 108; 2020 Q4: 0.7; 2021 Q1: 75.6; 2021 Q4: 0.625; 2022 Q1: 67.5; 2022 Q4: 1.55; 2023 Q1: 167.4; 2023 Q4: 0.475; 2024 Q1: 51.3; 2024 Q4: 2.2 | 237.6 |  | 707.4
[30 empty] | 6625.8 | 3672 | 2953.8
| TOTAL |  |  | 9 | 9 | 9 | 9 | 9 | 5.9 | 3 | 4.8 | 3.6 | 5.7 | 8.4 | 9.4 | 14.9 | 11.2 | 17 | 17.6 | 12.5 | 12.6 | 9.4 | 10.7 | 12.5 | 11.9 | 14.1 | 15.2
installaiton
staff profile
|  | Experimemnt Control and Data curation |  | 7 | 7 | 7 | 7 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
|  | Detectors |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  | choppers |  | 6 | 6 | 7 | 7 | 8 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  | MCA |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
BCG staff
|  | SE int |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Choppes | bar: 2019 Q1 to 2024 Q4
|  | Detector integration |  | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Motion control | bar: 2019 Q1 to 2024 Q4
|  | Experiment Control and DAQ |  | 3 | 3 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
|  | Network infrastructure |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Total |  | 6.5 | 6.5 | 8.5 | 8.5 | 9.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 12.5 | 12.5 | 12.5 | 12.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
Deltas
|  | SE int |  | -0.5 | -0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1.6 | 1.2 | 1.2 | 1.2 | -0.1 | -0.5 | 0.8 | 1.6 | 2 | 2 | 0.7 | 0.8 | 1.3 | 0.9 | -1.6 | -0.8 | 0
|  | Choppes |  | 0 | 0 | 0 | 0 | 0 | 1 | 0.2 | -1 | 0.2 | 0.2 | -1.2 | -1.2 | -0.7 | -0.1 | -2 | -0.5 | 0.4 | -0.5 | 0.4 | -0.2 | -2.3 | -1.4 | -0.3 | -0.4
|  | Detector integration |  | -1.5 | -1.5 | -0.5 | -0.5 | -0.5 | 0.6 | 0.2 | -1 | 0.2 | 0.9 | 0.5 | -0.1 | -2.7 | -1.6 | -2.5 | -3.3 | -1.1 | -0.5 | 0.2 | 0.3 | -0.7 | -0.7 | -2 | -2.2
|  | Motion control |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | -0.5 | -0.5 | 0.4 | -0.5 | 0.5 | -1.5 | -2.5 | -0.5 | 1 | 1 | -0.8 | -1.2 | 0.5 | 0.5 | 0
|  | Experiment Control and DAQ |  | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 5 | 4.2 | 3 | 4.4 | 4.4 | 3.9 | 3.6 | 2.5 | 1 | 1 | 1 | 2.7 | 3.5 | 6.2 | 6.4 | 5.4 | 4.8
|  | Network infrastructure |  | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | 0.1 | 0.1 | 0.1 | 0 | -0.3 | -0.3 | -1.9 | -1.9 | -0.6 | 0.2 | 0.2 | 0.2 | 0 | -0.3 | -0.9 | -0.6 | -2.4 | -2.9
|  | Total |  | -2.5 | -2.5 | -0.5 | -0.5 | 0.5 | 4.6 | 7.5 | 5.7 | 6.9 | 4.8 | 4.1 | 3.1 | -2.4 | 1.3 | -2.5 | -3.1 | 2 | 1.9 | 5.1 | 3.8 | 2 | 2.6 | 0.4 | -0.7

## Sheet2
| 2020 | 2021 | 2022 | 2023 | 2024
installtion | 7.6 | 28.1 | 31.3 | 15 | 41.6
hot commisoning | 0 | 0 | 30 | 30.2 | 2
operations | 0 | 0 | 0 | 7.5 | 7.5
| 2020 | 2021 | 2022 | 2023 | 2024
BCG Core activities | 8 | 4 | 2 | 2 | 2
Installation | 1.9 | 7.025 | 7.825 | 3.75 | 10.4
Hot Commissioning | 0 | 0 | 7.5 | 7.55 | 0.5
Operations | 0 | 0 | 0 | 1.875 | 1.875
Staff Plan | 6.5 | 10 | 13.5 | 14.5 | 14.5
total | 8.4 | 17.025 | 28.825 | 27.675 | 27.275
| 2020 | 2021 | 2022 | 2023 | 2024
staff plan | 6.5 | 10 | 13.5 | 14.5 | 14.5