## Slide 1: NCL Beam Commissioning - Coordination/Plan/Steps -
Ryoichi Miyamoto (Beam Commissioning Coordinator)
2020-01-29~30
ESS Accelerator Testing and Commissioning Workshop

## Slide 2: Outline
Introduction
  Beam commissioning aspects
  Coordination matters in light of experiences from ISrc and LEBT
NCL beam commissioning plan
  Situation and objectives
Steps for the upcoming stage
  ISrc restart
  RFQ injection preparation
  Probe beam threading to MEBT FC
  Low current tuning (MEBT linear optics)
Summary and outlook

## Slide 3: Introduction

## Slide 4: Beam commissioning aspects (definitions)
Subsystems (components) verifications with beam
  Overlap with testing team.
  Verify magnets, LLRF, diagnostics, protections, shielding, ...
  Occupy 50-75% of time, from experiences of other machines.
Tuning beam parameters
  Mandate of beam physicists.
  Low current (centroid) tuning: steering, RF setting, ...
  High current (phase space) tuning: matching, loss mitigation, ...
  If all the subsystems work perfectly, tuning activities could be short.
Preparations to operations
  Overlap with operations team.
  Handing over subsystems and setting, training operators, ...
  Power ramp-up?
  Availability improvement?

## Slide 5: How we did ISrc-LEBT beam commissioning? - Subsystems verifications with beam
For many subsystems, verifications were left in incomplete state.
Preparations can improve.
  A lot of improvising tests.
  Need more inputs from owners, especially what to do in a control room.
  Improve communication among stakeholders, on interfaces and especially on conventions.
    Don’t forget the “colorful” polarity errors in solenoids, steerers, and NPM.
Note priority was given for collecting measurement data, because of:
  Initial issues and time limit
  Commissioning tank available only for that stage
Was/is the whole chain from testing to handing-over clear?
Reports?
  The previous workshop pointed out the issue of a single person in charge of multiple aspects.

## Slide 6: How we did ISrc-LEBT beam commissioning? - Tuning beam parameters
Missing critical components meant:
  Spent a large fraction of time on unplanned improvising measurements.
  The original straight-line plan failed abysmally.
    The brainstorming during planning was vital.
    For the upcoming stage for RFQ and MEBT, we already plan for the minimal machine state and there is much less flexibility for this to happen.
Unexpected characteristics of beam also led to a lot of unplanned improvising measurements.
  Large trajectory error
  Large emittance
  (Polarity errors)
Scripting with jupyter saved the day.
How improvising measurements fit to the engineering handbook?
Reports?
  The same situation as the subsystems verifications.

## Slide 7: Some statistics from ISrc-LEBT commissioning
The first beam was achieved on 2018-09-19, but the effective duration was ~3.5 months from 2019-02-08 to 2019-07-03, minus ~1.5 month for water piping works.
  For 1 month out of ~3.5 months, 2nd solenoid was missing.
In ~3.5 months, we had 88 shifts scheduled to have beam.
The average beam availability per shift over those 88 shifts was 4:56, but improved to 7:54 after 2019-06-12.
Now counting the ratio between the verifications vs tuning....
  We’ll see the case for the NCL commissioning.
  Could use some help/inputs from operations and RAMI folks.

## Slide 8: NCL beam commissioning plan

## Slide 9: Situation for the upcoming commissioning
Technical homework from the ISrc and LEBT beam commissioning
  Beam mode production (short term)
    Timing system
    Iris
    New LEBT chopper
  Beam quality (long term)
    Large emittance (initial divergence?)
    Large trajectory error (initial divergence and solenoids)
Missing Bunchers and DTL1
Diagnostics
  Available
    ISrc+LEBT: FC, BCMs
    RFQ+MEBT: FC, BCMs, BPMs, FBPM, nBLMs
  Missing (likely)
    ISrc+LEBT: Dpl, NPMs, EMUs
    RFQ+MEBT: FBCM, WSs, NPMs, LBM, EMUs, collimators

## Slide 10: NCL beam commissioning goals at each stage
Stage 1A: ISrc-MEBT
  The main focus is subsystems verifications:
    (Restart ISrc)
    Make RFQ work
    Establish Beam mode production (timing, choppers, and iris)
    Verify MPS
  Tuning is limited to low current and transverse plane in MEBT.
Stage 1B: ISrc-DTL1
  The main focus remains to be subsystems verifications:
    Make DTL1 work
    Verify all the subsystems up to DTL (?)
  Tuning is likely to be limited to low current due to the time limit.
Stage 2: ISrc-DTL4
  Verify all the subsystems up to DTL4.
  Identify the current limit up to DTL4.
  Stability test (?).

## Slide 11: NCL configurations for stages
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
RFQ
MEBT
DTL1
DTL2
DTL3
DTL4
DTL5
MEBT FC
DTL2 FC
Temp shield wall
DTL4 FC
Stage 1A/B
Stage 2
DTL2-4 not installed.
DTL2 FC is placed right after DTL1 with shielding.
Temporary shield wall at DTL5.
MEBT and DTL2 FCs are at their nominal locations.
DTL4 FC is placed in shielding.

## Slide 12: Beam modes and stops during NCL commissioning
Mode | I [mA] | T [µs] | f [Hz] | IT [µC]
Probe | 6 | 5 | 1 | 0.03
Fast commissioning | 6 | 5 | 14 | 0.03
RF test | 6 | 50 | 1 | 0.3
Stability test | 6 | 50 | 14 | 0.3
Slow commissioning | 62.5 | 5 | 1 | 0.3125
Fast tuning | 62.5 | 5 | 14 | 0.3125
Slow tuning | 62.5 | 50 | 1 | 3.125
Production | 62.5 | 2860 | 14 | 178.75
Stop | “Max” mode | IT [µC]
LEBT FC | Production* | 178.75*
MEBT FC | Slow tuning | 3.125
DTL1 FC* | Fast tuning? | 0.3125?
DTL2 FC | Fast tuning? | 0.3125?
DTL4 FC | Slow tuning | 3.125

## Slide 13: Steps for the upcoming stage

## Slide 14: ~10 weeks live plan in Jira
Verifications
MEBT tuning
LEBT FC
LEBT
collimator
MEBT FC

## Slide 15: Overview
This stage is about verifying all available subsystems.
  In remaining time, low current transverse tuning of MEBT is conducted.
  High current beam is tried only briefly or not tried at all, unless a profile or emittance diagnostics becomes available.
3 verifications steps:
  ISrc restart (beam to LEBT FC)
    Check known ISrc settings
    Test the iris
  RFQ injection preparation (beam to LEBT collimator)
    Verify the new LEBT chopper -> establish beam modes production
  RFQ transmission optimization with probe (beam to MEBT FC)
    Make the RFQ work
    Establish stable probe beam transport to the MEBT FC
Verifications of MPS and shielding are done iteratively at each step.

## Slide 16: Comments on the Jira plan
Things to do were listed and very rough estimations of durations were added.
  No float nor consideration on availability.
Details of each activity will be further developed.
  I need much more inputs from the subsystem owners on what to do in the control room.
  MPS verification could be especially complicated and require interdisciplinary collaboration.
  Activities of the low current (centroid) tuning should be “relatively” straightforward. The key is to prepare adequate tools.
The issue with the straight-line plan vs reality is less like for NCL, due to much less flexibility.
In addition to improvising tests, how do the Jira plan fit to the engineering handbook, i.e., thorough documentation?

## Slide 17: Steps 1 & 2 at a glance
Solenoid 1
(Steerer 1H)
(Steerer 1V)
Chopper
Collimator
Solenoid 2
(Steerer 2H)
(Steerer 2V)
Iris
FC
EMU (H)
EMU (V)
NPM (H)
NPM (V)
Dpl
Beam stop
EMU (V)
NPM (H)
NPM (V)
FC
ACCT
Source
Repeller
Repeller
N2 injection
HV
NPM (H)
NPM (V)
BCM
New timing (supercycle), MPS, and beam modes production must work at this stage.

## Slide 18: MEBT layout

## Slide 19: Step 3 at a glance
This is a convoluted step involving:
  Iterations among the RFQ voltage scan, MEBT steering, and LEBT solenoids adjustment
  Verifications of FC, BCMs, and BPMs.
  Verification of MPS.

## Slide 20: What we could do with just the probe beam and BPMs
RFQ output energy measurement
  Direct measurement with a pair with special electronics
Aperture (limit) scan
Response matrix measurement
  Quad gradient
  Quad cycling curve
  Steerer deflection and nonlinearity
    Note the sextupolar component is as strong as ~30% at the border or ROI.
  BPM linearity
Beam based alignment
Trajectory correction
  Local correction
    Especially at the chopper and its dump
  Global correction

## Slide 21: Summary and outlook

## Slide 22: Summary and outlook
The upcoming beam commissioning stage focuses on subsystems verifications with beam for the RFQ and MEBT.
  Limited time
  Limited components
  Homework left from the ISrc-LEBT commissioning
In addition to make the RFQ (first RF accelerating structure), major goals include establishing beam modes production and protection functions.
Tuning activities will be limited low current one for the upcoming stage. It is likely that the stage one after is also limited to low current most of time and proper high current tunings are done when we have up to DTL4.