## Slide 1: Status of Beam Instrumentation for IS, LEBT, RFQ and MEBT
PRESENTED BY Tom SHea

## Slide 2: Organization
>20 Partners and Collaborators
System Leads
Rafael Baron
Clement Derrez
Elena Donegani
Hooman Hassanzedagen
Irena Dolenc Kittelmann
Roxana Tarkeshian
Cyrille Thomas
Aarhus University
CEA Saclay, Paris
CERN, Geneva
Cockcroft Institute, Daresbury
DESY, Hamburg
Elettra – Sincrotrone Trieste
ESS Bilbao
INFN, Catania
INFN, Legnaro
Lund University
University of Oslo
DTU, Denmark
STFC, Daresbury
WUT, Warsaw
Lodz U. of Technology, Lodz
Chinese ADS
J-PARC, Japan
ORNL, USA
LANL, USA
IHEP, Russia
INR, Moscow
Högskola Väst, Trollhättan
Stony Brook U., New York
BNL, New York
Technical Team
All system leads contribute technical expertise
In addition:
Edvard Bergman
Thomas Grandsaert
Slava Grishin
Hinko Kocevar
Mehdi Mohammednezhad
Johan Norin
Kaj Rosengren
Henrique Silva
At ESS Lund, the team consists of staff, consultants, students, and matrixed staff
Lead system design and deployment
Cover all technical disciplines
Tom Shea

## Slide 3: Proton Beam Instrumentation (PBI)
Beam Accounting
Faraday Cup (FC)
Beam Current (BCM)
Fast Current Monitor (FBCM)
Neutron monitor (nBLM)
Doppler (DPL)
Collimator (Coll)
For the IS, LEBT, RFQ, and MEBT
Centroid Measurement
Position Monitor (BPM)
Fast Position Monitor (FBPM)
Distribution Measurement
Wire Scanner (WS)
Emittance (EMU)
Longitudinal bunch shape (LBM)
Non-invasive Profile, Fluorescence (FPM)

## Slide 4: LEBT
LEBT

## Slide 5: LEBT PBI in Diagnostic Tank
LEBT
Also, current and voltage measurement in the Ion Source

## Slide 6: LEBT PBI in Cone
LEBT

## Slide 7: RFQ and MEBT
LEBT

## Slide 8: RFQ and MEBT PBI
LEBT

## Slide 9: LEBT FC status
  #2 Delivered late: Dec-19 from Pantechnik
  Revised actuator system
  Installed MPS limit switches
TBD:
  Fiducialization, installation, alignment, leak check
  ICS/BD: collisions avoidance (2 EMUs, 1 FC, 1 Doppler)
FC2
FC1
Commissioning
tank

## Slide 10: Towards beam on the LEBT, MEBT FC ( … and beyond ...)
  Revised grounding of EtherCAT modules by ICS (motion group), to be prepared for 3 FCs in total
  New Front-end enclosure, including 5 * LEBT FC FE
  Faraday cup .opi to monitor 3 FCs (LEBT, MEBT, DTL2)
Verified w. beam in LEBT; devices being installed; EPICS integrated in lab

## Slide 11: BCM installation
Site installation of the BCM sensors nearly complete
The already-installed BCM electronics in the FEB90 supports 7 ACCT sensors (i.e. from ISRC down to DTL tank 2) + the platform high-voltage measurement
ACCT front end installation in FEB90
BCM Patch Panel and Patch Boxes are being installed in the BCM rack and in the tunnel
EMC tests on the BCM-FBIS interface
Verified w. beam in LEBT; toroids installed; EPICS integrated in lab

## Slide 12: BCM tests
BCM machine protection functions based on a single ACCT are now integrated
~us pulses can be successfully measured with the 1 MHz BCM B.W.
A spare BCM channel is being used for measuring the voltage of the ISRC HV platform
A model-based protection function is implemented in the BCM firmware

## Slide 13: BPM
Verified w. beam at IPHI; MEBT electrodes installed; EPICS integrated in lab
Beam tests at IPHI CEA-Saclay with the MEBT BPM
Intra pulse phase measurements
~5 minutes
3 MeV, 0.4 mA to 50 mA, proton beam, 352.2 MHz RF
5 m
BPM electronics rack:
Repair of MEBT BPM broken during transportation from Bilbao. Repair done at ESS - Lund.
MEBT BPM inside the quadrupoles
Primary functionality:
Position, phase and amplitude
Waveforms and Averages
Data on demand
Position and energy interlocks

## Slide 14: Fast BPM and fast BCM
The fast BCM (i.e. FCT) is integrated in the MEBT. N.B. After FC so used in DTL commissioning run
A fast oscilloscope (Received; EPICS integration in progress) will measure the fast BCM/BPM signals
The FCT has a measured B.W. of 635 MHz and can be used for measuring pulse rise/fall time downstream of the MEBT chopper.
Measured FCT specifications (by the Bilbao team)
BPM4
LNA
Switch
Long cables
BPM3
2 BPM’s are connected through the same cable path for absolute RFQ energy measurements in time domain (3 GHz bandwidth)

## Slide 15: MEBT Wire Scanners
Acquisition system:
  Elettra IK delivery.
  Vertically tested with beam at LINAC4: Horizontal and vertical profile plots above
  HW Received and Verified. MEBT Back Ends installed and Analog Front Ends RFI.
SW: waiting for delivery and verification.
Actuators: WS1 being repaired (bellow) at Proactive, installation planned in March.
Acquisition verified in beam at Linac 4; All equipment received; init. EPICS integrated
Deliver H & V beam transverse profile scan at constant speed and in step by step mode (in tuning modes and below)
Test at Bilbao
Test at CERN
Electronics in FEB90

## Slide 16: NPM. Fluorescence Profile Monitor
Verified w. beam in LEBT. Photon counting version under construction for profile measurements in MEBT
16
xc mx
yc , my
Optical axis
H+ + H2 -> H+ + H2* + g
H+
H2
g
g
g
FPM operation principle
FPM @ ESS LEBT
Transverse beam position measurement @ LEBT

## Slide 17: LEBT Emittance Measurement Unit (EMU Allison Scanner)
AS developed at CEA for ESS LEBT @ 75 keV
Measured emittance at LEBT, 2019
Verified w. beam in LEBT

## Slide 18: MEBT Emittance Measurement Unit (Slit and Grid)
Reception tests in Lund on-going
    In-house (ICS) firmware development for IFC1410 + (2x) ADC3117;
    New EPICS data acquisition module based on AreaDetector.
    Next step: develop the EMU IOC to automate the scanning procedure;
24 ch current inputs from grid
200 nA – 200 uA
2 MHz bandwidth
Fully differential outputs
To FMC
  Vertical Integration test at ESSBilbao (cross talks, offset and noise in some channels observed that may be perturbing the emittance measurement.)
Equipment received, update nearing completion

## Slide 19: BSM
Requirements and Design
  Will be used to measure average bunch shape.
  Designed and fabricated at INR, Moscow, Russia.
  Same designed adopted for BSM2 (at the end of DTL).
  Improved symmetric λ-type RF deflector designed to fulfil the required 0.5o phase resolution for zero intensity beam (4ps @ 325.2MHz).
  Space charge effects estimated to increase the upper limit of phase resolution to 0.7o
Status
  Equipment received in April 2018.
  Device installed in the MEBT beam line in June 2019.
  Installation of electronics in the racks by INR team planed for May/June (after long haul cable installation, trip also combined with BSM2 pre-installation activities).
  The device comes with LabView based control system. Minimum steps to have the BSM ready for beam require timing and MPS integration.
BSM1 during bench tests at ESS in vacuum lab
BSM1 installation in MEBT
Symmetric RF deflector

## Slide 20: nBLM
Requirements and Design
  Particle discrimination
  µs time resolution, latency
  MPS function
  Fast (recoil) and slow (moderated) detectors
  Event-based acquisition
Status and Plans
  FPGA features: event building, data on demand (but restricted to 1 or 2 channels)
  Infrastructure for gas being installed
  System awaits MPS hardware, EPICS software
  Test in upcoming commissioning run to maintain contractual agreements and assure readiness for operations
Verified at Linac 4, equipment received
Neutrons indicating beam pulse (200μs and 150μs)
Gammas indicating
RF pulse (880μs)
Test at LINAC4 in Nov. - Dec. 2019
Fast nBLM at DTL1-2 intertank region at LINAC4

## Slide 21: Global functions
Intent: Deploy these initial versions for next commissioning
Remote system management
  IPMI management function integrated with EPICS
  Alarms, archiving of health data
Data on Demand (aka Synchronous Data Service)
  FPGA support for buffered, triggered data acquisition
  Software support with Area Detector
Low-latency multi-gigabit link
  Demonstrated for diferential current

## Slide 22: Acceptance to installation to commissioning
EAM Labelling
PBI lab Acceptance
Ready for Installation
Transport to G01/G02 & Installation
Beam Commissioning
Verification without beam / Cold Check Out
Ready for beam commissioning
Arrival at ESS
Verification with WeTest, etc

## Slide 23: Verification and Data Management
System status
Natalia’s talk
Multi-year effort, multi-directorate effort - now dangerously close to ready
Meas01
SciCat
Embedded HDF viewer
Reformatting to ESS NeXus
System Verification Data
Data storage
Cataloguing
Data source
EAM
Asset management
ESS User
PBI / BP Expert
Expert User
QR Scanning tool
Notes: Test benches produce data from the lab and the tunnel, from single unit acceptance to system verification with beam.
Data is stored in hdf5 format in meas01, files definition can be found in https://confluence.esss.lu.se/display/PBITECH/Systems+status+and+data+files+definition
Beam Diagnostics folders in meas01 are automatically analysed and catalogued by SciCat
A custom field in EAM links assets to their data, visualized in SciCat.
- Lifecycle (not sure exactly what to call this…): a couple of slides: Slava, Clement and Johan provide overview of supply chain management, installation, EAM, verification, WeTest, data management, etc .... System engineering graphic is OK, but also include real example(s), real data.

## Slide 24: Schedule Comparison
2002
2003
2004
2005
2006
2
1
4
3
5
7
8
9
6
2019
2018
2017
Source/
LEBT
RFQ/MEBT/DTL1
DTL 2-4
DTL5
+ Spokes
+ Medium Beta
SNS
ESS
Source/LEBT at Catania
Elliptical
Deployment at scale: superconducting linac devices
DTL 1
MEBT
improve
improve
2020
2021
2022
In years past, the ESS plan appeared too aggressive.
In 2018, it looked achievable and similar to RHIC and SNS.
Now, the pace appears slow
To target
split

## Slide 25: Challenges and Mitigations
Challenges:
  ICS resource limitations
  Infrastructure readiness
  Delayed deliveries.
Mitigations:
  Prioritize through Program Forum
  focus on first proton functions
  Data-driven, lean documentation, “we must have the data” (C. Saltmarsh c. 1992)
  Self perform
Opportunity:
  Contribute more globally (ex. Chopper, RF systems, EMC, operator screens, accelerator commissioning, even neutron science)
1st Sprint
2nd sprint
~2 weeks
Many Team Boards
One Program Board (CAP)
P6 Plan (Milestones, Earned Value)
~2 months

## Slide 26: System Status
Activities prioritized in Accelerator Controls Program Forum
System | Required for SRR2a | Priority of other systems | Design status | Material ordered | HW received up to SRR2a | Integration in the lab | Deployed | Projected readiness For commissioning
BCM | Yes |  |  |  |  | On track | Partly deployed for LEBT | 
BPM | Yes |  |  |  |  | On track |  | 
FC | Yes |  |  |  | FE in construction | On track | Partly deployed for LEBT | 
WS |  | 1 |  |  | 1 WS unit being repaired | Partially tested Next in priority |  | 
EMU |  | 2 | Rework ongoing | Rework ongoing | Additional cable needed |  | Partly deployed for LEBT | 
FBPM |  | 3 |  |  |  |  |  | 
LBM |  | 3 |  |  |  |  |  | 
nBLM |  | 3 |  |  |  |  |  | 
ICBLM |  | 3 |  |  | N/A |  |  | 
DPL |  | 3 |  |  |  |  | Partly deployed for LEBT | 
NPM |  | 3 | uTCA/IPC, fiber, drawings, cables |  | MEBT optics needed |  | Partly deployed for LEBT | 
COLL |  | 3 | Signal part will be target aperture prototype |  |  |  |  | 

## Slide 27: FC, BCM, BPM nearing deployment
Verifying timing, archiving, operator screens, …