## Slide 1: ENRIITC Work Package 5
Presentation by EATRIS, Nigel Wagstaff
Kick-Off and First General Assembly Meeting
Tuesday 21 January 2020
Stazione Zoologica di Napoli (SZN)
Naples, Italy

## Slide 2: ENRIITC Work Package 5 Objectives
Communicate effectively to the wider community of stakeholders
Share best practices for effective industrial engagement among the European ILO/ICO community
Serve the broad community of public and private entities
Specific objectives:
Communicate and disseminate project results taking account of the specific needs of target groups
Encourage bottom-up and top-down engagement among stakeholders
Ensure high visibility by amalgamating the social media channels of all partners and teaming up with existing initiatives and projects.

## Slide 3: ENRIITC Work Package 5 Task 5.1: Communication
EATRIS, ESS, WPT, IUC Syd, CDTI, NWO, SZN, EMSO, ESRF, CLARIN, DTI
Create the ENRIITC website and social media tools (Twitter, LinkedIn, YouTube)
Equip the website and social media tools and encourage their use to support the stakeholders in sharing experience and best practice and to be a repository for useful resources
Create high visibility by copying and dovetailing with other innovation activities and existing large-scale projects
Write the Communication Plan to cover all of the above and provide the road map forward

## Slide 4: ENRIITC Work Package 5 Task 5.1: Communication
WORK PLAN
Set up social media. IN PROGRESS
Confer and exchange technical details for the web site. IN PROGRESS, CONSTRUCTION OF THE WEB SITE PLANNED FOR FEBRUARY
Draft operating procedures and guidelines for web site and social media use. AIMING FOR M3
Start to populate the various media starting with already existing material and encouraging the stakeholder communities to make contributions. ONGOING
Consolidate into the Communications Plan. M4

## Slide 5: ENRIITC Work Package 5 Task 5.2: Dissemination
EATRIS, WPT, SZN, CDTI, IUC Syd, NWO, ESS, EMSO, ESRF, CLARIN, DTI
Disseminate project outputs including guidelines, resources,policies, training/webinar material, case studies to ensure they are both well advertised and easily accessible to all communities
Integrate with outputs from other work packages and activities
Present results at international fora such as ESOF 2022, ESFRI, EFPIA, ICRI2020, ERIC Forum and other networks and associations

## Slide 6: ENRIITC Work Package 5 Task 5.2: Dissemination
WORK PLAN
Advertise through various vehicles the opportunities arising from web site and social media
Reach out to promote forthcoming events and advertise upcoming webinars and workshops
Link to other sites/communities
Monitor use of the web site and social media, including downloadables, templates etc.
Presentation/road show to promote
Start to plan for dissemination through international fora

## Slide 7: Work Package 5 Milestones and Deliverables
Designation | Product | Due Date
D5.1 | Website launched | M2
MS01 | Creation of Twitter and LinkedIn group | M3
MS02 | Creation of YouTube channel | M3
MS04 | Communication plan | M4
D5.2 | Informational booklet of case studies and advocacy paper | M33

## Slide 8
Rosan Vegter
Education
Nigel Wagstaff
Innovation Support
Anton Ussi
Work Package Leader
Chris Tieken
Business Development
Anne-Charlotte Fauvel
Policy/Advocacy
Spyros Goudelis
Communication
EATRIS Staff Involved in ENRIITC Work Package 5

## Slide 9: EATRIS INVOLVEMENT IN WORK PACKAGES
Work Package | Subject | EATRIS personmonths
WP2 | Mapping of research infrastructure-industry collaboration | 2
WP3 | Strategies for innovation, training and outreach | 1
WP4 | Awareness and impact of research infrastructure-industry engagement | 3
WP5 | Communication, dissemination and exploitation | 6.5

## Slide 10: Thank you!