## Slide 1
Conventional Facilities
Jan Molander
Design Manager Conventional Facilities
www.europeanspallationsource.se
December 10, 2013

## Slide 2: Scope

## Slide 3: Organization
Staff Plan
CF | Employees | Consultants
2013 Q4 | 17 | 8
2014 Q1 | 22 | 8
2014 Q2 | 24 | 8
2014 Q3 | 26 | 9
2014 Q4 | 28 | 9

## Slide 4
2013
2014
2015
2016
2017
2018
2019
Conventional Facilities - Schedule
 | 2011 | 2012 | 2013 | 2014
Building Program |  |  |  | 
Architectural Competition |  |  |  | 
Feasibility Study |  |  |  | 
Baselining/ Scrubbing |  |  |  | 
Conceptual Design |  |  |  | 
Detailed Design |  |  |  | 
Procurement Contractor |  |  |  | 
Construction Start |  |  |  | 

## Slide 5
2013
2014
2015
2016
2017
2018
2019
DETAILED DESIGN
Conventional Facilities - Detailed Schedule
AUX. BLDGS
ACCELERATOR BLDG
TARGET BLDG + EXP HALLS 1,2
EXP HALL 3 + GUIDE HALLS
AUX. BLDGS
MAIN UTIL.(GROUND)
EARTH WORKS
MASTERPLAN GENERAL ARCH.
Design Phases
Construction Phase
CONTRACT SIGNED
START OF CONSTRUCTION
CUB OPERATIONAL
EARLY ACCESS COLD BOX & COMPRESSOR BLDG
EARLY ACCESS KLYSTRON GALLERY
PART 1 FINAL INSPECTION
FULL ACCESS ACCELERATOR
EARLY ACCESS EXP HALL 1
EARLY ACCESS EXP HALL 2
EARLY ACCESS EXP HALL 3
FULL ACCESS EXP. HALL 1 & 2
FULL ACCESS EXP. HALL 3
FULL ACCESS TARGET BLDG
FULL INSPECTION
PRELIMINARY DESIGN

## Slide 6: Top Risks Conventional Facilities

## Slide 7: Status
Challenges / Risks
Preliminary Design / Detailed Design
Procurement Civil Works
Scope Office & Labs
Requirements from Stakeholders
Challenges to Procurement
Start-up of Construction / Collaboration
Keep Scope within Budget

## Slide 8
The architecture of ESS
Architectural design competition Five architect consortia was preselected in an international architect competition and competed to design the ESS exterior. In February 2013 the winner was announced by the ESS jury: Henning Larsen Architects was selected to develop the final architectural design together with the ESS team.

## Slide 9: Architectural Concepts

## Slide 10: Architectural Concepts

## Slide 11: Architectural Concepts

## Slide 12
Conventional facilities | Masterplan Baseline
Security 2013-10-25

## Slide 13
Conventional facilities | Masterplan Baseline
Vehicle access 2013-10-25

## Slide 14
Conventional facilities | Masterplan Baseline
Pedestrian / bike access 2013-10-25

## Slide 15: Design Phases
The development of all required documents and data for the Project is divided into 3 stages.
Feasibility Study
Development of concepts and viable options taking into account stakeholder needs, time and budget constraints. Resulted in a CF Baseline for Accelerator, Target & Experimental Halls in August 2013.
Preliminary Design An Assessment of the Feasibility Study and alternative part solutions resulting in a main proposal for fulfillment of the project goals.
Detailed Design
The Detailed Design encompasses and implements the Preliminary Design decisions. All drawings and documents necessary for construction will be reviewed and collected in appropriate sub-projects.

## Slide 16: Master Plan

## Slide 17: Accelerator Buildings without berm

## Slide 18: Section through Tunnel

## Slide 19: Coldbox Hall and Test Facilities

## Slide 20: Gallery and Tunnel Colored volumes represent the machine

## Slide 21: Section through A2T

## Slide 22: Façade Concept: Gallery