## Slide 2: Sample Environment Systems for First Science – Temperature and Fields
Prioritised sample environment systems to be used on instruments #1-8
PRESENTED BY Alex Holmes

## Slide 3: Agenda
1 Overview
2 Individual systems
3 E03 workshop planning

## Slide 4
Overview
1

## Slide 5: Sample Environment Systems for Diffraction
Section | System | Details | partners | Status
TEFI (pool) | Magnet | Assymetric 8T | LLB | TA approved, CTV passed
TEFI (pool) | Dilution, He3 | Matched to magnet | LLB | TA approved
TEFI (instr) | Wet Cryostat | Specific | LLB | Not yet started
MAGiC
Section | System | Details | partners | Status
TEFI (Instr) | Cryofurnace | 20 pos. Inst specific | LLB | CTV passed
TEFI (Pool) | Wet Cryofurnace | Top loading | LLB | Generic OC integration started
TEFI (pool) | HT vac furnace | ILL style top loading | LLB | Not started
TEFI (pool) | Magnet | Assymetric 8T + ULT | LLB | TA approved, CTV passed
DREAM

## Slide 6: Sample Environment Systems for Spectroscopy
Section | System | Details | partners | Status
TEFI (pool) | 15T Magnet | Ex HZB VM1B +Dil. | ESS/HZB | Ready for delivery (delayed by COVID19)
TEFI (Instr) | Wet Cryostat | Specific OC 100mm | BIFROST/DTU | Specs being defined
BIFROST
Section | System | Details | partners | Status
TEFI (pool) | 6.5 T Magnet | Ex-HZB VM-2 +Dil | ESS/HZB | Verbal agreement
TEFI (Instr) | Cryofurnace changer | Inst specific 6 pos. | LLB | To be started
TEFI (pool) | Wet Cryostat | Standard OC | LLB | To be started
CSPEC
N.b. High field magnet desired for CSPEC but not prioritised

## Slide 7: Sample Environment Systems for LSS
Section | System | Details | partners | Status
TEFI (pool) | Warm bore magnet | 2T cryomagnet | LLB | TA agreed
TEFI (pool) | Electromagnet | 1T | ESS | Discussion with MCA for shared magnet
LOKI
Section | System | Details | partners | Status
TEFI (pool) | Warm bore | 2T magnet | LLB | TA agreed
TEFI (inst) | Flow cryostat | Instrument specific | PSI | Not yet started
ESTIA
N.b. High field magnet with sapphire windows desired for ESTIA/SKADI but not prioritised

## Slide 8
TEFI Individual systems
2

## Slide 9: 8T Magnet for MAGiC, DREAM, HEIMDAL
1. System Overview and Deliverables
+15°/-35° vertical field wet cryomagnet
2. Schedule, Milestones and Reviews
Call for tender review (CTV) complete.
Waiting in procurement queue at LLB, likely publication October
⇒ delivery late 2022/early 2023
3. Integration, Safety, Verification, Validation
Requires mechanical integration with kin. mounts, magnetic field safely checks & policy
Providing 8T, 1.6K (or 50/300 mK with ULT inserts)
 | Q1/20 | Q2/20 | Q3/20 | Q4/20 | Q1/21 | Q2/21 | Q3/21 | Q4/21 | Q1/22 | Q2/22 | Q3/22 | Q4/22 | Q1/23
8T Magnet |  |  |  |  |  |  |  |  |  |  |  |  | 
Procurement
Design
Manufacture
Acceptance/Integration
4. Achievements and Challenges
Completing CTV!
Finite procurement bandwidth.
Notes: A

## Slide 10: New ULT systems for ‘8T magnet + OC’
1. System Overview and Deliverables
  2 dilution systems
  1 3He sorption
Matched to 8T magnet, usable in wet cryo.
2. Schedule, Milestones and Reviews
Have model tender docs from ANSTO CTV to be complete ASAP.
3. Integration, Safety, Verification, Validation
Must be compatible with other systems.
Providing ‘parameter range’ 50/300mK – 300K
 | Q1/20 | Q2/20 | Q3/20 | Q4/20 | Q1/21 | Q2/21 | Q3/21 | Q4/21 | Q1/22 | Q2/22 | Q3/22 | Q4/22 | Q1/23
ULT Systems |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Achievements and Challenges
Technician Richard Ammer has participated in a number of dilution cooldowns.
Notes: B

## Slide 11: '15T magnet’ for ‘BIFROST’
1. System Overview and Deliverables
  15 T magnet ‘VM1B’ formerly from HZB
  Agreement to get further ULT inserts
2. Schedule, Milestones and Reviews
  Due for delivery as COVID19 lockdown started
3. Integration, Safety, Verification, Validation
  Requires mechanical integration onto L1 kinematic mounts. Updating auxiliary eqt.
4. Achievements and Challenges
  Technician RA attended final cooldown at HZB
  Delayed delivery due to COVID19 situation.
Second hand magnet
Notes: F

## Slide 12: Warm bore for ESTIA, LOKI
1. System Overview and Deliverables
  Based on TOFTOF HTS110 magnet with minor modifications.
2. Schedule, Milestones and Reviews
  CTV to be carried out shortly
3. Integration, Safety, Verification, Validation
  Mounting agreed with LOKI and ESTIA
4. Achievements and Challenges
  Procurement logjams, potential COVID19 supply issues.
Providing 2.5T magnetic field FR in-kind via LLB
 | Q1/20 | Q2/20 | Q3/20 | Q4/20 | Q1/21 | Q2/21 | Q3/21 | Q4/21 | Q1/22 | Q2/22 | Q3/22 | Q4/22 | Q1/23
2.5 T Warm bore |  |  |  |  |  |  |  |  |  |  |  |  | 
Procurement
Design
Manufacture
Acceptance/Integration
Notes: J

## Slide 13: Flow cryostat for ESTIA
1. System Overview and Deliverables
  Helium flow cryostat
2. Schedule, Milestones and Reviews
  Part of Instrument scheduling
3. Integration, Safety, Verification, Validation
  Integrated with hexapod, used with 2.5T warm bore magnet
Instrument specific flow cryostat 5-300K
Example from
https://ilt.kharkov.ua/bvi/technology/oc/optical%20cryostat.htm
Notes: L

## Slide 14: 6.5T Cryomagnet for CSPEC, TREX
1. System Overview and Deliverables
  Cryomagnet and compatible dilution system
2. Schedule, Milestones and Reviews
  Informal agreement with HZB, to be finalised
  Read for first science on CSPEC
3. Integration, Safety, Verification, Validation
  Needs top loading adaptor, possibly new tail.
4. Achievements and Challenges
  Delivery delayed by COVID19
Second hand assymetric cryomagnet from HZB
Notes: H

## Slide 15: '20 position Cryofurnace’ for ‘DREAM’
1. System Overview and Deliverables
  Instrument specific multi position dry cryofurnace
2. Schedule, Milestones and Reviews
  Part of DREAM instrument schedule
  CTV complete
3. Integration, Safety, Verification, Validation
  Fits with top loading
4. Achievements and Challenges
  CTV passed
  Very ambitions specs - need a plan B
Providing 20 samples, 4 K-800 K at measurement position, sample storage at 90 K
Notes: D

## Slide 16: ‘Wet cryostat’ for ‘MAGiC’
1. System Overview and Deliverables
  Orange-type or Variox wet cryostat system
2. Schedule, Milestones and Reviews
  Not yet fixed
3. Integration, Safety, Verification, Validation
  Mechanical integration with XYZ coils and kinematic mount
4. Achievements and Challenges
  JCNS has Variox available for donation.
Instrument specific cryostat providing 1.5K-300K
Notes: C

## Slide 17: ‘Wet cryofurnace’ for ‘DREAM’
1. System Overview and Deliverables
  Orange-type wet cryofurnace
2. Schedule, Milestones and Reviews
To be fixed – ready by first science milestone
3. Integration, Safety, Verification, Validation
  Top loading
  Needs special tail materials.
4. Achievements and Challenges
  Tail materials may not be compatible with spectroscopy. V/TiZr vs Al
Pool cryostat providing 1.5K-600K
Notes: E

## Slide 18: Vacuum furnace for DREAM
1. System Overview and Deliverables
  ILL type vacuum furnace
2. Schedule, Milestones and Reviews
  To be fixed – ready by first science milestone
3. Integration, Safety, Verification, Validation
  Needs special tail materials.
4. Achievements and Challenges
  Furnace expertise needs building
Pool HT vacuum furnace RT - 1300 K
Notes: E

## Slide 19: ‘Wet cryostat’ for ‘instruments BIFROST’
1. System Overview and Deliverables
  Wet orange type-cryostat 100mm VTI
2. Schedule, Milestones and Reviews
  Follows instrument schedule. Specifications under discussion now.
3. Integration, Safety, Verification, Validation
  Integration on to L2 floor mounts
4. Achievements and Challenges
  Agreeing on main
NB: similar slides for all prioritised systems
Instrument specific cryostat 1.5 K - 300 K
Notes: C

## Slide 20: 1T Electromagnet for LOKI
1. System Overview and Deliverables
  Low field electromagnet, to be procured by Motion Control and Automation Group, with power supply
2. Schedule, Milestones and Reviews
  Procurement planned this year for testing of motor components in stray field.
3. Integration, Safety, Verification, Validation
  Controls, supply mechanical integration.
4. Achievements and Challenges
  Coordinate with MCAG
1T electromagnet
Notes: K

## Slide 21: ‘Cryofurnace changer’ for ‘CSPEC’
1. System Overview and Deliverables
  6 position cryofurnance changer
  Detailed specifications to be determined
2. Schedule, Milestones and Reviews
  To be finalised
Providing ‘parameter range’ 1.5-600K

## Slide 22
E03 sample environment workshop planning
-
3

## Slide 23
5m
Sample Environment Equipment prep area
Fume hoods with water, power, gas.
E03 100
TEFI-cryomag
TEFI-Furnace
Fume hood
Alignment
TEFI-cryo
TEFI-Furnace
TEFI-cryo
Storg (n-mag)
Storage
Fume hood
walkway
Crane
Crane
Storage/prep
Storage
Storage
benches
Storage
Gas bottles
Hot works/

## Slide 24: The end (of the beginning)