## Slide 1: Short Review of ESS Project Status
Workshop – Quality for In-Kind@ CEA/IPNO
Mauro Zambelli
European Spallation Source ERIC
Orly, 27th January 2020

## Slide 2: Status of the ESS Project Construction, towards Operations & First Science

## Slide 3: ESS is a “true” green-field Project

## Slide 4: Journey to deliver the world’s leading facility for research using neutrons
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2019
Start of Initial Operations Phase
2023
ESS Starts
User Program
2019
TODAY
Construction project is 62% complete

## Slide 5: A reminder of the ESS Critical Path
Accelerator + ICS
CF + Target + NSS (Bunker+TBL) + ICS
2018
2019
2020
2021
2022
2023
2024
2025
Beam on Dump
(570 MeV)
Accelerator Schedule Float
Accel RBOT
Warm LINAC Commissioning Steps
BOT
SOUP
EOC
Access for Monolith Installation
Target RBOT
Bunker & TBL RBOT
NSS Instruments + ICS
Start beam commissioning for 1st Instruments
15th Instrument Complete (Ready for hot commissioning)
Instrument Hall Access for Start of Installation
Hi -Beta Install
0.8 GeV Capability Installed
BOT - Beam on Target
RBOT - Ready for Beam on Target
FS - First Science
SOUP - Start of User Programme
EOC - End of Construction project
FS
ESS is focused on delivering First Science with three instruments by the end of 2023
Schedule date (no float) is March 2023

## Slide 6: ESS Highlights
Conventional facilities
Civil construction remains on or ahead of schedule
Steelwork erection for target building high-bay and experimental halls now underway

## Slide 7: ESS highlights
Accelerator installation proceeding
  Ion source and LEBT commissioned
  MEBT installed
  DTL received and being integrated
  RFQ on site
Cryo-test stand permit received
Accelerator

## Slide 8: ESS highlights
Target installation proceeding
  High bay steelwork
  Monolith shielding
Major components in manufacturing
Monolith vessel on track for delivery by end 2019
Target

## Slide 9: ESS highlights
Bunker is in manufacturing
Instruments design phase complete – moving into construction
“First 3” instruments endorsed by IKRC
Common shielding, chopper and beam monitor designs developed to save time and money
Schedule mitigations implemented to reduce impact of port blocks on first science by modifying bunker installation sequence
Instruments

## Slide 10: Inauguration of the E01 Experimetal Hall
September 9th, 2019

## Slide 11: First eight instruments planned to be ready for commissioning by end of 2022
ESTIA
LOKI
DREAM
ODIN
BEER
C-SPEC
BIFROST
MAGIC
Aug 2019 Access
Jan 2021 Access
Jun 2021 Access
Preferred first
three instruments
May 2021 Access
Diffractometers | Spectrometers | Reflectometers | SANS | Engineering & Imaging
DREAM | BIFROST | ESTIA | LOKI | BEER
MAGIC | C-SPEC |  |  | ODIN
Notes: There is risk with this plan and we need to revisit it
2 of the 3 choices for first science has the last area access

## Slide 12: The IK Environment @ ESS

## Slide 13: New challenges for IK management
  IK Management @ ESS is rapidly moving from the Contractual phase to the Implementation phase, starting to look forward to the Operation phase
    This requires a progressively different approach to the relationship both with the IK Partners and with the relevant Functions inside ESS
    Complex issues are now coming into play: logistics, VAT on delivery and installation, quality documentation, CE marking

## Slide 14: ESS – IK Provider relationship
  The operative relationship between ESS and the IK Provider is essentially (and usefully) focused on the scientific/technical channel (WP Leader)
    However, IK is a far more complex process, which requires a “multi-channel” communication and comprehensive interaction between ESS and the IK Partners / IK Provider

## Slide 15: Multi-channel communication
  IK Contribution Agreements
  Technical Annexes and TA amendments
  Relationship with Ministries and Funding Agencies
  Administrative issues (i.e. Call-Offs payments)
  VAT issues (particularly on delivery and installation)
  Technical specifications
  Project schedule
  Logistics (transport, delivery)
  Quality Control and quality documentation
  CE marking / DOI
  Installation and commissioning

## Slide 16: ESS – IK Provider relationship
  The IK Partners and the relevant sub-contractors must be supported by ESS in order to accomplish their contracts on spec, on time and on budget
  ESS must be assured by the IK Partner about its capability to deliver equipment and services according to the specifications and to the schedule agreed

## Slide 17: ESS – Organizational issues
  In order to increase the effectiveness of the co-operation between ESS and the IK Partners, improvement in the internal organization for IK management are currently under way
  In particular the two following concepts have been introduced:
    IN-KIND FRAMEWORK MANAGEMENT
    IN-KIND SUPPLY CHAIN MANAGEMENT

## Slide 18: IK Framework vs. IK Supply Chain
ESS Project
IK
Partner
European Spallation
Source ERIC
ESS Requirements
Partner’s Issues
IKFR (Support)
IKSC (Control)

## Slide 19: ESS – Organizational issues
  IN-KIND FRAMEWORK MANAGEMENT
    General and organizational issues: contracts, amendments, legal issues, liabilities, warranties, VAT, quality, contacts with Funding Agencies, Ministries, National Bodies
    Responsibility: Strategy Directorate
  IN-KIND SUPPLY CHAIN MANAGEMENT
    Schedule and budget control
    Responsibility: Project Directorate

## Slide 20: Top Management Structure @ ESS

## Slide 21: ESS In-Kind System
In-Kind FRAMEWORK
Management
In-Kind SUPPLY CHAIN
Management
In-Kind TECHNICAL Management
ESS Work Package Leader
In-Kind
Partner
IK
ACCSYS
IK
ICS
IK
NSS
IK
TARGET
BrightnESS2 WP3
FC
FC
FC
FC
FC

## Slide 22: In-Kind Contributions @ ESS Results, Facts & Figures

## Slide 23: IK Status at present
Key Points
2015
2017
308 M€ (106 TAs) approved by Council (including 29 accredited).
145 M € (41 TAs) endorsed by IKRC.
Almost all IK for Accelerator, ICS and Target is approved by Council or endorsed by IKRC.
To date
62 M€ to be agreed for NSS – mostly Instruments (Sample Environment + Neutron Technologies)
4 remaining IKCAs, HGZ (DE), ESS Bilbao (ES), CNR (IT), STFC (UK).
Following 15th Council approval of IK Principles, next step is to establish Procedures for IK Contributions during Operations
Ongoing
550 M€ estimated IK.
Additional c. 28 M€ in collaborations (SE/DK) and c. 14 M€ in direct contracts placed with German Institutes.
End of ESS Construction

## Slide 24: Status of Specific IKCAs
Institute | Country | Status | Forecast | Estimated Total IK Value
FZJ | Germany | Jülich Contribution Agreement approved at Council #14 in Dec 2018. Jointly signed agreements with TUM and FZJ. Agreement with HZG is finalized but awaiting agreement on the BEER Instrument TA. | Qtr 2 2020 | 49.8 M€
TUM |  |  |  | 15.3 M€
HZG |  |  |  | 8.0 M€
CNR | Italy | Tri-lateral agreement with INFN and CNR is finalized, pending signature process. Tri-party structure selected for VAT reasons. Agreement ready for presentation at IKRC. | Qtr 1 2020 | 14.9 M€
ESS Bilbao | Spain | ESS Bilbao reviewing IKCA. Involvement of the State Attorney. | -Procure-ments not affected | 45.0 M€
STFC | UK | IKCA with UKRI finalized and agreed. Expected to be signed shortly. Agreement ready for presentation at IKCA. | -Procure-ments not affected | 111.8 M€

## Slide 25: IK Status
Status of Agreements

## Slide 26
Yearly progress of In-Kind
Chart: 
| End of 2014 | End of 2015 | End of 2016 | End of 2017 | End of 2018 | Sep 2018 | End of 2019 | End of 2020 (estimate)
Agreed / Endorsed | 0.19 | 128.5 | 254.7 | 319 | 334.1 | 417 | 453 | 535
Planned | 272.59 | 207.15 | 258.49 | 215.34 | 210 | 115 | 64.14 | 10
Potential | 335.78 | 313.19 | 110.54 | 25 | 10 | 8 | 14.81 | 0
Collaborations | 9.4 | 16.7 | 17.09 | 22 | 19.8 | 28 | 28.4 | 28.4
Direct Contracts | 0 | 5.7 | 15.7 | 20 | 21.36 | 13 | 14.23 | 15

## Slide 27: In-Kind Contributions @ ESS Conclusions

## Slide 28: Conclusions
New management for and special focus to IK
Alignment of IK to implementation
IK during Operations being established
Specific issues to be solved (VAT, etc.)

## Slide 29: The commitment
ESS In-Kind System
is fully committed to achieve
FIRST SCIENCE in 2023

## Slide 30: Thank you!
Mauro.Zambelli@esss.se