| IKON19 Control hutches Report for IKON19 |  |
| --- | --- |
| Author(s): Gabor Laszlo | Date/time of session: [Monday, 29 September 2020, 14.30-14.45] |

# Introduction

NSS is going to procure four hutches for instrument teams: NMX, LOKI/FREIA, ODIN and TBL

# Status of the Procurements

## NMX

We have published the NMX tender at the beginning of summer without success.

Status: exploring potential suppliers

## LOKI/FREIA

We have published the LOKI/FREIA tender during the summer without success.

Status: exploring potential suppliers

## ODIN

ESS Procurement has decided not to publish the tender before we find the reasons of the failed procurements and agree on the way forward.

## TBL

The procurement has been postponed until we have an agreed strategy.

## Lessons learnt and potential strategies

- The projects are relatively small and complex the suppliers don´t like these kind of challenges.

- Many companies reported that the scope of the hutch tender is not in their profile.

- Some of them reported that the timing was not right and they did not have the resources to answer.

- Typically, we define requirements instead of specifying solutions, that is not what these suppliers used to. It gives the impression that we don´t know exactly what we want. We have the following options:

- Joint procurements, to create a larger project to be able to invite larger companies.

Disadvantage: Larger companies has larger overheads. In some cases, the price can be significantly higher

- Choose specific solutions and minimize the number of general requirements.

Disadvantage: limits the range of suppliers

- Break down the projects to sub-systems. Expand the scope of the common utilities project to fit out the hutches and find suppliers for the hutch structures separately.

Disadvantage: additional administrative load and resource allocation for ESS.

We are still negotiating and discussing different options with the suppliers.

- Skanska Direkt

- Lindner AG

- DC-Supply

- Jacobs CMS UK Field Solutions

- MOE

- Constructor Sverige AB

- https://www.indus.se/

- https://www.moelven.com/se/

- https://www.pcsmodulsystem.se/

- Lindner