## Slide 1: Build on Best Practice Video Workshop Best practices and lessons learnt
Vincent HENNION, CEA for Gallia Hub
27.08.2020, Remote
This project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No 823867

## Slide 2: Background
CEA-Irfu
  Our institute is in charge of several contributions in the ACCSYST and one for ICS (expertise skills)
  In the frame of B2, representation of the whole contribution inside Gallia Hub (including CNRS, and LLB) is tricky (resources, contacts, different sites…)

## Slide 3: Best Practices already in place on which to build further developments (B-1/B-2)
Technical aspect: organization of the project team
  To be developed
Procurement aspect: processes and team organization
  Contract managers more dedicated to ESS
  Generic contract chapters
  Dedicated meetings and tools for monitoring
QA and risks aspect: processes and team organization
  To be developed

## Slide 4: BP#1 – Technical aspects
Engineering
  Systems engineering (interfaces management and technical reviews)
  Lessons learnt with demonstrators
  Meetings, reviews and boards
Installation and integration
  Processes and procedures + assembly tools
  Technological transfer to the subcontractor (B&S)
Verification/validation/qualification process
  Requirement management (DOORS before CHESS)
  Tests campaigns (proto cavities, cryomodule demonstrators…)
  Data and documentation management on CHESS (workflow, reference design configuration…)

## Slide 5: BP#2 – QA and risks management aspects
Internal organization at CEA-Irfu
  Lessons learnt from E-XFEL
  Contract managers in close contact with QA/QC engineers
  Dedicated tool for configuration management and documentation management system
Risks management
  table for each TAs, discussed with ESS
  Tasks and organization for CE Marking process
  Workshop/meetings about risks management
Corrective actions and organisation when crisis
  Adjustment in organization because of COVID-19
  Major technical issues

## Slide 6: Main risks identified in IK Management
ID | Event | Cause | Impact | C - Cost S – Schedule | Prob. 1-5 | Mitigation Measures
 | Restriction for travelling | Covid-19 crisis | Commissioning activities on site without support | C: S: 6 | 5 | Documented procedures in order to ease ESS to perform
 | Restriction for travelling | Covid-19 crisis | Complexification of the collaborative work inside instruments project teams | C: S: 3 | 4 | Similar to those to implement between ESS and partners
 | Quality control/traceability in subcontractors | Lack of resources or loss of skills (economic crisis) | Technical issues in integration or unreached performances | C: S: 3 | 2-3 | Regular inspection before reception
 |  |  |  | C: S: |  | 
 |  |  |  | C: S: |  | 
Probability: 5 = most severe; Cost: Estimated potential cost in M€ if not mitigated; Schedule: Estimated delay of activity in months if not mitigated |  |  |  |  |  | 
Comments: |  |  |  |  |  | 

## Slide 7: Possible new Best Practices to develop in B-2
Based on the content of the previous BP WS, what has been applied, what has not and why?
For ESS, to re-think and adapt the work organization (comparison with agile architectures) in the different phases of the construction, due to this new economic context, in particular with travel restrictions; what about ITER or CERN collaborative contributions?

## Slide 8: Thank you!
Vincent HENNION, CEA
Vincent.hennion@cea.fr
This project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No 823867

## Slide 9: Achievements & Lessons Learnt
Describe significative achievements and/or lessons learnt in your Institution/Hub/Country obtained in the frame of B-1 and/or B-2, or in any case related to the IK contributions to ESS
  This information will be precious for the B-2 Mid Term Review
  Also, please be aware that Deliverable 3.2 “Handbook of lessons learnt from IKC on ESS” will be due by end June 2021