## Slide 1: i-CDR committee on welds of port tubes on monolith vessel
Peter rådahl, ESS Chief engineer, chair of the i-CDR
DR. Bertrand Nicquevert, advisor to the ESS technical director, secretary of the i-CDR
On behalf of the whole committee
Draft recommendations

## Slide 2: Introductory remarks
The committee thanks the speakers for the presentations and responsive answers to the open Q&A session.
This has been a virtual meeting. The lack of face-to-face opportunities has prevented the committee to have further detailed discussions with the presenters and attendees.

## Slide 3: Charge to the committee
“The Review Committee is asked to undertake the following tasks:
1. REVIEW: The Review Committee is asked to scrutinize and assess the deliverables listed in Appendix 1, sent to the committee and presented at the CDR
2. ANSWERS: The Review Committee is asked to answer the questions listed in Appendix 3.
3. RECOMMEND: The Review Committee is asked to recommend to the ESS Technical Director if the welds of port tubes to MV meet all requirements with acceptable risk and within the cost and schedule constraints, and if the maturity of the design is appropriate to support proceeding with preparation of the full-scale execution, site acceptance test, and future operation. The recommendation should have one of the following forms:
- Endorsed, without qualifying comments or further actions.
- Endorsed, but with recommended actions.
- Not endorsed, but with recommended further actions and inputs, and with a proposal for a follow-up review.”
The review committee is today presenting some recommended actions and offers to organize a follow-up review within about one month, before formulating a recommendation to final endorsement by the Technical Director

## Slide 4: Scope of the work under review
In the framework of the agreement (TIK 4.5 revision 2) signed between ESS ERIC (Lund) and ESS Bilbao on December 11, 2017:
“The division of responsibilities and tasks for the installation of the Monolith Vessel (all components included) is the following: […]
ESS ERIC is responsible for the installation and placement of each part of the Monolith Vessel including the PBW port block, in its final location, meeting the alignment requirements needed for the final welding
ESS-Bilbao will be responsible for the final welding of each of the pieces of the Monolith Vessel and the in-situ welding test, including the Neutron beam port block welds.”

## Slide 5: Recommendations #1
Mechanical behaviour
Complete the thermo-mechanical calculations with the identified missing load cases (including combination of the loads, thermo-mechanical effect, buckling, influence of the restraining devices…)
Join to the documentation of the review the thermo-mechanical calculations report of the system “MV+PT” and assess that this was properly validated by an authorised body
Assess the representativity of the results of the tests on the mock-up
Clarify the relationship between the widening of the window and the probable restriction of its height

## Slide 6: Recommendations #2
Tolerance budget
  Consolidate the tolerance budget estimate
  Consider increasing the adjustability range of the inserts
  Ensure exchange of information on the position of port tubes between target and instruments
  Revise the sequence between target and instruments regarding the installation of the port tube and NBPI-NBOA
  Establish a fall-back solution in case the position is exceeding the limits
  To be developed further in the written report

## Slide 7: Recommendations #3a
Welding sequence: comment on sequence A proposed by ENSA
    The weld sequence is crucial for monitoring and minimize weld stresses and deformation. This applies for the separate welding of each port tube as well as for the setup of the welding of all port tubes
    Carry out a direct and on-time survey of structure during welding operations to check deformations in order to be agile and being able to react during the installation phase, and work on the full assembly in one go
    In order to enable a improved control and behaviour, consider a welding sequence (sequence B) that would not only sequence the tack weld, but also sequence the root pass and then go for a run-by-run sequence instead of a complete weld of each port.
      The need for some additional tooling shall be considered for this run-by-run sequence B
    A fall-back plan should be prepared, to be applied as a last resort, if after the first weld runs, the deformations appears to drift to unacceptable values.

## Slide 8: Recommendations #3b
On alternative sequence C of welding by sectors
      The review committee is not fully clear on the scope of the proposal, and not unanimous on the interest of this sequence; drawbacks and advantages should be well considered and balanced (is the possible added value worth the risk?)
      Is this sequence to be considered as a full scale test, to start?
      The risk is to get permanent deformation of the vessel that could not be compensated at a later stage. A limit of the allowable deformation measured with careful monitoring should be determined before further decision
      Responsibility needs to be clarified

## Slide 9: Recommendations #4
Welding activities
    The WPS should be properly developed
      Ranges of parameters should be more defined, and not depending on the welders’ personal choice
      A WPQR (Welding Process Qualification Record) needs to state the limits of the welding activities
    The WPQR for repair is required, and tested on the mock-up
    Consider getting a sufficient number of qualified welders
      Ensure a proper training of each welder
      The mock-up should be moved on site for refresher training, or training of additional welders (in particular due to sanitary restrictions)

## Slide 10: Recommendations #5
Welding control
  Consider radiographic test of the welds for all positions (not only top position) and all welders
  Aim at a % level that should be as high as possible
    Start from 100% level, and reduce according to real limitations, and also outcome of actual welds
    Even if 10% is a minimal legal requirement, ESS may consider to increase this level
  Ensure the availability of a validated weld book

## Slide 11: Recommendations #6
Global test
  Clarify acceptance criteria, responsibility and ownership for both pressure test and leak test
  Pressure testing
    Pressure test needs to quickly be organized, the company in charge should be involved in the definition of the test
    The pressure test shall be documented (to know what are the quality records required) (PED cat IV + AFS-2006-8). This may have an impact on the definition of the inspection plan and QC documents.
    This needs to involve a third party.