ILL - PaNOSC update
29-30 Nov 2021

---
WP2
Recruitment in september [done]
Need to adapt the 2017 Data Policy [todo 11/22]
  1. Meetings with the science representatives [todo]
  1. Meetings with Management board [todo]
Implement DMPs [todo 2022/2023]
  1. Will be included in the « users portal » refactoring project
  1. Next step : define the right tool [todo 04/22]

---
WP3
Implement search API [done]
More development is needed to implement the common search scoring [to be discussed]
Waiting for additional demands aligned with ILL needs.

---
WP4
Published VISA with an Open Source licence [done]
Develop a new graphical export system prototype[done]
Finalise the graphical prototype for production [todo 10/22]
Increase VISA interoperability with Proxmox support [in progress 07/22]
VISA support will be continued after PaNOSC. Waiting for PaNOSC partners needs/ideas for next versions. [Needs]

---
WP5
On track. Next srpint incoming.

---
WP6
Start data transfer with ISIS storage [done – in progress]
VISA documentation (installation/maintenance) [done]
VISA initial support for early adopters [done – in progress]
Support partners to deploy VISA locally [todo until 11/22]
Update keycloak for umbrellaID [todo 03/22]
Recruitment in september + internal both started in november.

---
WP7
Consolidate cost collection [in progress]
Missed several meetings [needs]
Following next demands [until 11/22]

---
WP8
Staff outside from IT – needs to be updated internally
Late on declaring ILL spending – Will be corrected soon

---
WP9
ESS VISA prestation [done]
Nomad-lab : prestation of VISA [done]
Collaboration on the VISA video presentation made by ESRF [done]
3 use cases to publish rapidly [todo 01/22 – late]
6 more use cases to publish [todo 11/22 – late]
Need for personnel backup – ILL management on it. [Needs]

---
Summary
Work needs to be done on VISA:
  1. Improve interoperability
  1. Improve graphical performances
  1. Support for RIs
Work on data policy, confidence of management support
Issue on communication part: personnel backup needed