## Slide 2: Updates on mechanical processing and high temperature
PRESENTED BY Caroline Curfs

## Slide 3: Mechanical processing
60 kN uniaxial stress rig
  Built by NPI, CZ
  Body can go up to 100 kN but new grips will be needed
  Tension and compression possible for round samples only
  Nearly ready to be sent but TA for transfer not signed (discussions on going about warranty)
  Kick- off after next IKRC in 10.22 for transfer to ESS in 2023
50 kN rotation/tortion stress rig
  Budget : 420 kEuros
  SREss grant with LU and MAU to refurbish or duplicate Robin’s rig including improvements– Project started – Quotation in progress
  Will include a DIC/DVC system
  Planned to be ready by end Q3/23
5-10 kN stress rig dedicated to soft matter
  Postponed : No ESS instrument showed interest
  Can be borrowed from MAX IV ?
Stress rigs

## Slide 4: Mechanical processing & high temperature
Furnaces
Furnaces adapted to stress rigs:
  Vacuum chamber with Joule heating system up to 1200 ℃
    Built by NPI, CZ – Will be sent with the stress rig
    TA nearly ready to be signed – discussions on going about warranty
    Kick-off planned after next IKRC in 10.22 and delivery in 23
  UHT furnace = mirror furnace
    External grant with Chalmers Uni, ISIS and ESS (2 years post-doc)
    Drawings ready by end 22/ beg. 23
    Prototype will be built and tested by ISIS
Furnaces
  Aarhus furnaces
    Induction and hot air blower/cryostream system
    Budget 90 kEuros + 90 kEuros
    Planned initially to be ready by 2023 BUT departure of post-doc
      Induction furnace : Swedish IK (UU) in collaboration with Aarhus
      Hot air blower/cryostream : project on hold – equipment will be purchased to be used independantly
  ILL type furnaces
    Budget 75 kEuros
    2 second-hand furnaces from LLB
    Refurbished by LLB with support from ESS technicians

## Slide 5: Mechanical processing
Thermo-mechanical testing
TA Instrument
Gleeble
  Discussion started but postponed to after 2027
  No SE budget planned : private – public partnership? Grant?
  Will need a dedicated person to run it
  Can be used without neutrons
Dilatometer
  Budget : 480 kEuros
  Commercial product with modifications
  Specifications to be defined before end of 22 : quenching needed?
  Dedicated person needed to run it
  Can be used without neutrons

## Slide 6: Mechanical processing
summary
 | SES | Budget | Planned | First use | Status
Deformation rigs | 60 kN uniaxial | 100 kEuros* | 22/23 | HCBEER | Ready to be transferred – waiting for TA signature
 | 50 kN Tortion/Rotation + DIC/DVC | 420 kEuros + Grant | 22/23 | FSODIN | Waiting for cost estimation
 | 5-10 kN soft matter | 0 | >2027 | SOUPLOKI | On hold
Furnaces | Joule heating for 60kN rig | Included in * | 22/23 | HCBEER | Idem 60 kN uniaxial rig
 | UHT- Mirror furnace | Grant | ? | FSBEER | Kick-off meeting done
 | Induction furnace (Aarhus) | 90 kEuros | 23 or 24 | HCDREAM | Potential Swedish IK – won’t start before beg 23
 | Cryostream/hot air blower (Aarhus) | 90 kEuros | ? | HCDREAM | On hold- looking for partners
 | ILL- type (x2) | 75 kEuros | 22 | HCDREAM | Refurbishment started at LLB
Thermo-mechanical testing | Dilatometer | 480 kEuros | 22-24 | FSBEER | Start specifications end of 2022
 | Gleeble | 0 | >2027 | SOUPBEER | On hold but first discussions in 2021

## Slide 7: Finish presentation