## Slide 2: Installation and commissioning plan/status for the ACC ODHDS¶
PRESENTED BY Mattias Eriksson/Donya daryadel

## Slide 3: Agenda
Accelerator ODHDS Installation Current Status/Remained Activities
Accelerator ODHDS Installation/Commissioning Plan

## Slide 4
1
Accelerator ODHDS Installation Current Status/Remained Activities

## Slide 5: Accelerator ODHDS Installation
All 14 monitors were installed in klystron gallery and GSA.
Installation of sampling and exhaust micropipes and filters for all 14 sampling points along the SCL and A2T area were done .
All the sampling and exhaust micropipes are connected to the monitors.
Current status

## Slide 6: Accelerator ODHDS Installation
Current status

## Slide 7: Accelerator ODHDS Installation
Current status

## Slide 8: Accelerator ODHDS Installation
Current status

## Slide 9: Accelerator ODHDS Installation
Current status

## Slide 10: Accelerator ODHDS Installation
Current status

## Slide 11: Accelerator ODHDS Installation
Current status

## Slide 12: Accelerator ODHDS Installation
Remained activities and their pre-requisites
  Procurement of required cables
  Conduit installation
ODH monitors cabling
  Procurement of extra alarm plates and boxes
  Switching off TODHDS
Alarm device Installation
  Procurement of junction boxes
  Conduit installation
Alarm device cabling
  Delivery of all the components inside the cabinet
  Manufacturing of the cabinet.
  Hardware FAT of the cabinet.
Cabinets installation after FAT
  Cabinets installation
Connecting cables to the cabinets

## Slide 13
2
Accelerator ODHDS Installation/
Commissioning Plan

## Slide 14: Accelerator ODHDS Installation/ Commissioning Plan
ODHDS Development lifecycle

## Slide 15: Accelerator ODHDS Installation/ Commissioning Plan
SEP 22
OCT 22
NOV 22
DEC 22
JAN 23
FEB 23
MAR 23
APR 23
MAY 23
26th
MAY 23
SEP22 – DEC22
NOV22-FEB23
MAR23
SEP22-20th APR23
This activity can be finished after delivery of all required cables, boxes, and conduits
This activity can be finished after the delivery
of all the cabinet’s components.
This activity can be started after cabinet manufacturing. The planned end date for it is on 15th MAR.
Starting this activity needs delivery of extra alarm plates, boxes and switching off TODHDS.
This activity can be started after Hardware FAT. The planned end date for it is on 31th MAR 23.
This activity can be started after cabinet installation and cable termination. The planned end date for it is on 20th APR 23.
The planned end date
for it is 20th APR 23.
This activity can be started after soft. Pre-FAT and Hardware SAT. The planned end date for it is on 8th MAY 23.
The planned end date for it is on 26th MAY 23.
FEB22 – SEP22
This activity was started in parallel with PDR and finished before this CDR.
FEB 22
ODH monitors/
Alarm device cabling
Hardware FAT
Alarm device installation
Cable termination
Hardware SAT
Soft. Dev./Peer review/Pre-FAT
Cabinet manufacturing
SIT
Punch removal &
Put into operation
ODH monitors/Sampling pipes installation

## Slide 16: THANK YOU