## Slide 2: PSS Ways of Working
Enigneering Handbook & High Level Requirements
PRESENTED BY Gustav Ljungquist

## Slide 3: Agenda
1 Organisational structure
2 Engineering Phases
3 Verification and Validation
4 Post first validation
5 High Level Requirements

## Slide 4
Organisational structure
1

## Slide 5: Organisational structure
  Thee different types of roles
    Project
    Engineering
    Installation & commissioning
  Responsibilities for documents
    Author
    Reviewer
    Approver
Roles

## Slide 6: Organisational structure
  One coordinator per system
  Leads works with several systems
Structure

## Slide 7
Engineering Phases
2

## Slide 8: Engineering Phases
  High Level documents
    Applicable to all ESS PSS
  Documents in workflow, system specific
  Order of activities and documents
  Alignment with functional safety standard IEC 61511
  Entry criteria to documents
High Level documents

## Slide 9: Engineering Phases
Requirements & Analysis Phase and System Design Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 10: Engineering Phases
Detailed Design Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 11: Engineering Phases
Manufacturing & Preparation for Installation Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 12: Engineering Phases
Installation Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 13: Engineering Phases
Local Functional Testing Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 14: Engineering Phases
Integrated Functional Testing Phase
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 15
Verification and Validation
3

## Slide 16: Verification and Validation
  Verification
    Confirmation by examination and provision of objective evidence that the requirements have been fulfilled. The activity of demonstrating for each phase of the relevant SIS safety life-cycle by analysis and/or tests, that, for specific inputs, the outputs meet in all respects the objectives and requirements set for the specific phase.
    Verification proves “Have we built it right?”. Verification is mainly an internal development process.
Definitions
  Validation:
    Confirmation by examination and provision of objective evidence that the particular requirements for a specific intended use are fulfilled. This means demonstrating that the SIF(s) and SIS after installation meet the SRS in all respects.
    Validation proves “Have we built the right thing?”. Validation is mainly an external development process which involves the end user.

## Slide 17: Verification and Validation
  Connection between tests and High Level Requirements for PSS
  Verification activities
    Tests
    Reviews
  Connection between verification activities and requirements
Requirements and design specifications

## Slide 18: Verification and Validation
  Hardware specific verification
    Electrical Design Review
    Hardware FAT
    Hardware SAT
  Software specific verification
    Software peer-review
    Software pre-FAT
  Integration verification
    SIT
    FIT
Verification
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 19: Verification and Validation
  Done in Detailed Design Phase
  Electrical design documentation reviewed in detail against the electrical design specifications
  Testing done against the design documentation
Verification - Electrical Design Review
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 20: Verification and Validation
  Done in Manufacturing and Preparation for Installation Phase
  Verify as-built hardware system meets specified design
    Includes component tests
Verification - Hardware FAT
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 21: Verification and Validation
  Done in Installation Phase
  Verify hardware system is installed as specified in its operational environment
    Includes the same tests as HW FAT, once the hardware is delivered to ESS and some additional field device tests and a loop check
  Shall be performed by ESS on the site
Verification - Hardware SAT
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 22: Verification and Validation
Verification - Software Peer-Review
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review
  Done in Manufacturing and Preparation for Installation Phase
  First stage
    Before software pre-FAT
    Confirm software is developed according to guidelines
    Reveal potential software design defects
    Ready for simulation
  Second stage
    After FIT
    Confirm all software related procedures have been properly followed
    Software properly versioned and stored
    All recommendations and modifications from first stage of software peer review properly implemented
  Explained further in “Software strategy for ESS PSS”

## Slide 23: Verification and Validation
Verification - Software pre-FAT
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review
  Verify software functionality
    Simulations in test environment
  Main objectives:
    Reveal software design defects
    Avoid systematic failures
    Verify compliance with systems requirements and design specifications
  Explained further in “Software strategy for ESS PSS”

## Slide 24: Verification and Validation
  Done in Local Functional Testing Phase
  Verify installed hardware and software work together properly
    Ensure their combination is serving the purpose of PSS safety functions and procedures.
  EUC to be connected to PSS and tested during SIT will be assessed on a case-by-case basis.
  Some EUC may need to be disconnected from PSS during PSS SIT
    To reduce the risk of damaging the EUC due to repeated tests
Verification - SIT
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 25: Verification and Validation
  Done in Integrated Functional Testing Phase
  Generally a repetition of the positive tests from SIT
    EUC is operational and connected to PSS
  Connection to and test with ACC PSS is performed during FIT for:
    Target Station PSS
    Bunker PSS
    Instruments PSS
Verification - FIT
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 26: Verification and Validation
  Prove PSS meets safety and operational requirements
  Demonstration of SIFs and other PSS functions should be presented to all identified stakeholders
  Stakeholders should have the access to all PSS documentation
    Test specifications
    Test reports
  Demonstration shall be carried out on the real system at the ESS site
    Normally covers the tests from the FIT
Validation
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 27
Post First Validation
4

## Slide 28: Post First Validation
  Now:
    Tracking in Jira
    Fill in CHESS template
  Future
    EAM
Maintenance
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 29: Post First Validation
  Before fault
    Preventive Maintenance
    Proof Testing
  After fault
    Corrective Maintenance & Revalidation
  No fault
    Revalidation
Maintenance
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 30: Post First Validation
  Configuration management plan
    CIDL
    Change requests
    Change log
  Non-conformity
  Non-compliance
    Figures to the right ar the different workflows
Configuration Management
CDR = Critical Design Review
CHESS = Collaboration Home European Spallation Source
CIDL = Configuration Item Documentation List
EAM = Enterprise Asset Management
EUC = Equipment under control
FAT = Factory Acceptance Test
FIT = Final Integration Test
FSA = Functional Safety Assessment
HW = Hardware
IRR = Installation Readiness Review
ISRA = Information Security Risk Assessment
PDR = Preliminary Design Review
SAT = Site Acceptance Test
SIF = Safety Instrumented Functions
SRR = Safety readiness review
SW = Software
TRR = Test Readiness Review

## Slide 31
High Level Requirements
5

## Slide 32: High Level Requirements
  PSS_HLREQ1
    Comply with functional safety standard IEC 61511
  PSS_HLREQ2
    Where necessary, contribute to the mitigation of risks to personnel as identified in the parent system risk assessment
Specific Requirments

## Slide 33: High Level Requirements
  PSS_HLREQ3
    Provide parent system operator(s) with the information necessary to supervise the PSS
    This information includes but is not limited to:
        Health status of the PSS
        Feedback from PSS actuators, where applicable
        State of the PSS controlled area
        Warning and alarms
Specific Requirments

## Slide 34: High Level Requirements
  PSS_HLREQ4
    Record information of PSS operation to allow for event reconstruction and analysis
  PSS_HLREQ5
    Support operation in case of a degraded mode of operation of EUC if the degraded state is not hazardous to personnel, as defined in the parent system risk assessment
Specific Requirments

## Slide 35: End of presentation