## Slide 1: Project Schedule and risks
CDR for PSS Target station and bunker
PRESENTED BY Ahmed Abujame

## Slide 2: Agenda
1 Project status
2 Project Procurement plan
3 Project Schedule
4 Project Risks & Risk Register
5 Next Step

## Slide 3
Project Status
1

## Slide 4: Project installation- Target
PSS raceways and supports are completed (inspected by ESS QC and approved)
Raceways earthing completed (inspected by ESS QC and approved)
All PSS Racks have been installed (PLC Rack, 3 RIO, KEU and PA system control cabinet)
Manufacturing of PLC racks and RIO racks are planned to start W19
D02
Completed Installation

## Slide 5: Project installation – Target Station
Field devices
  Emergency shutdown stations
  Message displays
  Mechanical and electrical switches
  PLC & RIO racks population
  Blue lights and ICCs
Fibers, power and signal Cables
D02
Upcoming installation

## Slide 6: Project installation – Bunker PSS
D01/D02/D03
Completed Installation
bnrpss-NWBCtrl-Rack-002 installed in D02.085 utility room
bnrpss-SEBCtrl-Rack-002 installed in D02.085 utility room
Mechanical switches for NWB and SEB for Light shutter system are all installed
Installation of raceways and supports in D02 is completed

## Slide 7: Project installation – Bunker PSS
D01/D02/D03
Upcoming installation
bnrpss-NWBCtrl-Rack-002 installed in D02.085 utility room
bnrpss-SEBCtrl-Rack-002 installed in D02.085 utility room
Raceways in D03/D01 to the racks, cable laying , earthing, etc…

## Slide 8
Project Procurement plan
2

## Slide 9: Project procurement plan
14-ICS-Live.9 Personnel Safety System | 
14-ICS-Live.9.1 Management and Administration | 
14-ICS-Live.9.1.5 Equipment | 
ICS-A20218250 | Access Stations & accessories NSS Bunker (Gunnebo)
ICS-A20218390 | Key exchange Accelerator PSS, Target, NSS Bunker (Fortress)
ICS-A20218430 | Message Displays Accelerator PSS, Target & NSS Bunker (Lasermet)
ICS-A20218550 | Equipment Installation support (from Service provider)
ICS-A20218570 | NSS PSS Equipment budget (TBL, Bunker1, Bunker2 Loki, Odin, Dream and Bifrost)
ICS-A2146942890 | NSS Infra for PSS
ICS-A2146942930 | Generic equipment for installations 2024
ICS-A2146943050 | NSS PSS Equipment budget (TBL, Bunker1, Bunker2 Loki, Odin, Dream and Bifrost)
ICS-A2146943070 | Equipment Installation support for NSS (from Service provider)
ICS-A20218290 | Racks NSS Bunker (Pentair)

## Slide 10
Project’s Schedule
3

## Slide 11: Project Schedule
P6 PSS Target Station

## Slide 12: Project Schedule
PSS Bunker

## Slide 13
Project Risks & Risk Register
4

## Slide 14: Project risks
For this stage of the project, the risks are dependencies to the installation of stakeholder’s equipment in different areas as well as energization of various systems
Delays in any installation or energization will subsequently delay SAT/SIT/FIT
 | IMPACT |  |  |  | 
LIKELIHOOD | NEGLIGABLE | LOW | MODERATE | SIGNIFICANT | SEVERE
CERTAIN | MED | MED | MED | HIGH | HIGH
LIKELY | LOW | MED | MED | HIGH | HIGH
POSSIBLE | LOW | MED | MED | MED | HIGH
UNLIKELY | LOW | LOW | MED | MED | MED
IMPROBABLE | LOW | LOW | LOW | LOW | LOW
 | 1 | 2 | 3 | 4 | 5
0.9 | 0.9 | 1.8 | 2.7 | 3.6 | 4.5
0.7 | 0.7 | 1.4 | 2.1 | 2.8 | 3.5
0.5 | 0.5 | 1 | 1.5 | 2 | 2.5
0.3 | 0.3 | 0.6 | 0.9 | 1.2 | 1.5
0.1 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5
Risk ID | RISK/Opp | Type | Description | System | PSS Milestone | Probability | IMPACT | Risk SCORE | RISK MITIGATION COMPLETION PLAN | Status of Action
1 | RISK | SCHEDUELING | high dependencies on stakeholders installation and commissioning plans | PSS-Bunker | PSS-Loki SIT | 0.5 | 2 | 1 | implement activities linking in P6, weekly coordination with concerned stakeholders | 

## Slide 15
Next Steps
5

## Slide 16: Next Steps
E01/D02/D03
Address any comments raised by CDR committee
Conduct installation readiness review (IRR) with relevant stakeholders
Commence installation activities on site
Complete all procurement and mounting plates for PLC/RIO racks manufacturing

## Slide 17
Questions?