## Slide 1: Conventional Facilities
Kent Hedin
Head of Conventional Facilities
www.europeanspallationsource.se
28 September 2016

## Slide 2: CF Scope
From CF Project Plan:
  “CF shall deliver the physical space for a sustainable research facility in a sustainable way, within budget, according to schedule and with the proper function and quality “.
CF will provide ESS with
Buildings,
Mechanical and electrical infrastructure
Layout and landscaping

## Slide 3: Aerial view 26 August 2016

## Slide 4: Project Scope (23 buildings) Plan, July to December 2016
H05 Primary Substation
H06 Distribution Substation
H01 CUB Building
G04 Cryo Compressor Building
G02 Klystron Gallery
G01 Linac Tunnel
D01
Experimental Hall 1
D02 Target Building
E02 Beam Line Gallery
F03 Logistic Centre/Shipping & Receiving
H09 Waste Storage
H10 Sprinkler Central
F04 Guard House
D03 Exp. Hall 2
MEP in progress
Internal finishes
Roofing & Facade
Concrete works
Not started
E03
E01 Experimental Hall 3
E05
E04 Lab
D05
D06
D07
Building complete
Earthworks/excavation
D08
D04
MEP works
Sectional Handover Inspection (SHIN)
Aug 2016
SHIN, Oct 2016
E01-E05: Concrete Works completed by end 2016
D01/D03-D07:Concrete Works completed by end 2016
Concrete works ongoing to Monolith & Active Cells
(remaining areas tbc)
Civil works:
Backfill ongoing to all areas of G01
Excavation and installation of HV Cables between H06 and G-Bldgs.
Commencement of HA-HA wall construction.
Steel/frame erection completed by Sep 2016
G04: First Access for Acc Div 09-Sep-16
G02: First Access for Acc Div 28-Nov-16
(Cold box)
Piling works
Start Oct 2016

## Slide 5: CF Organization
Employees 23
Consultants 206
On site 339
Sum 569
Notes:   Energy
  Climate
  Health
  Agriculture
  Digital society

## Slide 6: CF Staff on site
Chart: 
| Jan-2015 | Jun-2015 | Dec-2015 | June-2016 | Dec-16 (forecast)
SEC Office | 62.5 | 95 | 108.5 | 124 | 122
TC Office | 8 | 28 | 35 | 35 | 36
SEC Site Operatives | 16 | 59 | 39 | 28 | 23
TC Site Operatives | 20 | 68 | 142 | 173 | 155
6
93,5
83
106,5
250
324,5
123
127
143,5
181
201
159
336
178
158
360

## Slide 7: CF Staff on site
Chart: 
| Jan-2015 | Jun-2015 | Dec-2015 | April-16 (actual) | Jun-16 (forecast) | Dec-16 (forecast)
SEC Office | 62.5 | 95 | 108.5 | 120 | 118 | 117
TC Office | 8 | 28 | 35 | 28 | 33 | 31
SEC Site Operatives | 16 | 59 | 39 | 32 | 32 | 32
TC Site Operatives | 20 | 68 | 142 | 162 | 219 | 185
7
93,5
83
106,5
250
342
324,5
123
127
143,5
151
181
194
251
148
402
365
148
217
Chart: Total staff, projection
| mars | april | maj | juni | juli | augusti | september | oktober | november | december | januari | februari | mars | april | maj | juni | juli | augusti | september | oktober | november | december | januari | februari | mars | april | maj | juni | juli | augusti | september | oktober | november | december | januari | februari | mars | april | maj | juni | juli | augusti | september | oktober | november | december | 2016 | 2017 | 2018 | 2019
 | 332 | 329 | 378 | 399 | 377 | 414 | 425 | 408 | 401 | 407 | 405 | 410 | 461 | 492 | 499 | 517 | 507 | 533 | 550 | 580 | 618 | 649 | 693 | 722 | 773 | 789 | 779 | 755 | 791 | 812 | 832 | 868 | 874 | 814 | 741 | 726 | 603 | 588 | 518 | 488 | 395 | 370 | 320 | 305 | 295 | 280

## Slide 8: G02 Gallery & G01 backfill

## Slide 9: G01, Accelerator tunnel, topfill

## Slide 10: H01 & G04 from above

## Slide 11: MEP works inside G04

## Slide 12: G04 – Cryo Compressor Building - first handover to ESS
CTL Partial Access (09-Sep)
Linac Compressor Hall Early Access (07-Nov)
Gas Storage Compound Partial Access (07-Nov)
Substation Early Access (21-Nov)
TTI Hall Partial Access (05-Dec)

## Slide 13: CF – project milestones 2016-03-04
Milestone | Access | Date | Status | Comment
G04 Cryo Compressor Building | Full Access | 02 May - 17 | OT | 
CTL Gallery (G04-G01) | Partial Access | 09 Sep - 16 | OT | 
Linac Compressor Hall | Early Access | 07 Nov - 16 | OT | 
Linac Compressor Hall | Partial Access | 04 Jan - 17 | OT | 
Electrical rooms (substation) | Early Access | 21 Nov - 16 | OT | 
Electrical rooms (substation) | Partial Access | 04 Jan - 17 | OT | 
TTI Compressor Hall | Early Access | 05 Dec - 16 | OT | 
TTI Compressor Hall | Partial Access | 01 Feb – 17 | OT | 
Gas Storage | Partial Access | 07 Nov - 16 | OT | 
G04 Cryo Compressor Building

## Slide 14: CF – project milestones 2016-03-04
Milestone | Access | Date | Status | Comment
Gallery Test Facility & Coldbox | Full Access | 02 May - 17 | OT | 
Test Facility CM & RF | Partial Access | 28 Feb - 17 | OT | 
TTl Coldbox & Linac Coldboxhall | Partial Access | 28 Nov - 16 | OT | 
FEB Level 100+2 Stubs | Partial Access | 1 Sep - 17 | OT | 
Gallery + rem stubs B190-B510 | Partial Access | 29 Jan - 18 | OT | 
Gallery + rem stubs B510-B720 | Partial Access | 04 Dec - 17 | OT | 
Gallery + rem stubs B720-B820 | Partial Access | 03 Okt - 17 | OT | 
Cryo Control room | Partial Access | 31 Mar - 17 | OT | 
G02 Klystron Gallery

## Slide 15: The ESS Target Station Layout
130 m
22 m
37 m
Accelerator – Target interface
Target monolith
Utilities block
High bay
Active cells
Isometric View
Transport hall

## Slide 16: Target – Hot cell, Utility & Monolith
Reinforcement works, 1600 mm bottom slab, Monolith.
First casting: September 28.

## Slide 17: D03 – Installation Galleries

## Slide 18: Dog Leg front, D01 installation galleries & D06 substation

## Slide 19: E02 Beam Line Gallery Approx. half of the 838 concrete piles have been installed to date. Total number of concrete piles on site: 6192, whereof 4868 completed (79%)

## Slide 20: Target Station and Instrument Hall sequence

## Slide 21: ESS vision