## Slide 1: ESS Status Update
IKON 11
James Yeck
Director General
www.europeanspallationsource.se 14 September 2016

## Slide 2: People
2
377
Employees
48
Nationalities
~ 100
Collaborating Institutions
42 In-kind Partners
60 Collaboration, MoU and Grant Partners

## Slide 3
Aarhus University
Atomki - Institute for Nuclear Research
Bergen University
CEA Saclay, Paris
Centre for Energy Research, Budapest
Centre for Nuclear Research, Poland, (NCBJ)
CNR, Rome
CNRS Orsay, Paris
Cockcroft Institute, Daresbury
Elettra – Sincrotrone Trieste
ESS Bilbao
Forschungszentrum Jülich
Helmholtz-Zentrum Geesthacht
Huddersfield University
IFJ PAN, Krakow
INFN, Catania
INFN, Legnaro
INFN, Milan
Institute for Energy Research (IFE)
Rutherford-Appleton Laboratory, Oxford(ISIS)
Kopenhagen University
Laboratoire Léon Brilouin (LLB)
Lund University
Nuclear Physics Institute of the ASCR
Oslo University
Paul Sherrer Institute
Polska Grupa Energetyczna - PGE
Roskilde University
Tallinn Technical University
Technical University of Denmark
Technical University Munich
Science and Technology Facilities Council
University of Tartu
Uppsala University
WIGNER Research Centre for Physics
Wroclaw University of technology
Warsaw University of Technology
Zurich University of Applied Sciences (ZHAW)
ESS In-kind Partners

## Slide 4
ESS In-kind, Collaboration and Grant Partners
Aarhus Universitet - AU
A.V. Shubnikov Institute of Crystallography Russian Academy of Sciences -IUCr
Australian Nuclear Science and Technology Organisation - ANSTO
Bilbao Bizkaia Kutxa - BBK
Brookhaven National Lab - BNL
Budker Institute of Nuclear Physics of SB RAS - INP SB RAS
Centre National de la Recherch Scientifique - CNRS
Chalmers Tekniska Högskola - CTH
Cockcroft Institute
Commissariat a l’Energie Atomique et aus Energies Alternatives - CEA
Consejo Superior De Investigaciones Cientificas - CSIC
Consiglio Nazionale delle Ricerche - CNR
Consorcio ESS Bilbao - ESS Bilbao
Consorzio Interuniversitario Risonanze Magnetiche di Meallo Proteine - CIRMMP
Danmarks Tekniske Universitet - DTU
Deutsches Elektronen-Sychrotron - DESY
Diamond Light Source
École Polytechnique Fédérale de Lausanne - EPFL
Elettra Sincrotrone Trieste S.C.p.A.
Eötvös Loránd Tudomanyegytem - ELTE
European Molecular Biology Laboratory - EMBL
European Organisation for Nuclear Research - CERN
European Synchrotron Radiation Facility - ESRF
European X-Ray Free-Electron Laser Facility GmbH - European XFEL
Extreme Light Infrastructure Delivery Consortium - ELI DC
Facility for Antiproton and Ion Research in Europe GmbH - FAIR
Foschungszentrum Jülich GmbH - FZJ
Goethe Universitaet Frankfurt Am Main
GSI Helmholtzzentrum für Schwerionenforschung GmbH - GSI
Helmholtz-Zentrum Berlin für Materialien und Energie GmbH - HZB
Helmoltz Zentrum Geesthacht - HZG
Hongik University, Seoul
Huddersfield University
Indiana University
Institut Laue-Langevin - ILL
Institute of Accelerator Technologies of Ankara University - IAT-AU
Institute of Applied Physics of the Russian Academy of Sciences - IAP RAS
Instituto de Tecnologia Química e Biológica, Universidade Nova de Lisboa - ITQB NOVA
Institutt for Energiteknikk - IFE
Instruct Integrating Biology - Instruct
Instytut Fizyki Jądrowej Henryka Niewodniczańskiego Polskiej Akademii Nauk - IFJ PAN
Integrated Detector Electronics AS - IDEAS
ISIS Neutron Source Facility - ISIS
Istituto Nazionale di Fisica Nucleare - INFN (Catania, Legnaro, Milano)
Japan Proton Accelerator Research Complex - J-PARC
Joint Institute for Nuclear Research - JINR
Karlsruher Institut für Technologie - KIT
Kobenhavns Universitet - KU
Kungliga Tekniska högskolan - KTH

## Slide 5
ESS In-kind, Collaboration and Grant Partners
Laboratoire Léon Brilouin - LLB
Laboratório De Instrumentação e Física Experimental de Partículas - LIP
Latvijas Universitāte - LU
Leibnitz-Instituit für Molekulare Pharma - FMP
Linköpings Universitet
Lund University - LU
Magyar Tudományos Akadémia Atommagkutató Intézet - MTA Atomki
Magyar Tudományos Akadémia Energiatudományi Kutatóközpont - MTA EK
Magyar Tudományos Akadémia Wigner Fizikai Kutatóközpont - MTA Wigner
Masarykova Univerzita - MUNI
Mittuniversitetet - MiUN
Narodowe Centrum Badán Jądrowych - NCBJ
National Research Center Kurchatov Institute - NTI
Nederlands Kanker Instituut - NKI
Norges teknisk-naturvitenskapelige universitet - NTNU
Oak Ridge National Laboratory - ORNL
Oulun Yliopisto - OULU
Paul Sherrer Institut -PSI
Politechnika Warszawska
Politechnika Wrocławska
Polska Grupa Energetyczna - PGE
Roskilde Universitet
Science and Technology Facilities Council - STFC
Source Optimisée de Lumière d’Energie Intermédiaire du LURE – SOLEIL
Stanford University National Accelerator Laboratory - SLAC
Stockholms Universitet
Tallinna Tehnikaülikool - TUT
Tartu Ülikool - UT
Technische Universität Chemnitz - TU Chemnitz
Technische Universität München - TUM
Technische Universiteit Delft - TU Delft
Teknologisk Institut - DTI
Thomas Jefferson National Accelerator Facility - Jefferson Lab
United Kingdom Atomic Energy Authority
Universidade da Coruña
Università degli Studi di Brescia
Université Laval
Universiteit Leiden
Universiteit Utrecht
Universitetet I Bergen
Universitetet i Oslo
University of Bath
University of Manchester - UoM
University of Patras - UPAT
Uppsala Universitet
Ústav jaderné fyziky AV ČR, v.v.i, Oddělení neutronové fyziky - UJF CAS
Ústav technické a experimentální fyziky, České vysoké učení technické v Praze - ÚTEF ČVUT
Vilniaus Universitetas
Weizmann Institute of Science
Zürcher Hochschule für Angewandte Wissenschaft - ZHAW
Swiss Center for Electronics and Microtechnology - CSEM

## Slide 6: Aerial view 26 August 2016

## Slide 7: Tunnel vision

## Slide 8: Target view, from Dog Leg

## Slide 9: D02 monolith casting, 400 mm base slab

## Slide 10: Target – Hot cell, Utility & Monolith

## Slide 11: Target - Hot cell

## Slide 12: D03 – Installation Galleries

## Slide 13: E02 Beam Line Gallery Approx. half of the 838 concrete piles have been installed to date. Total number of concrete piles on site: 6196, whereof 4815 completed (78%)

## Slide 14: E01 – Experimental Halls 3, ramps to E02

## Slide 15: G02 Gallery & G01 backfill

## Slide 16: G02 Klystron Gallery, steel structure & floor castings

## Slide 17: H06 & H01 from above

## Slide 18: H01 & G04 from above

## Slide 19: G04 facades

## Slide 20: MEP works inside G04

## Slide 21: Construction Profile, Aug 2016
 Machine Ready for Beam on Target
 Operations Starts
 Construction
Starts
 First installations
(of Machine Systems)
 Construction Project Complete
 1st Call for
User Proposals
 Machine 2.0 GeV
Total Funding (Cumulative)
Total Baseline Budget incl. Contingency (Cumulative)
Total Baseline Budget excl. Contingency (Cumulative)
Total Earned Value (Cumulative)
Total Actual Cost (Cumulative)
ESS Construction Funding and Budget Profile (As Year Prices)
Notes: Schedule variance = Earned – Schedule
Cost Variance = Actuals - Earned
SPI = Earned/Scheduled
CPI = Earned/Actuals

## Slide 22: Contingency Tracking
Notes: Schedule variance = Earned – Schedule
Cost Variance = Actuals - Earned
SPI = Earned/Scheduled
CPI = Earned/Actuals

## Slide 23: Level 2 Cost Baseline Tracking
34%
% complete
18%
17%
20%
49%
12%
50%
Notes: Schedule variance = Earned – Schedule
Cost Variance = Actuals - Earned
SPI = Earned/Scheduled
CPI = Earned/Actuals

## Slide 24: In-kind possible and agreed/planned
Chart: 
| 2013.0 | 2014.0 | 2015.0 | 2016.0 | 2017.0 | 2018.0 | 2019.0 | 2020.0 | 2021.0 | 2022.0 | 2023.0 | 2024.0 | 2025.0
In-kind Agreed & Planned Total Budget | 2.7181 | 13.7423 | 94.7209 | 234.3816 | 363.2191 | 427.2061 | 468.699 | 494.6458 | 519.6508 | 533.0391 | 540.7246 | 544.909
In-Kind identified as possible Total Budget | 0 | 0.55287 | 6.0495 | 45.5572 | 90.5915 | 114.9353 | 117.8624 | 119.9312 | 120.8799 | 121.0322 | 121.164 | 121.272
Accelerator, Target, ICS and NSS Total Budget | 6.466 | 68.6555 | 160.0625 | 362.0235 | 616.3405 | 839.3408 | 956.341 | 1002.091 | 1039.735 | 1066.176 | 1079.522 | 1086.228 | 1088.463
675m
544.9m
Stretch Goal 747.5m

## Slide 25: IK status - Project dashboard
Agreed
Potential
Planned
Stretch goal

## Slide 26: Main messages
ESS is advancing
at high speed and on track…
Installation phase is starting

## Slide 27: Target Project Status (summary)
Good progress on:
  Design of components (at ESS and by partners).
  Prototyping and testing of key hardware (cold moderator, target W bricks cassettes…).
  Clarification on licensing framework.
  Definition of safety-credited active controls (TSS).
High priority on-going work
  Safety case analyses and accident scenarios assessment.
  Optimization of Target installation plan and integration with civil construction plan, aiming for beam on target in 2019.
Near term efforts focus on:
  Radiation hazard and accident analyses for maintenance.
  Continued transition from Preliminary to Final Design.
  Neutronic calculations for engineering support and shielding verification.
  Intensifying interface integration and coordination.

## Slide 28: Accelerator Project Status (summary)
Continued progress in the construction phase:
  IK contracts: 25 Technical annexes being prepared for the IKRC in October.
  Successful test of key equipment (plasma in the ion source, compressor for cryo-plant, Medium Beta elliptical cavity, …).
  Manufacturing contract for RFQ launched in France.
  Whenever relevant, negotiation and agreement with IK partners on means to recover or mitigate delays.
  Plan for having “Lessons learnt” presentations at the Accelerator Technical Board after encountering issues(first done by INFN Catania)
  At the Accelerator Technical Board on 1 September, all Work Packages showed progress according to plan.

## Slide 29: 2016 priorities
Continue emphasis on schedule performance – key to success
Transition In-kind partners into execution phase (instruments!)
3rd Annual Project Review and Response – April
Submit application to regulatory authority for license to commission first stages of accelerator systems – May
Establish a “cash facility” for liquidity gap/hold schedule – June
Start machine installation (accelerator cryogenic piping) – Sep
Establish operations plans consistent with requirements – Dec
Engage new members – ongoing

## Slide 30: Annual review themes
Evaluated the results from the annual project review completed in late April, a hard-nosed and constructive review.
Recognized intense effort and impressive progress over the last year and provided excellent advice on issues and future challenges. The feedback is used to strengthen plans and actions defined in response to the recommendations. Key themes:
Schedule Management - Continue to improve integrated schedule and resolve known schedule conflicts and delays. Identify lessons from current experience, e.g., delays starting machine in-kind work, target building construction, etc. and consider these lessons-learned in future plans. Ensure that interim milestones are relevant to delivery of early science success at start of user program in 2023.

## Slide 31: Review themes continued (2)
Liquidity Gap – Encouragement to finalize work with lending institutions and the Council so that a “cash facility” for managing the liquidity gap is in place by the last half of the year.
Technical Integration, Installation, and Project Management – Strengthen central technical integration and project management to achieve better ESS-wide communication and optimization. Organize for integrated coordination of installation.
Instrument Program – Take the necessary steps to establish credible schedules for the construction of instruments and increase the probability that the first suite of instruments will be ready at the start of the user program in 2023.

## Slide 32: Review themes continued (3)
Operations Transition – Ramp-up planning for operations. Integrate the schedules and plans for construction and initial operations and establish a management approach that can optimize over the total effort.
Safety and Health – Ramp-up efforts on safety and health to be ready for delivery of buildings and the start of installation work on the site later this year.
The report included over sixty recommendations and many positive findings. The committee reviewed an organization with the competency and capacity to benefit from a thorough critique.
“Project reviews are the most important management tool to ensure that the project is staying on track. If you are not required to have them, you should inflict them on yourself.”

## Slide 33: Summary
  Construction ~25% complete today and over 30% by end of 2016
  Priority on schedule performance – key to success
  Emphasis on securing in-kind deliverables in collaboration
  Additional work to ensure European Spallation Source ERIC provides the institutional framework needed for long term success
  Working to establishing operations plans consistent with facility requirements and supportable by the Council
  Core Values are Excellence, Openness, Collaboration, and Sustainability
  Mission – design, build, and operate the world’s
  leading research facility using neutrons