## Slide 1: Problems Identified - Schedule
Need better communication of what milestones means and what they require of all teams.
General perception that the schedule is unrealistic
No one asking for an integrated schedule and it’s missing (scheduling silos)
Need of a management forum for the schedule
Not (totally) clear who is the owner of the integrated schedule

## Slide 2: Outcomes
Generally a lot more focus on the schedule and related processes
Redefined level 1 MS
Improved process for managing the milestones
Ownership of integrated schedule adressed
Dedicated workshops focusing on scheduling interfaces
Planners working closer across project bounderies
”Sketchy” plans being replaced with detailed schedules
Partner schedules being detailed, communicated and managed
Collective understanding and ownership of the ESS schedule
Completed
Ongoing