## Slide 1
Interface Advisory Committee
October, 2016
Out-Brief

## Slide 2: Response to Charge
Requirements for BES and bunker not yet completely defined but good start has been made (e.g. seismic, local v global shielding in bunker)
Yes – to the extent they have been defined
Value engineering is needed if it does not imply significant delay
  Alternate shielding design choices need to be tensioned against schedule, cost and resources
  Windows need to be carefully considered (trade between safety assumptions and scientific performance)

## Slide 3: Observations
Each month of project delay costs $20M
Bunker and beam extraction on CP
Two moderators will be installed
Instrument teams asked to assess using upper moderator
PDR for bunker Dec 2016
Interfaces are documented in ICDs that must be complete before PDR
ESS needs 5 – 10 additional engineers to meet instr schedule
Scientific success is the driver
1-cm-thick Al window at monolith exit
Unstacking bunker shielding requires dedicated use of main hall crane during significant part of every outage

## Slide 4: Observation (cont’d)
Bunker & beam extraction are ESS self-performing
Monolith insert alignment off-line on a test stand
Light shutters not intended to be closed during beam delivery
Additional shutters responsibility of instrument teams
All biological shielding has to be approved by shielding coordinator
Civil design is fixed (changes expensive)
Expect 3 mm of creep plus 3 mm elastic deflection for floor in bunker region
Bunker is not ventilated

## Slide 5: Findings
ESS has clearly recognized the importance of managing technical and organizational interfaces
  Project manager & technical coordinators to oversee interfaces
Encouraging start on bunker design & operational plan
Self performing bunker work is a sensible step
Fully effective internal communication not yet achieved
Talented group of neutronics staff not effectively coordinated due to organizational barriers
Requirements for BES and bunker not yet completely defined

## Slide 6: Recommendations
Pull together a team that can deliver bunker (leadership, neutronics, safety, operations, engineering, neutron optics)
  Consider colocation of team
  eliminate potential for single-point failure
  3D print models of bunker
Pursue effective communication across organizational boundaries and with external partners
Define information and expectations for the preliminary design review
Conduct internal, followed by external, peer reviews of the shielding calculation suite (bio, bgr, activity) prior to sign-off by shielding coordinator
Review operational interfaces
  Consider impacts of beam power increases on bunker access
Consider adding neutron beam transport and experimental hall layout to the tTAC scope

## Slide 7: Thank you