## Slide 1: Commissioning - Safety
Lali Tchelidze
Monika Hartl
Stuart Birch
Peter Jacobsson
www.europeanspallationsource.se
2 October 2016

## Slide 2: Readiness Reviews & Commissioning Steps
Step | Commissioning Scope | Readiness Review date (Accelerator/ICS) | Commissioning Start date (Accelerator/ICS)
1 | Ion Source & Low Energy Beam Transport (LEBT) | Oct-17/Dec -17 | Nov 2017/Jan 2018
2 | RFQ & Med Energy Beam Transport (MEBT) | Jun-18 | Jul-18
3 | Drift Tube Linac 1 (DTL 1) | Sep 2018 | Nov-18/Oct-18
4 | DTL 2-4 | Dec-18/Feb-19 | Jan-19/Feb-19
5 | DTL 5, Spoke and Med-β Cryomodules, HEBT & Beam Dump | Mar 2019 | May-19/Mar-19
6 | Accel to Target (A2T), HEBT, Target, Instrument bunker, & test beamline | Jun-19 | End Jun-19

## Slide 3: 1st Stage of Proton Beam Commissioning
Fist stage of the beam commissioning will take place in several steps:
  Ion Source and LEBT commissioning
  RFQ and MEBT commissioning
  DTL1 commissioning
  DTL2 to DTL 4 commissioning

## Slide 4: 1st Stage of Proton Beam Commissioning
Top view of tunnel section housing ion source, LEBT, RFQ, MEBT and DTL 1-4, separated from the rest of the tunnel by a temporary shielding chicane.
At each step of commissioning, a temporary beam stop (Linac4/CERN design) will be used to safely absorb the beam.

## Slide 5: 1st Stage of Proton Beam Commissioning
Prompt total dose rate maps up to DTL tank 4, for an operational 1 W/m uniform beam loss rate.

## Slide 6: 1st Stage of Proton Beam Commissioning
Fault studies for shielding verification.
  A series of predefined verification studies will be conducted with the beam at the output of the RFQ and DTL tanks.
  A limited power beam will be sent to a specific location and a set of measurements will be made, using radiation monitoring system, to compare the measured radiation dose rate levels to those from calculations.
  The beam power will be increased in small steps and measurements will be repeated and recorded at each step.
  Additionally, X-ray dose rates will be measured during RF conditioning.

## Slide 7: Accelerator Tunnel PSS Zones
To facilitate the search procedure in accelerator tunnel, PSS has considered 7 zones in the tunnel which are separated from each other by
6 fences. The position of these fences will be continuously monitored through two safety switches installed on each fence. (It should also be
noted that the emergency exit routes are also considered as independent search zones)
Zone 1 includes: Proton Source, LEBT, RFQ, MEBT
Zone 2 includes: DTLs
Zone 3 includes: Spoke cavities
Zone 4 includes: Elliptical cavities
Zone 5 includes: Elliptical cavities
Zone 6 includes: HEBT
Zone 7: A2T

## Slide 8: Accelerator Tunnel PSS1

## Slide 9: PSS 1 Hardware: Beam-off Stations
Zone 2
BOS 1
Zone 2
BOS 3
Zone 2
BOS 2
Zone 1
BOS 1
Zone 1
BOS 2
Zone 1
BOS 3
PSS 1 Area Plan View
Beam-off Stations

## Slide 10: PSS 1 Hardware: Radiation Monitors
BOS
BOS
BOS
BOS
BOS
BOS
PSS 1 Area Plan View
Radiation Monitors
Zone 2
RM 1
Zone 1
RM 2
Zone 1
RM 1
Zone 2
RM 3
Zone 2
RM 2
Beam-off Station

## Slide 11: PSS 1 Hardware: Access & E-exit Doors
+
BOS
BOS
BOS
BOS
BOS
BOS
PSS 1 Area Plan View
Access/E-exit Doors
RM
RM
RM
RM
RM
E-Exit Door
Access System
FEB
E-Exit
Door
Beam-off Station
Radiation Monitor

## Slide 12: PSS 1 Hardware: Fire Door & Zone Fences
+
BOS
BOS
BOS
BOS
BOS
BOS
PSS 1 Area Plan View
Fire Door/Zone Fence
RM
RM
RM
RM
RM
PSS Zone Fences
Fire Door
E-Exit
Door
Fire
Door
Zone 2
Fence
Zone 3
Fence
Beam-off Station
Radiation Monitor
E-exit Door
Access Doors

## Slide 13: PSS 1 Hardware: PSS Blue & Red Lights
+
BOS
BOS
BOS
BOS
BOS
BOS
PSS 1 Area Plan View
PSS Blue/Red Lights
RM
RM
RM
RM
RM
E-Exit
Door
Fire
Door
Fence
Fence
Kanby 2 batten luminaries
Separately switched, 2x58W
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
Beam-off Station
E-exit/Fire Door
Access Doors
Radiation Monitor
Zone Fence

## Slide 14: PSS 1 Hardware: Message Display
+
BOS
BOS
BOS
BOS
BOS
BOS
PSS 1 Area Plan View
Message Display
RM
RM
RM
RM
RM
E-Exit
Door
Fire
Door
Fence
Fence
Message Display
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
Beam-off Station
E-exit/Fire Door
Access Doors
Radiation Monitor
Zone Fence
B/R Light
Message Displays will be installed at the entry and E-exit points to tunnel as a pre-warning for radiation hazards, ODH, access status, etc.
The potential solutions are: LED signage interfacing Siemens S7-1500 PLC and/or LED TV.

## Slide 15: PSS 1 Hardware: Public Address System
BOS
BOS
BOS
+
BOS
BOS
BOS
PSS 1 Area Plan View
PA System
RM
RM
RM
RM
RM
E-Exit
Door
Fire
Door
Fence
Fence
PA System
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
PSS B/R Light
Beam-off Station
E-exit/Fire Door
Access Doors
Radiation Monitor
Zone Fence
B/R Light
Message Display
Currently no PA system has been foreseen by CF for accelerator tunnel and target buildings.
PSS PA system will be installed to broadcast messages during ODH, search, etc.
PA system will be triggered by PSS PLC(s).

## Slide 16: Licensing View
SSM will handle the commissioning after finalisation of the installation permit; (Q2/Q3 2017)
ESS has all the requirements concerning radiation protection, ESS will finalise
  Necessary hardware installations (temporary and permanent)
  Necessary rules & regulation
  Staff plan
Before start-up, ESS will conduct an Accelerator Readiness Review
Set-up of the team has to be done Q1 2017.

## Slide 17: Science Directorate (SD) work areas
RML laboratory and central ESS sample
storage facility in D08
Hall 1
Hall 2
Hall 3
E03
E04
D04
D07
D08
Hall 1
Instr. Estia / Vespa / Skadi / Odin / Dream / Vor
D07 labs (1 × Life Science+specialized)
D08 labs (1 × Chemistry, 1 x Radioactive Mat. L.
+specialiced)
Hall 2
Instr. Freia / Loki / HR-NSE
D04 Labs (1 × Life Science, + specialized labs)
Hall3
Instr. NMX / Beer / C-Spec / Bifrost
Miracles / Magic / T-Rex / Heimdal
E03 workshops, labs (1 × Engineering)
E04 labs (1 × Life Science, 1 × Chemistry,
+ characterization/specialized labs)
17
Notes: The room fit out has been aligned with instrument layout. Each hall has access to a basic laboratory. Main labs not included in construction are the basic chemistry in D04 and instrument rooms in D07, D08 and E04.
No large ticket, capital equipment is included in construction budget scope.

## Slide 18
Experimental
Cave -
Closed
Shutter
sample
beamline
Experimental
Cave –
Open
Shutter
sample
beamline
Shielding with active
Personal Safety System (PSS)
FLEXIBLE ZONING
Supervised
Unrestricted controlled
Restricted controlled
Highly restricted controlled
Zoning for experimental hall & labs:
one supervised zone
access control,
radiation monitor.
Rad. Mat. Lab.
RML

## Slide 19: Science Directorate: Experimental Facilities
Experimental Halls host instruments and bunker
Laboratories & Workshops support instrument operation and user program –sample handling, equipment maintenance
Generic Instrument used to estimate dose rates, activation, inventory, hazards …
Individual instrument requires operational readiness review prior hot commissioning.

## Slide 20: Instrument in the short hall Loki
bunker
beamline
Instrument specific lab
exp. cave

## Slide 21: Instrument in the long hall - NMX
bunker
beamline
Instrument hutch
Instrument specific lab
exp. cave

## Slide 22: Safety Acceptance Review (SAR)
Safety Acceptance Review (SAR) will occur for each instrument before installation & commissioning and when instruments are modified
SAR-committee will consist of subject matter experts from within ESS as well as experts from other facilities
Each review will include:
  Radiological Safety (shielding assessment including activation, functionality of PSS/shutters, radiation monitoring for the instrument and more)
  General Safety (mechanical, electrical,…)
  Instrument Specific Hazard Analysis
  ...
During hot-commissioning : verification of radiological performance by measurements
During instrument lifetime: regular surveys