## Slide 1: Gamma Blockers Kick-off Meeting High level project overview & schedule
Iñigo Alonso
Linac Integration Section
www.europeanspallationsource.se
9 November 2016

## Slide 2: Outline
Accelerator Overview
Accelerator Collaboration
High Level Schedule – ACCSYS Project
Civil Construction Status
Installation Schedule Overview
Team Members

## Slide 3: Accelerator Overview
Design Drivers:
High Average Beam Power
5 MW
High Peak Beam Power
125 MW
High Availability
Key parameters:
    -2.86 ms pulses
    -2 GeV
    -62.5 mA peak
    -14 Hz
    -Protons (H+)
    -Low losses
    -Minimize energy use
    -Flexible design for mitigation and future upgrades
Spokes
Medium β
High β
DTL
MEBT
RFQ
LEBT
Source
HEBT & Contingency
Target
2.4 m
4.6 m
3.8 m
39 m
56 m
77 m
179 m
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
352.21 MHz
704.42 MHz
First beam at 572 MeV in June 2019
5 MW capacity for 2023

## Slide 4: Accelerator Collaboration
Spokes
Medium β
High β
DTL
MEBT
RFQ
LEBT
Source
HEBT & Contingency
Target
2.4 m
4.6 m
3.8 m
39 m
56 m
77 m
179 m
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
352.21 MHz
704.42 MHz

## Slide 5: In-Kind Project Turned Into In-House Project
In-kind (main contributions)
ATOMKI (RF-LPS)
CEA (RFQ, SRF, Diagn)
CNRS (SRF, Cryo distrib)
Daresbury Lab (SRF, Vacuum)
Elettra (RF, Magn, PS, Diagn)
EPFL (Modulators)
ESS-Bilbao (MEBT, RF)
Huddersfield Univ (RF distrib)
IFJ PAN (Installations)
INFN Catania (Source, LEBT)
INFN Legnaro (DTL)
INFN Milan (SRF)
Lodz UT (LLRF)
NCBJ (LLRF, gamma blockers)
Tallinn UT (RF)
Univ Bergen (Seconded staff)
Univ Oslo (Diagn)
Warsaw UT (LLRF)
Wroclaw UT (Cryo distrib)
Paid contracts
Aarhus Univ (Beam delivery)
DESY (Diagn)
Lund Univ (LLRF, RF)
Uppsala Univ (Tests)
In steady state, all knowledge has been transferred from in-kind partners to ESS in Lund, expertise has been acquired in all areas, technical capabilities for maintenance and repair of all systems have been developed.
In some cases, as for repair of super-conducting cavities and cryomodules, it may take 10 years to reach such capability.
Maintenance of technical expertise is clearly of vital importance.

## Slide 6: High Level Schedule – ACCSYS Project
2016
2017
2018
2019
2020
2021
2022
RF
NCFE
Cryogenics
Spoke & Elliptical
cavities and cryomodules
CDS INSTALLATION
STARTS
ACCELERATOR
CRYOPLANT
COMM./READY
Commissioning
SPOKE CM
TESTING STARTS
START RFQ MACHINING
SPOKE & MB CM
PRODUCTION
LAUNCHED
DECISION IOT OR
KLYSTRON FOR HB LINAC
1370 MeV PROTONS
AVAILABLE
RF SYSTEM
FOR MB
READY
2 GeV PROTONS AVAILABLE
SC LINAC
570 MeV
READY
SC LINAC
2 GeV
READY
FIRST PROTONS ON TARGET
TECHNICAL STOP
TECHNICAL STOP
BEAM COMM. COMPLETED FOR NCFE but DTL5
BEAM COMM. COMPLETED FOR ISRC-> MEBT
TOSHIBA/CPI/THALES KLYSTRON
PROTOTYPE DELIVERED
CPI/THALES AND L3 IOT
PROTOTYPES DELIVERED
MB CM
TESTING STARTS
START RFQ COMMISIONING
1-11 HB CM INSTALLED
12-21 HB CM INSTALLED
CDS COMMISSIONED
RFI ISRC & LEBT
RFI
RFQ
RFI
MEBT
RFI
DTL5

## Slide 7: Civil Construction Status
Klystron Gallery
Accelerator Tunnel

## Slide 8: Installation Schedule Overview
Tunnel length
Time
DMPL
A2T
Notes: Under development

## Slide 9: Team Members
Name | Role regarding the Gamma Blockers
Iñigo Alonso Fernandez | Work Unit manager
Stephen Molloy | Integration Section Leader
Lali Tchelidze | Accelerator Safety Group Leader
Timo Korhonen | ICS Chief Engineer
Daniel Piso | ICS Hardware Integration Group Leader
Annika Nordt | Protection Group Leader (MPS)
Stuart Birch | PSS
Fabio Ravelli | Vacuum Engineer
Edgar Sargsyan | Installation Planning
Nick Gazis | Interface to Conventional Facilities
Fabien Rey | Survey and Alignment Group Leader