## Slide 1: Gamma Blockers Kick-off Meeting Schedule and Milestones Review
Iñigo Alonso
Linac Integration Section
www.europeanspallationsource.se
9 November 2016

## Slide 2: Outline
Project Stages and Activities
Schedule for deliverables from the SoW
Key Milestones and Earned Value

## Slide 3: Project Stages and Activities
Stage 1: Design
  Preliminary Design
  Detail Design
Stage 2: Realization and Verification
  Fabrication
  Verification
  Transport
Stage 3: Installation and Operational Verification
  Installation
  Reporting

## Slide 4: Schedule for deliverables from the TA
Start date (T0): 2016.10.01
Preliminary Design Review (PDR): 2017.01.13
Critical Design Review (CDR): 2017.06.01
Factory Acceptance Test (FAT): 2018.03.30
Delivery at Lund: 2018.04.29
Site Acceptance Test (SAT): 2018.06.01
Installation Readiness Review: 2018.11.30

## Slide 5: Key Milestones and Earned Value
# MS | MS ID | Short Description | Planned/Baseline date | Responsible | Location | EV value [%]
1 |  | Kick-off meeting | As soon as possible | ESS ERIC | ESS ERIC | 0%
2 | A20150500 | PDR | 2017.01.13 | ESS ERIC | ESS ERIC | 10%
3 | A20150520 | CDR | 2017.06.01 | ESS ERIC | ESS ERIC | 20%
4 | A20150580 | SAR for FAT & SAT | 2018.06.01 | ESS ERIC | ESS ERIC | 60%
5 | A20150610 | IRR | 2018.11.30 | ESS ERIC | ESS ERIC | 10%
Total: |  |  |  |  |  | 100%