## Slide 1: Critical design review #1 for medium beta cavity cryomodules 3-4 APRIL 2017 - Cryomodule overview, organization and development plan - Franck Peauger

## Slide 2: Medium beta cryomodules in ESS linac
Proton Beam
Medium-b and high-b elliptical cavity cryomodules
 | MEDIUM-β | HIGH-β
β | 0.67 | 0.86
# CM | 9 | 21
Cav. /CM | 4 | 4
# Cav. | 36 | 84
CM L [m] | 6.584 | 6.584
Sector L [m] | 77 | 179

## Slide 3: CEA – ESS Agreements for the Elliptical Cryomodules
Fr-Sw Agreement:
  Cooperation Agreement in the field of Neutron Accelerator Science to the ESS Design Phase, Amendment #2, 18 December 2013
    Medium-Beta Elliptical Cavity Cryomodule Technology Demonstrator (M-ECCTD)
Schedules of the In Kind Contribution Agreement
  AIK#1.1: Technical Management Scope of Work to the In-Kind Contribution Agreement signed between ESS-ERIC and CEA
  AIK#5.1 High-Beta Elliptical Cavity Cryomodule Technology Demonstrator (H-ECCTD)
  AIK#5.2 Elliptical Medium and High Beta Cryomodule Component Supply
  AIK#5.3 Elliptical Cryomodules Engineering, Assembly and Test and Technical Assistance in Cavity Design, Manufacturing and Tests
  AIK#5.5 Elliptical Cryomodules Installation and Commissioning

## Slide 4: Scope of the medium beta cryomodules activities
CEA is charge of all the prototyping activities and series production of the 9 medium beta cryomodules except:
  The design and prototyping of the cryostat (IPN Orsay)
  the production of the series medium beta cavities (INFN/LASA)
  The RF power acceptance tests of the cryomodules at ESS in Lund
The INFN/LASA proposed a new medium beta cavity design slightly different from the one developed in the prototyping phase by CEA
Activities done in two steps:
  Development of a cryomodule demonstrator M-ECCTD
  Delivery of the nine series medium beta cryomodules
 | M-ECCTD | M-SERIE
β | 0.67 | 0.67
# CM | 1 | 9
Cav. /CM | 4 | 4
# Cav. | 3 + 1 LASA + 3 spares | 36

## Slide 5: Detailed scope
For the prototype phase M-ECCTD :
  design and procurement of the cavities, couplers, tuners, magnetic shieldings (CEA)
  Design and procurement of the vacuum vessel, spaceframe, thermal shielding, cryogenic circuits (IPNO)
  Preparation and tests of the cavities and couplers (CEA)
  design and fabrication of the cryomodule assembly toolings (CEA)
  Development of the high power test stations (for couplers and cryomodules) (CEA)
  assembly and high power RF tests of the cryomodule (CEA)
For the series phase:
  CEA is responsible for:
    the procurement of the cryomodule components (except cavities)
    the clean room preparation and RF conditioning of the power couplers
    the assembly of the nine cryomodules
    the high power RF tests of the three first cryomodules at CEA
    The prepare the cryomodule for shipment to Lund
  INFN is responsible for the procurement, preparation and tests of the cavities
  IPNO is responsible for the update of the cryostat components design and drawings

## Slide 6: ESS MB Cryomodule 3D view and cross section
6.6 m long

## Slide 7: Medium beta cryomodule Main specifications
Four superconducting cavities in pure bulk niobium (RRR>250)
  Frequency: 704.42 MHz
  6 cells at b=0.67
  Beam pulse: 2.86 ms at 14 Hz
  No HOM couplers (decided at the PDR)
Accelerating gradient
  Eacc max = 16.7 MV/m, Q0 > 5.109
  Power coupler: 1.1 MW max
  External coupling: Qext = 7.5.105
Slow tuning system: ± 300 kHz
Fast tuning system (LFD) : 1+1 piezo
Cavity cooling: LHe at 2 K
Coupler cooling: SHe at 4.5 K, 3 bars
Thermal shielding cooling: LHe 50 K
Overall length: 6584 mm from flange to flange
Thermal losses (for MB):
  Static losses at 50 K: 46.2 W
  Static losses at 2 K: 13.2 W
  Dynamic losses at 2 K: 23.2 W
Pressure vessel: good engineering practice (article 4.3 of PED)

## Slide 8: Organisation chart (ESSI project level)

## Slide 9: Organisation chart (CRYOMODULE LEVEL)
Products
G. Devanz
Functions
+ CEA/DRF purchase department (« Service Commercial »)
+ CEA/DRF/IRFU/SACM Infrastructures and Safety managers

## Slide 10: Project organisation and collaborationS
ESS
CEA
IPNO
ESS Medium beta cryomodule activity
INFN
Contractual links
“short links” for technical exchanges
(with ESS and CEA always in copy)
STFC
“Observers”

## Slide 11
CRYOMODULES
Cavités
Nobium
Cavité M-beta
Cavité H-beta
RF pick up
Coupleurs
Coupleurs M-beta
Coupleurs H-beta
Doorknob
Cryostat équipé
Train de cavités (SB)
Train de cavités (hors SB)
Blindage M-beta
Blindage H-beta
SAF
Circuits cryogéniques
Écran thermique
Structure spaceframe – Ensemble
Enceinte à vide – Ensemble
Outillage
Instrumentation externe
Infrastructures et zones de test
Soufflets inter-cavité M-beta
Soufflets inter-cavité H-beta
Transitions M-beta
Transitions H-beta
Vannes vide
Instrumentation coupleurs
Instrumentation cavités
Outillage cavités
Outillage assemblage coupleurs
Outillage assemblage coupleur/cavité
Outillage assemblage cryomodule
Outillage conditionnement coupleurs
1. M-ECCTD
2. H-ECCTD
3. MBL
4. HBL
x.1.
x.2.
x.3.
x.4.
x.5.
Ex. niv. 3
x.3.1.
x.3.2.
x.3.3.
x.3.4.
x.3.5.
x.3.6.
x.3.7.
x
x.4.1.
x.4.2.
x.4.3.
x.4.4.
x.4.5.
x.2.1.
x.2.2.
x.2.3.
x.1.1.
x.1.2.
x.1.3.
x.1.4.
Ex. niv. 3
Deliverables to ESS
Product Breakdown Structure (PBS)
  6 levels in total

## Slide 12: Overall ESS cryomodule Development plan

## Slide 13: Medium beta cryomodules Development plan and reviews
Fabrication, surface preparation and test of medium beta cavities
Final assembly and high power test of the M-ECCTD
Cavity performances in a cryomodule configuration
Validation of the cryogenic circuits operation
Fabrication and test of power couplers
Assembly of a cryomodule mock-up
Procurement of cryostat components
Clean room assembly of the M-ECCTD cavity string
Development and fabrication of assembly toolings
CDR-M1
03&04/04/2017
CDR-M2
Summer 2017
Procurement of the series cryomodule components
Assembly Readiness review
First 4 MB cavities arrives 2 months later
→ March 2018 (from LASA)
CM1,2,3
SAR1
System Acceptance Review for Medium-beta pre-series components
SAR
End March 2018
System Acceptance Review for Medium-beta series components
SAR
Mars 2019
Oct. 2018
CM4,5,6
SAR1
Jan 2019
CM7,8,9
SAR1
Apr. 2019
Acceptance for shipment to Lund
Acceptance after RF test at Lund
CM1,2,3
SAR2
Dec 2018
CM4,5,6
SAR2
March 2019
CM7,8,9
SAR2
July 2019
ARR
Jan 2018

## Slide 14: Key points
Cryomodule components procurement:
  Divided in several procurement contracts adapted to the skills of the companies
Cryomodule assembly :
  Assembly rate of one cryomodule per month
  Will be performed in the former “XFEL Village” which becomes officially now the “ESS Village”
    Fully dedicated to the ESS cryomodule (no interference with other projects at Irfu)
  Will be done by an industrial partner on CEA Saclay site, under the supervision of CEA team
    Include clean room cavity string assembly, rool –out activities, alignment and cryostating (XFEL like)
    Include also power coupler clean room preparation (same clean room) (new!)
Cryomodule tests at CEA:
  Will be done on the three first series MB cryomodules only
  These tests are mandatory to have a fast feedback on the quality of the cryomodule assembly

## Slide 15: PROCUREMENT and ASSEMBLY ROADMAP
CONTRACT AWARDED
RF conditionning of the last couplers pair = CRITICAL PATH
Start of the clean room assembly of the last MB CM
INTERCAVITY BELLOWS, CRYOGENIC LINES
TUNERS, MAGNETIC SHIELDS, MLI
KLYSTRON #1
KLYSTRON #2
COUPLERS
CAVITIES
CLEAN ROOM
ROLL-OUT
CRYOSTATING
TESTS/SHIP.
THERMAL SHIELD, SPACEFRAME, INSTRUM.
SPACEF. PREP.
VAC. VESSEL, EXCHANGER, VALVE
2017
2018
2019
2020
2021
ASSEMBLY INGENIERIE
CALL FOR TENDER
PRODUCTION ASSEMBLY
M-ECCTD RF TESTS
CDR-M2
CDR-M1 = TODAY
LAST MEDIUM BETA CRYOMDULE CM#9
- CDR-M1 will give the authorization to award the main cryomodule components procurement contracts
- CDR-M2 will be mandatory to release the hold point n°2 after the pre-series fabrication and start the series components fabrication
HOLD POINTS n°2 AFTER PRE-SERIES PROCUREMENT

## Slide 16: Conclusion
Cryomodule scope and development plan well defined
Organization in place and structured within the ESSI project and within an international collaboration
Procurement process anticipated and fully optimized to limit technical risks and to “fine-tune” the cryomodule delivery schedule

## Slide 17
Thank you
Commissariat à l’énergie atomique et aux énergies alternatives
Centre de Saclay | 91191 Gif-sur-Yvette Cedex
T. +33 (0)1 69 08 76 11 | F. +33 (0)1 69 08 30 24
Etablissement public à caractère industriel et commercial | RCS Paris B 775 685 019

## Slide 18: Organisation: meetings
ESSI Project meeting
  with all the workpackage + CEA purchase department
  Every month (Thursday morning)
ESS cryomodules meeting:
  with all the workpackage + CEA purchase department
  Every month (Thursday morning)
Non-conformity/modification meeting:
  Internal meeting at CEA with workpackage leaders, Quality team and system engineer
  Tuesday afternoon every 2 weeks
Infrastructures meeting:
  Internal meeting at CEA with infrastructures leaders and other project leaders
  Agree on short term schedule for chemical treatment, clean rooms, testing activities
  Every Friday afternoon
SRF meeting :
  Visio
  ESS / CEA / INFN / STFC
  every Friday morning
Interface meeting:
  Visio
  ESS / CEA / IPNO
  Every Tuesday afternoon
SRF collaboration meeting
  ESS / CEA / INFN / STFC
  every 3 months
Organized by ESS
Internal CEA meetings