## Slide 1: Status of ESS
Mats Lindroos
Head of Accelerator
Adjungated Professor at Lund University, Physics department
and the ESS Accelerator Collaboration
www.europeanspallationsource.se
June 2017

## Slide 2: Neutrons & x-rays: similar methods, sensitive to different elements.

## Slide 3
Neutrons are beautiful!
Wave
Magnetic moment
Particle
Neutral
Diffractometers - Measure structures
– Where atoms and molecules are
Spectrometers - Measure dynamics
– What atoms and molecules do

## Slide 4: ESS design
High Power
Linear Accelerator:
Energy: 2 GeV
Rep. Rate: 14 Hz
Current: 62.5 mA
16 Instruments in Construction budget
Committed to deliver 22 instruments by 2028
Peak flux ~30-100 brighter than the ILL
Target Station:
He-gas cooled rotating
W-target (5MW average
power)
42 beam ports
Ion Source
Total cost: 1843 MEuros 2013

## Slide 5
Neutron facilities
ISIS
ILL
Effective thermal neutron flux n/cm2-s
FRM-II
SNS
J-PARC
LANSCE
NIST
Year
ESS
Chart: 
| 1968.0 | 1970.0 | 1986.0 | 1989.0 | 2003.0 | 2008.0 | 2009.0 | 2025.0
 | 0.72 | 4.44 | 2 | 7 | 0.72 | 28 | 43 | 268
Reactor sources
Accelerator-driven sources
CSNS
Notes: CP-1 Chicago USA
CP-2 Chicago USA
X-10: Oak Ridge, USA
NRX: Chalk River, USA
MTR: Idaho, USA
LVR: Rez, Czech Republic
HIFAR: Sydney Australia
NRU: Chalk River, USA
HOR Delft Netherlands
SAFARI-1 Pretoria South Africa
HFBR: Brookhaven, USA
HFIR: ORNL, Oak Ridge, USA
NIST: National Inst. for Stds and Tech. Gaithersburg, USA
ILL: Grenoble, France
JEEP II Kjeller Norway
MARIA Swierk Poland
ORPHEE LLB Saclay France
Dhruva: Mumbai, India
RSG: serpong, Indonesia
SINQ: PSI, Switzerland
JRR-3: Tokai, Japan
ES-Salam Algiers Algeria
HANARO: Daejon KAERI, South Chorea
ETERR-2 Cairo Egypt
FRM-II: Munich, Germany
OPAL: Sydney, Australia
CARR: Beijing China
PIK: Gatchina, Russia
ZING-P Argonne USA
WNR Los Alamos USA
KENS Tsukuba Japan
IPNS Argonne USA
IBR-II Dubna Russia
LANSCE Los Alamos USA
ISIS Oxfordshire UK
SNS Oak Ridge USA
JPARC Tokai Japan
CSNS Beijing China
ESS Lund Sweden
More reactor sources exist across the world….

## Slide 6
April 2017
Klystron Gallery
Cryo Compressor
Building
Central Utility
Building
Distribution
Substation
Primary
Substation
Target
Monolith
Exp. Hall
E01
Active
Cells
Front End
Building
High Energy
Loading Bay

## Slide 7: Linac tunnel
Tunnel, view from HEBT
Front End Building

## Slide 8: Cryo Compressor Building

## Slide 9: Target Monolith & Active Cells

## Slide 10: Organisation and People
401
Employees
48
Nationalities
> 45
Collaborating Institutions

## Slide 11
Total Funding (Cumulative)
Total Baseline Budget incl. Contingency (Cumulative)
Total Baseline Budget excl. Contingency (Cumulative)
Total Earned Value (Cumulative)
Total Actual Cost (Cumulative)
Machine Ready for Beam on Target
 Start of user programme
 Construction
Starts
 First installations
(of Machine Systems)
Construction funding & budget profile
M€

## Slide 12: ESS linac
  Average beam power of 5 MW
  Peak beam power of 125 MW
  Acceleration to 2 GeV
  Peak proton beam current of 62.5 mA
  Pulse length of 2.86 ms at a rate of 14 Hz (4% duty factor)
96% of acceleration will be provided by superconducting cavities supplied by 150 high power RF sources (one per cavity):
  80% of the RF power sources delivering over 1.1 MW of peak RF power
  The RF system is the cost driver for the ESS accelerator.
    Low losses
    Minimimum energy use & energy recovery
    Flexibility for
    mitigation or upgrade

## Slide 13: Accelerator components benefit from expert competencies all across Europe
Spokes
Medium β
High β
DTL
MEBT
RFQ
LEBT
Source
HEBT & Contingency
Target
2.4 m
4.6 m
3.8 m
39 m
56 m
77 m
179 m
75 keV
3.6 MeV
90 MeV
216 MeV
571 MeV
2000 MeV
352.21 MHz
704.42 MHz

## Slide 14: Accelerator components benefit from expert competencies all across Europe
Concept, courtesy of GRE (UK)

## Slide 15: Test Stands 1, 2 in Lund and FREIA in Uppsala – Hands-on work has begun!

## Slide 16: Accelerator cryoplant being completed

## Slide 17: Ion source in Catania at nominal parameters

## Slide 18: Beam Instrumentation Commissioning in Catania – Emittance Measurement
In-kind from CEA Saclay
Commissioned in January 2017
Evolution of the beam emittance along the pulse (values every 5 s)
Beam transverse emittance reconstruction after data post processing
Emittance Measurement Unit installed in Catania

## Slide 19: MEBT design and fabrication are in progress
Buncher Cavity Production
and Heat Treatment
THPIK082 Quadrupole Magnet Design for the ESS MEBT
(D. Fernandez-Canoto – ESS Bilbao)
Strip Line Chopper Tests Complete

## Slide 20: DTL recent achievements
5 tanks
Tank 4: forged 304 L stainless steel
Drift tube
prototypes
DTL design work at ESS and in Legnaro, 3.6 ->90 MeV.
[Picture from CERN Linac4]

## Slide 21: Spoke Cavities design & prototype performances
Spoke cavity prototype test results (Jan15 – Feb16):
Excellent performances, well within specifications (both on Eacc & Qo)
Pcav<0.5W
Ultra pure water
high pressure rinsing
Chemical etching
THOBB3 ESS SRF Linear Accelerator Components Preliminary Results and Integration (C. Darve (ESS)
MOPVA090 ESS Superconducting RF Collaboration (C. Darve – ESS)
Cryomodule with 2 cavities

## Slide 22
The INFN LASA cavity was successfully tested @ 2 K, exceeding the ESS specifications.
Soft Multipacting barrier
A soft MP barrier was easily conditioned.
This barrier matches with simulations.
HOM near 5th machine line
f = 1741.8 MHz (> 19 MHz from machine line)
Df < 1 MHz from simulations (f =1742.4 MHz).
100 W CW cryo power, i.e. 16.7 MV/m @ Q0 5 109
Power Rise @ 2 K
Elliptical Cavities Highlights

## Slide 23: Cleanroom, RF Station, Assembly hall, Test Stand are ready in Saclay
RF station: Power-coupler conditioning
    Re-use the current infrastructure of XFEL
First Medium b String in CEA Saclay Cleanroom
Notes:     Assembly room in Saclay
    Uses the current infrastructure of XFEL
    Benefits from the experience of the XFEL cryomodule assembly (ALSYOM)

## Slide 24
SML modulator topology successfully demonstrated on 120 kVA prototype
Order of 3 units for NC linac by ESS-Bilbao
On-going ESS tender for 9 units for MB linac
Integrated oil spill bin
All in one frame with permanently mounted wheels for easy transportation
Total footprint: 3.8m x 1.4m
(planned was 5.5m x 1.6m, i.e. 40% less);
Total weight: < 4 tons (without oil);
Total volume of oil: ~ 2200 litters;

## Slide 25: Klystrons and MB-IOT prototypes
Klystron Prototypes (resp. CPI, Thales and Toshiba)
Thales/CPI IOT
L3 IOT
Height: 3.8 m 4.5 m 3.5 m
THPIK084 Results from the
704 MHz Klystron and
Multi-Beam IOT Prototypes
For the European Spallation
Source (M. Jensen – ESS)

## Slide 26: Beam raster scanning on target
5:4 pattern
Raster system sweeping beam in 2D pattern @ target
8 colinear magnets, individually powered
Crosshatch pattern (fx/fy, ϕxy, ax, ay) within 2.86 ms pulse

## Slide 27: Accelerator schedule
2016
2017
2018
2019
2020
2021
2022
RF
NCFE
Cryogenics
Spoke & Elliptical
cavities and cryomodules
CDS INSTALLATION
STARTS
ACCELERATOR
CRYOPLANT
COMM./READY
Commissioning
SPOKE CM
TESTING STARTS
START RFQ MACHINING
SPOKE & MB CM
PRODUCTION
LAUNCHED
DECISION IOT OR
KLYSTRON FOR HB LINAC
1370 MeV PROTONS
AVAILABLE
RF SYSTEM
FOR MB
READY
2 GeV PROTONS AVAILABLE
SC LINAC
570 MeV
READY
SC LINAC
2 GeV
READY
FIRST PROTONS ON TARGET
TECHNICAL STOP
TECHNICAL STOP
BEAM COMM. COMPLETED FOR NCFE but DTL5
BEAM COMM. COMPLETED FOR ISRC-> MEBT
TOSHIBA/CPI/THALES KLYSTRON
PROTOTYPE DELIVERED
CPI/THALES AND L3 IOT
PROTOTYPES DELIVERED
MB CM
TESTING STARTS
START RFQ COMMISIONING
1-11 HB CM INSTALLED
12-21 HB CM INSTALLED
CDS COMMISSIONED
RFI ISRC & LEBT
RFI
RFQ
RFI
MEBT
RFI
DTL5

## Slide 28: EV Graph
Current Status
Cost Variance has by end of Apr remained at -2.1 M€ ( same as in Mar).
Main negative contributors to the CV are: Power converters, Beam Diagnostics, Beam Delivery and Cooling Support
Schedule variance has slipped to -24.2 M€ dominated by delays at IK partners
Main negative contributors to the SV are: Vacuum, Power Converters, Cooling Support, NCFE, RF Systems, Spoke Cavities & Cryomodules and Beam Diagnostics.
(* No InKind included)

## Slide 29: Accelerator Division (AD) – Site Organization
Task masters (Installation Support Team)
AREAS
Accelerator Installation Manager
Nick Gazis
AD and ESS central Installation Services (ISC workgroup, etc.)
RATS AreaSuper hiring process
Inst-Test-Commis. Plan (MS Project) Eugene Tanke
QA/QC Kent Wigren
Mechanical
Mechanical
Mechanical
Safety Team Duy Phan Area Supervisors and ES&H
Area Supervisor Tunnel (G01) & FEB (levels 090 & 100) Dennis de Wit
Area Supervisor Gallery (G02 incl.Test Stand 2) Marcus Green
Electrical
Utilities
Electrical
Utilities
Area Supervisor Cryobuildings (G04) Ila Sjoholm
Electrical
Utilities
BAS-U framework
ESS management
mech
util
other..
System Leader 2
other
Other..
System Leader 3, 4..
el
RF
other..
System Leader 1
Indeed everyone is responsible for safety

## Slide 30: Installation, Testing and Commissioning
The ESS Accelerator sub-project today has access to the cryo-buildings, test stand area and tunnel
Blue lining and drilling is now starting in the tunnel for the NCFE
Stub installation (RF transfer from gallery to tunnel) has proven very challenging but we are now starting a test installation and we are maintaining the installation schedule
We are seeing delays from several IK partners for the equipment “Ready For Installation” dates
  Technical delays of up to 3 month
  Administrative delays of 6-9 months
We are working on a new ITC schedule which resources will permit us to install efficiently the equipment as we receive it with the ambition of running parts of the linac in 2019
Note that it is crucial that delays in some areas isn’t used as an excuse to be late in other areas
We urge IK partners to let us know about possible delays or deviations for deliveries as early as possible so that we can work with them to mitigate the effects.

## Slide 31: Conclusions
Thanks to all ESS Accelerator IK partners for all the hard work to set-up contracts, get work started and for maintaining the high tempo required by the Project schedule
Collaboration has enabled ESS to get construction under way at a green field site while building up an organization for installing, commissioning and operating the facility
Working together we can do what might seem as impossible

## Slide 32: Many thanks to all my colleagues in the ESS accelerator collaboration Thank you for listening!
Thanks to all my colleagues at ESS!
Together we are building ESS

## Slide 34: ESS: The worlds first long pulse source
4
8
time (ms)
Brightness (n/cm2/s/sr/Å)
7
5
x1014
UK TS1
128 kW
UK TS2
32 kW
SNS
1-2 MW
JPARC
0.3-1 MW
ILL 57 MW
ESS 5 MW
2015 design
0
1
2
3
3
4
1
2
6
λ = 1.5 Å
ESS 5 MW
2012 design (TDR)
Possibilities of pulse shaping

## Slide 35: Neutron Imaging - Examples

## Slide 36: Några visioner för neutronanläggningar och synkrotronljusanläggningar
Higher (Room?) Temperature Super Conductors
Hydrogen storage substrate
Efficient membrane for fuel cells
Flexible and highly efficient solar cells
Understanding liquid membranes
Nano scaled structures for controlled drug release
Self healing materials – smart materials
Spintronics - Spin-state as a storage of data (1023 gain in capacity)
CO2 sequestration
Neutron electric dipole moment
Neutron oscillations
And much more…