## Slide 1: Ion source and LEBT installation at ESS Øystein Midttun – University of Bergen Ion source and LEBT system leader
www.europeanspallationsource.se
SLHiPP-7 – 8 June 2017

## Slide 2: ESS accelerator tunnel – March 2017

## Slide 3: The ion source and LEBT is made though a partnership between INFN-LNS, ESS, and CEA
WP leader
Overall design
Construction
Commissioning
Installation
Controls
Beam diagnostic
Vacuum
Controls
Beam diagnostic

## Slide 4: This presentation describes what we will install, where and when, and how we are preparing
Ion source and LEBT
Accelerator tunnel
How are we preparing?

## Slide 5: The ESS proton source is a microwave discharge ion source
Waveguide
Solenoid magnets
Plasma chamber
Gas injection
High voltage insulator
Extraction electrodes
Pumping ports
50 cm

## Slide 6: The plasma generator sits inside a 75 kV high voltage platform

## Slide 7: The Low Energy Beam Transport (LEBT) matches the beam to the RFQ input
Proton source
– creates the beam
Iris
– controls the current
Chopper and collimator
– controls the pulse length
Solenoid
– focuses the beam

## Slide 8: LEBT as installed in Catania – June 2017

## Slide 9: The ion source and LEBT will be the first accelerator components installed in the tunnel
Ion source and LEBT
Accelerator tunnel
How are we preparing?

## Slide 10: The location of the ion source is in the accelerator tunnel furthest from the target
Target Station
Ion Source and LEBT

## Slide 11: The ESS Survey Alignment Metrology Group provides Truview to visualize the installation environment: https://truview.esss.lu.se/

## Slide 12: The ion source and LEBT will be installed in November 2017
Installation
(INFN-LNS)
Commissioning
3 weeks
for installation, and
9 weeks
for commissioning
is (very) short
In addition comes:
Installation readiness review
Accelerator readiness review
INFN-LNS will bring a team of 5-6 persons (technicians + coordinators) for the installation

## Slide 13: Good preparation at the ESS site is needed for making the installation according to the schedule
Ion source and LEBT
Accelerator tunnel
How are we preparing?

## Slide 14: ESS Accelerator Division’s site organization for the installation
Task masters (Installation Support Team)
AREAS
mech
util
other..
System Leader 2
other
Other..
System Leader 3, 4..
el
RF
other..
System Leader 1
Accelerator Installation Manager
Nick Gazis
AD and ESS central Installation Services (ISC workgroup, etc.)
RATS AreaSuper hiring process
Inst-Test-Commis. Plan underway in P6
QA/QC Kent Wigren
Mechanical
Mechanical
Mechanical
Safety Team Duy Phan Area Supervisors Skanska and ES&H
Area Supervisor Tunnel (G01) & FEB (levels 090 & 100) Dennis de Wit
Area Supervisor Gallery (G02 incl.Test Stand 2) Marcus Green
Electrical
Utilities
Electrical
Utilities
Area Supervisor Cryobuildings (G04) Ila Sjoholm
Electrical
Utilities
Indeed everyone is responsible for safety

## Slide 15: The Work and Safety Coordination Plan lists the preparatory measures prior to the installation
Courtesy of: D. Phan, ESS AD Safety Group
Part 1: Work Coordination Plan
GENERAL INFORMATION
ESS-0085649
Working hours
Duration of the activity
Contact persons
Contractor information
Regulatory framework & applicable documentation
PREPATORY MEASURES
Pre-work visits
Organizational measures (e.g. storage, waste management, equipment/machines, etc.)
Provision of services by ESS (e.g. electricity, water, staff, equipment/machines, safety measures, hot desks, toilets, changing rooms, etc.)
Provisions of safety measures by ESS (e.g. lock-out/tag-out, signage, etc.)
Description of the work to be done and/or systems to be installed

## Slide 16: The WSCP lists associated hazards and safety control measures foreseen
Courtesy of: D. Phan, ESS AD Safety Group
Part 2: Safety Coordination Plan
HAZARD IDENTIFICATION AND CONTROL MEASURES
ESS-0085649
Area Hazard Analysis (AHA)
Job Hazard Analysis (JHA)
Parallel works
Control documents (e.g. fire permit, work authorization, lock-out/tag-out permit, permit for the use of lifting equipment, etc.)
INFORMATION AND TRAINING
List of mandatory safety trainings and awareness (see Skanska matrix)
Minimum number of first aiders required (1 per working team)
Site map
Reporting in case of an incident
Accident/incident reporting form

## Slide 17: The ESS site follows rules of a construction site
Welcome to a Safe workplace!
Register before entering site
Wear helmet
Wear safety goggles
Wear gloves
Wear safety boots
Wear high visibility clothing
ID 06 visible
Unauthorized may not enter
Do not forget long trousers
Notes: Compulsory

## Slide 18: This may conflict with the standards of installation of equipment in a laboratory
Keep the environment clean
No dust around vacuum installations
No drilling of holes etc.
Wear plastic gloves
Protective equipment is not very practical for all tasks
Images from the installation at INFN-LNS

## Slide 19: Example of challenge: tunnel roof height is 3.5 meters, and there is no crane installed
~ 2000 kg
~ 2000 kg

## Slide 20: Below the drop hatch: Install the ion source and LEBT on a support frame

## Slide 21: Below the drop hatch: Mount the ceramic insulators

## Slide 22: Wit the drop hatch crane: Lower the high voltage platform onto the insulators

## Slide 23: Below the drop hatch: Mount the LEBT support on the support frame

## Slide 24: Inside the tunnel on the beam axis: Install the feet for the support frame

## Slide 25: Bring the assembly on the feet using wheels (not represented), and align

## Slide 26: Install the 1st LEBT component with the extraction column, and align

## Slide 27: Mount the extraction column with the high voltage insulator

## Slide 28: Attach the plasma chamber, and verify the alignment

## Slide 29: Install the coils on the support, and slide the assembly in place

## Slide 30: Install the wave guide from the magnetron to the plasma chamber

## Slide 31: Install and align the commissioning tank that will be used to characterize the beam at the RFQ entrance

## Slide 32: Install and align the permanent tank with instruments in place (because of the tunnel height)

## Slide 33: Install and align the LEBT solenoids

## Slide 34: Install the beam pipe inside the 1st solenoid

## Slide 35: Install and align the iris

## Slide 36: Install the beam pipe inside the 2nd solenoid

## Slide 37: Install the collimator between the 2nd solenoid and the commissioning tank

## Slide 38: Install the ground shielding plate

## Slide 39: The work finishes by installing and connecting ancillary equipment (not exhaustive list)
Cooling water
Fiber optics
HV power
Controls power
Ground connections
High voltage
protection cage
H2 gas delivery
Vacuum
Cables, power, water cooling, compressed air, drilled holes, etc. needs to be in place before the installation starts!
Diagnostics

## Slide 40: We are preparing for the installation of the ion source and LEBT in November 2017
The ion source and LEBT
are already installed
In Catania, and will be commissioned before shipment to Lund
A team from INFN-LNS will make the installation at ESS
We will together use the experience from Catania for planning the installation activities at ESS