## Slide 1
Test Stand Installation:
Cryomodule test stand at ESS site
7th Open Collaboration Meeting on Superconducting Linacs for High Power Proton Beams (SLHiPP-7)
Emilio Asensi, Test Stand Engineer
www.europeanspallationsource.se
2017-06-09

## Slide 2: Contents
Test Stands at ESS
Cryomodule test stand (TS2)
  Organisation
  Schedule
  RP Bunker
  RF Equipment
  Cryogenic Distribution System
  Electricity and Water
  Cryomodule installation and handling
Summary

## Slide 3: WP10 – Test Stands
The ACCSYS work package 10 covers the test stands for main accelerator components in Uppsala and in Lund.
Test Stand 1 concerns the main RF equipment prototype soak tests (Uppsala).
Test Stand 2 (TS2) concerns the Site Acceptance Tests (SAT) of the series production cryomodules (elliptical cavities).
Uppsala test stand FREIA tests the spoke cavities and the spoke cavity cryomodule series SAT.
Other ESS Test Stands
RF Lab Lund concerns the testing of a new design modulator prototype (LTH).
Test Stand 3 concerns the SAT of the modulator series.
Testing at TS2 includes:
  Reception & preparation
  Couplers (re)conditioning
  Cool down
  RF tests up to full power
  Heat load tests
  Warm up & prepping for installation

## Slide 4: Collaboration
ESS ACCSYS-WP
ESS Divisions
In-Kind Institutes
Industrial partners

## Slide 5: Schedule
 | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Partial access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Full access |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Utilities available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RF inst. and comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cabling inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Controls comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bunker inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TL and Cryo inst. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PSS inst. and comm. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MB-ECCTD CM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MB-Series CM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IFJ PAN: Preparations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation in 2017 with first tests of medium beta cryomodules in 2018,
high beta cryomodules to be tested starting middle 2019.
 | 2018 |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
MB-ECCTD installation |  |  |  |  |  |  |  |  |  |  |  | 
MB-ECCTD commissioning |  |  |  |  |  |  |  |  |  |  |  | 
MB-ECCTD testing |  |  |  |  |  |  |  |  |  |  |  | 
MB CM 1 installation |  |  |  |  |  |  |  |  |  |  |  | 
MB CM 1 testing and SERIES |  |  |  |  |  |  |  |  |  |  |  | 
IFJ PAN: commissioning |  |  |  |  |  |  |  |  |  |  |  | 
IFJ PAN: phase 1 starts (testing medium beta CMs) |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6
Test Stand 2 occupies 45 m in the high energy end of the klystron gallery, in the Gallery Technical Area (cont. space).
W. Hees
Test Stand 2

## Slide 7: Layout
It consists of a bunker, a preparation area, an area for RF equipment and a control room.
High power RF
equipment
Test bunker
Cryogenics and
Test Stand Control room
Preparation
Area
Cryo Transfer Line

## Slide 8: RP Bunker
Total dose rate mSv/h
10 μSv/h
L. Tchelidze & M. Jarosz
The main function of the bunker is to protect the surrounding area from x-rays produced during the cryomodule tests. It consists of 1200 t of heavy, magnetite loaded concrete, arranged to form 1 m thick walls all around the cryomodule.

## Slide 9: RF Systems

## Slide 10: RF Systems
Two 1.5 MW, 704 MHz pulsed power klystrons are already installed in TS2, one coming from Thales and the other from CPI.
RFDS equipment like waveguides and circulators have also been delivered and are waiting to be installed.

## Slide 11: Cryogenic Distribution System
Interface to TICP
1
2
3
Interface to cryomodule
1. Test Stand Valve Box
2. CTL housing 4 cold process lines
  Helium supply line
  VLP line
  TS supply line
  TS return line
3. Auxiliary process lines
  HP line
  Purge return line
  Helium recovery line
  SV relief line
J. Fydrych

## Slide 12: Cryogenic Distribution System
J. Fydrych

## Slide 13: Cooling Water
Cooling water at 25’C is provided for one 330 kVA modulator and two RF stations, also for the RF couplers of the CM.
TS2 includes a separate water skid to prevent propagation in case of irradiated water.
The cooling system will run at low pressure due to the allowable pressure of the RF couplers.

## Slide 14: Electricity
TS2 includes 24 electrical racks for multiple uses, including:
RF data acquisition systems
Vacuum and Cryogenics instrumentation
Machine protection
Safety systems
Expansion modules
Cable trays and ladders are placed on top of the electrical racks and through the waveguides and water support to accommodate the power cables from the substation and the data cables from the cryomodule and installation instrumentation.

## Slide 15: Cryomodule
Installation and Handling
Courtesy of IPNO and FREIA
F. Schlander
Cryomodule transport trolley
Truck transport frame

## Slide 16: Summary: Cryomodule workflow
Saclay
Lund

## Slide 17: Summary: Cryomodule workflow
 | MEDIUM-β | HIGH-β
β | 0.67 | 0.86
# CM | 9 | 21
Cav. /CM | 4 | 4
# Cav. | 36 | 84
CM L [m] | 6.584 | 6.584
Sector L [m] | 77 | 179
Proton Beam
Elliptical cavities Cryomodules
Medium-b and high-b
Klystron gallery
P.Bosland, C.Darve

## Slide 18: Thank you!

## Slide 20: Installation and Handling
Order placed for dedicated truck for safe maneuvering, aligning and height adjustment.
Delivery expected in June 2017
Klystron and equipment Delivery Access:
Two 5x5 m doors in cold box building with overhead crane
3x5 m door between Klystron assembly area and RF gallery
M. Jensen
RF Systems

## Slide 21: Cryogenic Distribution System
J. Fydrych

## Slide 22: Cryogenic Distribution System
J. Fydrych

## Slide 23: Test Plans overview
Reception:
  Inspection for damage, obvious manufacturing errors and completeness of delivery
Preparation for test bench:
  Preparation for installation on test bench, including adjustments as well as mounting and dismounting of parts (door knobs, beam vacuum pumps, insulation vacuum pump)
Installation on test bench:
  Moving into the bunker
  Alignment of the cryo jumper connection
  Connection of flanges
  Waveguide connections, cabling connections, coupler cooling connections
Initial testing:
  Diagnostic test, showing status of insulation vacuum, leak tightness of helium circuits, integrity of electrical circuits, proper functioning of instrumentation
Warm RF tests:
  Fundamental mode spectra measurements
  Cable calibration
Warm coupler conditioning:
  Monitoring and pumping of the beam vacuum
  Coupler conditioning, using ramped RF power
Cool down:
  System checking to assure it is purged and clean
  Cool down following a predetermined ramp
  Maintain cold He flow to assure operating temperature of cavities
Cold LP cavity tests:
  piezo capacitance measurement (before and during cooldown)
  microphonics measurement
  piezo scans (cavity detuning transfer function)
  4π/5 and 3π/5 mode identification
  cavity tuner motor characterization
  cavity loaded Q motor characterization
  Lorentz force detuning compensation
  closed-loop nominal gradient operation
Cold HP RF tests:
  loaded Q measurements and adjustment
  cavity gradient calibration
  cavity gradient performance measurement
Heat load measurements:
  Measuring heat loads at different operating conditions
Warm up:
  Warm up
Disconnection:
  Opening cryo connections
  Disconnecting waveguides, cabling, coupler cooling, vacuum pump
  Extraction from the bunker
Preparation for tunnel
  Preparing for transport to tunnel and installation.
Testing of CMs includes a number of preparatory steps, the testing itself and a number of post-processing steps. This list of tasks is preliminary and will be expanded: