## Slide 1: Work Unit 11.11.5.3 - AIK 11.2 CDR of the CDS-SL Procurements
April 20th 2017

## Slide 2: Purchasing
The purchasing of a product or a service is based on the following document (see Project Quality Plan):
  1- A technical specification is written by the CNRS defining:
    the requirements and quality characteristics of the product or of the service
    the methods to measure or to validate those characteristics (including specific tests and quality controls)
    Requirements are in accordance with those defined with ESS
    This specification also indicates, when applicable, the codes and standards which are to be implemented by the sub-contractor to supply or manufacture the product or to execute the service (see section Annexe I).
    A schedule is included in this specification defining some milestones, check points or delivery dates to conform to the schedule of the in-kind contribution.

## Slide 3: Purchasing
The purchasing of a product or a service is based on the following document:
  2- An administrative specification is written by the CNRS defining:
    the legal conditions of tendering and of executing the contract
    it might includes (this can be included in the technical specification) elements of Project Quality Plan such as:
      the organization of the sub-contractor with respect to the contract execution (resources, communication, quality);
      the identification and traceability;
      the control documents, the control of nonconformities.
NB: this administrative specification can be compiled with the technical specification described in the previous paragraph to form a unique general specification. Or it can be a separate document.
The procurement phase (call for tender) is set according to the European regulations for public procurement and this(ose) specification(s) is (are) published.
Selection of the sub-contractor is based on the compliance of the supplier’s offer with the specification(s) written by the CNRS.

## Slide 4: Technical specification
Contents
  I Presentation of the ESS context (machine, consortium…) and of CNRS
  II Description of the needs (product or service, functionality requirements, operating conditions…)
  III Description of the supply (quantity, complementary products, options…)
  IV Description of the complete supply (related products or services, controls, documentation …)
  V Schedule
  VI Technical conditions for tendering
  VII Technical requirements
  VIII Qualification, controls and tests
  IX Acceptance and waranty (Acceptance tests, milestones, deliveries…)
  X Quality management (Quality plan, non conformities, visits and audits…)
  XI General conditions to the procurement execution (follow up organization, sub contractors…)
  XII Applicable standards

## Slide 5: Technical specification
Needs, schedule and technical requirements complies with:
  Requirement list
  ESS Schedule annex to the AIK
Quality control during manufacturing phase:
Controls
& Tests
Factory acceptance test
Site acceptance test
Visual inspection
Leak test
Dimensional control
Documentation check
Etc.
Factory acceptance test report
Site acceptance test report
manufacturer
manufacturer & CNRS
CNRS
Ready for assembly
Manufacturing operation
Responsibility
Control types
Traceability of controls and acceptance
Visual inspection
Leak test
Dimensional control
Etc.
Manufacturer folder (tests & controls reports, etc.)
According to the CNRS technical specifications and the validation of the quality plan of the manufacturer
CEA
Manufacturer
CEA
Manufacturer
Manufacturer
(After ESS Acceptance – System Acceptance Review)
Source:
A. Bruniquel, WP5 CDR

## Slide 6: STANDARDS
WP11 applicable standards (See PQP)
Quality management
ISO 9000 (2015) Quality management systems – Fundamentals and vocabulary.
ISO 9001 (2015) Quality management systems – Requirements.
ISO 10005 Quality management systems – Guidelines for quality plans.
ISO 10007 Quality Management Systems – Guidelines for configuration management
ISO 10013 Guidelines for quality management system docuementation
Pressure vessels, cryogenic equipment
2014/68/UE Directive 2014/68/EU of the European Parliament and of the Council of 15 May 2014 on the harmonisation of the laws of the Member States relating to the making available on the market of pressure equipment.
EN 13445 Unfired pressure vessels – Parts 1 to 5.
EN 13458 Cryogenic vessels - Static vacuum insulated vessels - Parts 1 to 8.
EN 13480 Metallic industrial piping - Parts 1 to 8.
Design drawing
EN ISO 1101 Geometrical product specifications (GPS) - Geometrical tolerancing - Tolerances of form, orientation, location and run-out.
EN ISO 5459 Geometrical product specifications (GPS) - Geometrical tolerancing - Datums and datum systems.
EN 22768 (ISO 2768) General tolerances - Parts 1 and 2.

## Slide 7: STANDARDS
  WP11 Standards (See PQP)
Materials
EN 485 Aluminium and aluminium alloys - Sheet, strip and plate - Parts 1 and 2.
EN 573 Aluminium and aluminium alloys - Chemical composition and form of wrought products - Parts 1 and 3.
EN 1252-2 Cryogenic vessels - Materials - Part 2: Toughness requirements for temperatures below -80 °C.
EN 10222-5 Steel forgings for pressure purposes - Part 5: Martensitic, austenitic and austenitic-ferritic stainless steels.
EN 10225 Hot rolled products of structural steels - Parts 1, 2 and 5.
EN 10028 Flat products made of steels for pressure purposes – Parts 1 to 7.
EN 10088 Stainless steels - Parts 1 to 5.
EN 10204 Metallic products - Types of inspection documents.
EN 10216-5 Seamless steel tubes for pressure purposes - Technical delivery conditions - Part 5: stainless steel tubes.
EN 10217-7 Welded steel tubes for pressure purposes - Technical delivery conditions - Part 7: stainless steel tubes.
Welding and brasing
EN ISO 3834 Quality requirements for fusion welding of metallic materials - Part 1, 3 and 5.
EN ISO 9606 Qualification testing of welders - Fusion welding - Parts 1, 2, 3 and 5.
EN 14732 Welding personnel - Qualification testing of welding operators and weld setters for mechanized and automatic welding of metallic materials.
EN ISO 15607 Specification and qualification of welding procedures for metallic materials - General rules.
EN 15614-1 Specification and qualification of welding procedures for metallic materials - Welding procedure test - Parts 1, 2, 5 and 6.
EN ISO 13585 Brazing - Qualification test of brazers and brazing operators.
EN 13134 Brazing - Procedure approval.

## Slide 8: STANDARDS
WP11 Standards (See PQP)
Manufacturing
EN ISO 898 Mechanical properties of fasteners made of carbon steel and alloy steel – Parts 1 and 2.
EN ISO 3506 Mechanical properties of corrosion-resistant stainless steel fasteners - Parts 1 to 4.
EN ISO 3669 Vacuum technology - Bakable flanges – Dimensions.
EN ISO 4014 Hexagon head bolts - Product grades A and B.
EN ISO 4017 Fasteners - Hexagon head screws - Product grades A and B.
EN ISO 4287 Geometrical Product Specification (GPS) - Surface texture: Profile method - Terms, definitions and surface texture parameters.
EN ISO 8735 Parallel pins with internal thread, of hardened steel or martensitic stainless steel
EN 12300 Cryogenic vessels - Cleanliness for cryogenic service.
EN 14917 Metal bellows expansion joints for pressure applications.
EN 28839 Mechanical properties of fasteners - Bolts, screws, studs and nuts made of non-ferrous metals
EN 60534 Industrial Process Control Valves – Parts 1 to 9.
ASTM A380 Practice for cleaning, descaling and passivating of stainless steel parts, equipment and systems.

## Slide 9: STANDARDS
WP11 Standards (See PQP)
Tests and controls
EN 1779 Non-destructive testing - Leak testing - Criteria for method and technique selection.
EN 3452 Non-destructive testing - Penetrant testing – Parts 1, 2 and 4 .
ISO 3530 Vacuum technology. Mass-spectrometer-type leak-detector calibration.
ISO 5817 Welding - Fusion-welded joints in steel, nickel, titanium and their alloys (beam welding excluded) - Quality levels for imperfections.
ISO 9712 Non-destructive testing - Qualification et certification of NDT personnel.
EN 10042 Welding - Arc-welded joints in aluminium and its alloys - Quality levels for imperfections.
EN 10204 Metallic products - Types of inspection documents.
EN 12799 Brazing - Non-destructive examination of brazed joints.
EN 13185 Non-destructive testing - Leak testing – Tracer gas method.
EN ISO 17635 Non-destructive testing of welds - General rules for metallic materials.
EN ISO 17636 Non-destructive testing of welds - Radiographic testing - Parts 1 and 2.
EN ISO 17637 Non-destructive testing of welds - Visual testing of fusion-welded.

## Slide 10: STANDARDS
WP11 Standards (See PQP)
Handling
EN ISO 3266 Forged steel eyebolts grade 4 for general lifting purposes.
Instrumentation and sensors
JCGM 200(ISO/CEI Guide 99) International vocabulary of metrology - Basic and general concepts and associated terms (VIM).
CEI UNI ENV 13005 Guide to the expression of the uncertainty in measurement.
ISO 5725 Accuracy (trueness and precision) of measurement methods and results – Parts 1 to 6.
EN ISO 10012 Measurement management systems - Requirements for measurement processes and measuring equipment.
EN ISO 10012 Measurement management systems - Requirements for measurement processes and measuring equipment.
FD X 07-011 Constat de vérification des moyens de mesure.
FD X 07-012 Certificat d’étalonnage des moyens de mesure.
FD X 07-028 Métrologie - Procédure d’étalonnage et de vérification des thermomètres - Estimation des incertitudes sur les mesures de température.

## Slide 11: Procurements
Procurement strategy
  Objective: to save time !
HU03
HU02
End box
VB01
VB02
VB03
VB13
Interface with the CDS-EL
Beam direction
HU-EL
HU01
HU13
1x End box
13x valve box
13x (standard) Headers Unit
1x Elliptic interfaced Headers Unit
 1 call for tenders
 1 call for tenders
 1 call for tenders
 Several procurements for the CDS-SL
Support and transportation frames
 1 call for tenders
Auxiliary lines, vent lines
 1 call for tenders
Temperature sensors (Cernox type)
 1 call for tenders
On site installation
 1 call for tenders
 1 call for tenders
Control valves
 1 call for tenders
Heat exchangers (subcoolers)

## Slide 12: Procurements
Procurement strategy
 save time on the administrative aspects of the calls for tenders:
smaller budget  simpler procedure  less administrative time
more technical specifications to write
more administrative procedures to do
 more human resources (different departments of the CNRS)
 priory the components which are on the critical path:
do not wait for the finalization of the other components
(ex. launching VB procurement does not imply that end box is finalized)
 possibility of having several suppliers:
taking into account the (aggressive) schedule, workload might be dispatched
more follow-up (in different places)
 more human resources (CNRS)

## Slide 13: Procurements
Procurement process at CNRS
  Product cost < 90 k€HT
    “Adapted procurement process”
T0
Technical specification ready
and conditions to tender ready
Tendering is closed
+ 5 days
Offers are analysed
Offers are ranked
Report is written
1 days
Time
+5 day
Kick-off meeting
From technical specification to kick-off: 12 days minimum
Procurement notification letters received by the supplier
+1 days
If 90 k€HT < product cost < 135 k€HT, 1 additional week

## Slide 14: Procurements
Procurement process at CNRS
  Product cost > 135 k€HT
    “Formalized procurement process”
T0
Technical specification ready
Administrative specification ready
(procurement regulation and tendering rules)
Call for tender published
+ 1 month
Tendering is closed
+35 days
Offers are analysed (tech and admin)
Offers are ranked
5 days
Time
Plea (appeal)
+11 days
+5 days
Kick-off meeting
From technical specification to kick-off: 3 months min
Procurement notification letters received by the supplier
+3 days

## Slide 15: Procurements
Procurement process at CNRS
  Product cost > 1 M€HT
    call for tender must be analyzed by a committee before being published
    3 additional weeks required
     4 months from technical specification to kick-off meeting
  But this is an ideal workflow
    with human resources fully available (IPNO + CNRS procurement department)
    with not any difficulty nor any problem at any step of the tendering
  At the present time
    human resource is not available for Formalized procurement process with product cost > 1 M€ !
    human resource is not fully available for Formalized or Adapted procurement process with product cost > 135 k€

## Slide 16: Procurements
Status of the CDS-SL procurements
  Heat exchangers
    Formalized procurement process
    Call for tender to be published
    Notification expected at the beginning of July
    Kick off in July
     Last heat exchanger to be delivered in February 2018
  Control valves
    Formalized procurement process
    Call for tender to be published
    Notification expected to be at the beginning of July
    Kick off in July
     Last set of control valves to be delivered in February 2018

## Slide 17: Procurements
CDS-SL procurements
  Valve boxes (Formalized procurement process with cost > 1M€HT)
    Technical specification  finalized in June 2017
    If procurement officer is available at that time (?)
    or
    the possibility of outsourced procurement set (?):
    administrative specification ready  July 2017
    > 1 M€HT  Committee  September 2017
    Call for tender published  September 2017
    Notification and kick off cannot be done before the beginning of December 2017
     The last Spoke valve box cannot be delivered to Lund by March 2018 !
    But the first Spoke valve box cannot neither !!
    By March 2018, at best, the valve box components (bellows, dish ends…) might be supplied.
    (NB: the manufacturing folder might be set by the manufacturer and validated by the CNRS before the procurement starts.)

## Slide 18: Procurements
CDS-SL procurements
  Valve boxes
    From those statements, considering:
      the manufacturing time (including controls and Factory Acceptance Test)
      the helium test of the first Valve box for complete design validation
    We expect the first valve box to be delivered at Lund:
    not before August 2018
    Not later than October 2018
  Other components procurements
    Valves boxes define the critical path
    ( other components might be delivered before the delivery of the last valve box)

## Slide 19: Thank you for your attention
CSP12
28 Novembre 2014