## Slide 1: BrightnESS WP2 impact on ESS Bilbao In-Kind work Jose Luis Martínez
06 Sept 2017 MTR meeting

## Slide 2: Objetive:
Strengthening the coordination of In-kind Contributions - Maximise the possibility for ESS and In-Kind partner organisations to deliver value during the Construction Phase through ‘In-Kind Contributions’ (IKC) according to the ESS IKC Process and to minimise and mitigate the risks associated with those contributions.
Partners: STFC (UK), TUD (NL), INFN & Elettra (IT), [BNC(HU)], ESS-Bilbao (ES), CEA (FR), FZJ (DE), ESS.
4.247 M€, 345 Person-Months (minimum)
BrightnESS WP2 - Stengthening the In-kind Contribution coordination
BrightnESS is funded by the European Union’s Horizon 2020 research and innovation programme under grant agreement No. 676548
Carlo J. Bocchetta – WP2 General Meeting – RAL (UK) 2 June 2017

## Slide 3: The IKC network of Regional Hubs
WP2 Regional Hubs
Regional Hub | Owner | Field Coordinator | Countries
North-West | STFC TU Delft | Justin Greenhalgh, Philippa Kingston, Deena Fernandes, Louise Dixon, John Webber for the UK Toon Verhoeven for NL | UK NL
Central | FZJ | Stefano Pasini, Tania Claudio Weber | DE, CZ, CH
Iberia | ESS Bilbao | Fiamma Garcia-Toriello, Estefania Abad Garcia | ES
Gallia | CEA | Florence Ragon, Antoine Dael | FR
South-East | INFN | Paolo Mereu, Santo Gammino Ornella Leonardi Andrea Miraglia Dániel Csanády for HU | IT, HU
Nordic-Baltic | ESS | Marie-Louise Ainalem, Miloš Davidović, Wojtek Fabianowski (ICS), Peo Gustavsson (ACC), Michela Dell'Anno Boulton (NSS), Gareth Aspinall, Jazmin Barreto Hamneby, Carlo J. Bocchetta | DK, SE, NO,IS, LT, LV, EE, PL
BrightnESS is funded by the European Union’s Horizon 2020 research and innovation programme under grant agreement No. 676548
Carlo J. Bocchetta – WP2 General Meeting – RAL (UK) 2 June 2017

## Slide 4
Spanish In-Kind Contribution
ESS Project | Type of Agreement | WBS/IK No. | WP description | Status | CB Value (kEUR) | Planned Date TA sign
ACCSYS | IKC | AIK 3.1 | MEBT | TA Signed | 4.522.285 € | 2017 Q2
ACCSYS | IKC | AIK 8.1 | RF for warm Linac | TA Signed | 7.257.000 € | 2017 Q2
ACCSYS | IKC | AIK 17.6 | 3 Klystron modulators | TA Signed | 3.370.000 € | 2016 Q4
ICS | IKC | IIK 14.10.4#1 | MEBT CONTROL SYSTEM | TA Signed | 863.258 € | 2016 Q4
Target | IKC | TIK.2.1 | Target Wheel | TA Signed | 8.420.000 € | 2015 Q4
Target | HoA | TIK.4.2 | Proton Beam Instrumentation Plug | HoA Signed | 540.000 € | 2017 Q2
Target | IKC | TIK.4.4 | Proton Beam Window | TA Signed | 890.000 € | 2016 Q2
Target | IKC | TIK.4.5 | Monolith Vessel | TA Signed | 4.560.000 € | 2016 Q3
Target | IKC | TIK.4.9 | Tuning Beam Dump | TA Signed | 2.480.000 € | 2016 Q2
NSS | IKC | NIK 2 #3 | Beam Transport Optimisation for the Extreme Condition Diffractometer | TA Signed | 20.000 € | 2014 Q4
NSS | IKC | NIK 5.3 #7 | Training of Motion Control Engineer (ES) | TA Signed | 97.000 € | 2015 Q4
NSS | IKC | NIK 6.3 #1 | Secondment of a mechanical engineer to LOKI | TA Signed | 54.000 € | 2016 Q1
NSS | IKC | NIK 6.16 #1 | Miracles Instrument | TA Signed | 423.500 € | 2017 Q2
NSS | IKC | NIK 6.16 #2 | Miracles Instrument | TBD | 13.045.250 € | 

## Slide 5
Training and knowledge of ESS procedures
Risk assessment in WPs
TAs preparation
Call for tenders preparation
Coordination with ESS and other partners Logistic and deliveries
Installation works
QA/QC
Monitoring IK work.
  Milestones tracking (progress, achievements, delays, action points)
  Regular meetings with WP leaders
  Monitoring of WP planning and monthly report.
Coordination with WP6 outreach and dissemination.
Coordination with Spanish ILO.
Following up Technical Board and Collaboration Board meetings for Accelerator, Target and Instruments
Brightness WP2 during these 24 months has helped/supported ESS Bilbao in:

## Slide 6
FCs have participated in the redaction of :
  MEBT TA
  Control for MEBT TA
  3 klystron Modulators TA
  RF for warm linac TA
  Miracles instrument TAs
FCs have organized the delivery of the concrete shielding for the Beam Dump and are working on the preparation of the future deliveries of MEBT, Target and Monolith Vessel.
Brightness has supported the preparation of the call for tender for the 3 Modulators.
FCs have stablished and developed a ESS-Bilbao Risk Management procedure that has helped to identify and mitigate important risks on several Work Packages :
  MEBT Buncher coupler manufacturing problems
  MEBT Transport issues
  Design of RF WGs through the stubs
  Target Monolith Vessel atmosphere
  Target Monolith Vessel Installation
  Target cooling pressure drop
  Target RCCM class changes
Some specific cases:

## Slide 7
FCs are working/ colaborating on the Installation Works for MEBT, Target and Monolith Vessel.
FCs are working on the racks and cabling definition for MEBT and RF for the Front-End Building and the klystron Gallery, making the coordination with ESS installation team.
FCs have developed a complete planning of all WPs, including major procurements, FATS, deliveries and SATs together with the cashflow needed.
Brightness has helped to a better coordination with ESS and other partners supporting the travels for the Technical and Collaboration Boards meetings.
Brightness (through FCs) has helped WPs leaders to understand ESS procedures and follow them on WP works.
FCs have shared information about standardization (coming from a BrightnESS workshop) for instrument shielding important for MIRACLES team
FCs have and share knowledge of ESS collaborative tools (CHESS, confluence, DOORS,..)

## Slide 8
Fast communication channel to report problems, delays, risks…
Improve coordination between partners
Pushing ESS to improve the existing procedures or to create new ones (i.e.: in quality, logistics, Installation..)
In the preparation for the installation
Brightness has supported workshops/forums where ESS has learnt and listened different points of view from different partners in every phase of the project: Design, installation..(is expected one for commissioning)
To detect ESS lacks of task/personnel/ resources in the master plan (i.e.:installation manager, housing for in-kin partners staff, trainings...)
Developing an In-Kind information system XRM+
How Brightness has helped ESS (from partners point of view):