## Slide 1: SSM licence for test stands
Lena Johansson
ESS Radiation Protection Expert
www.europeanspallationsource.se
ESHAC 9-10 October 2017

## Slide 2: Test stand licences
Documented description of the hazards, activities and area
Formal submission to SSM
Approval
Review
Response
Review
Response

## Slide 3: Mini PSAR
time
practice
feedback
Quality
Test stand 2a
Test stand 2b
Ion source

## Slide 4: Test stand 2a - klystrons
SSM Permit received 28 June 2016
Background dosimeters placed in the test stand (last week)
Local rules template sent out
Supervised Area Training module for (a few) members of staff in 2017
Purchase of monitors and OSL completed during summer 2017.

## Slide 5: Test stand 2b - cryomodules
SSM application should be submitted in November 2017.
Start Feb 2018 - delayed
In contact with Project Manager who will provide lab description for the application and time frames.
The PSS on the Bunker will include radiation monitors.
Also partly described in PSAR Chapter 4.

## Slide 6: Ion source – in-kind contribution from INFN, Italy
Documentation in preparation with input from INFN and AD and ICS at ESS.
Ion Source arrives at ESS in November 2017.
Permit for installation goes under the general application. Should be fulfilled November 2017.
Licence approved Feb 2018
SSM application should be submitted in November 2017.
RP (Ida) visited INFN in June 2017 - further radiation measurements on the IS and LEBT.
PSS is mainly for electrical safety purposes but will also provide radiation shielding.
(This is/was at the same time as the cryomodules test stand.)

## Slide 7: AOB – test stand licensing
AOB
Regular meetings with Johan to update on licensing.
SSM has been informed of the dates for the applications.
SSM has confirmed contact person regarding test stands.