## Slide 1: Radiation Monitoring
Alasdair DAY
ESHAC, 9-10 October 2017
www.europeanspallationsource.se

## Slide 2: Introduction
“5. The Committee recommends that ESS deals with radiation monitoring issues with the highest priority. Monitors must be specified and tested if no reference exists (in particular electronics most probably need to be able to cope with pulsed beams).”

## Slide 3: Using CERN as a guide
Costs still be included
Spares
Analytical labs
Maintenance & operations
Resources, workshops & space
 | Material Cost | Infrastruture Cost | Installation Cost | Totals
Pulsed monitoring | € 855,000 | € 556,063 | € 92,865 | € 1,503,928
Secondary monitoring | € 220,000 | € 115,313 | € 24,600 | € 359,913
Personnel surveillance | € 920,000 | € 218,581 | € 46,330 | € 1,184,911
Gas, particulate and dedicated samplers | € 1,290,000 | € 147,959 | € 51,968 | € 1,489,926
Mobile and hand held instrumentation | € 580,000 |  |  | € 580,000
Dosimetry | € 495,000 | € 56,375 | € 6,150 | € 557,525
Environmental monitoring | € 820,000 | € 309,038 | € 35,260 | € 1,164,298
Totals | € 5,180,000 | € 1,403,328 | € 257,173 | € 6,840,500
X

## Slide 4: Key milestones
Test bunker
  Test stand 2a Klystron
  Test stand 2b Cryogenics
    Week 9 - 2018
Ion Source – PSS0
    Week 9 - 2018
Beam on Temporary Dump – Warm Linac – PSS1
    Week 36 - 2018
Beam on Target – PSS
    Week 33 - 2020
Full suite of instruments
    2025?

## Slide 5: Monitoring options
“It is hard to find on the market the type of monitors required e.g. for PSS and Area monitors – ESS might be forced to relax on the requirements.
The related consequences should be assessed.”
Market leaders have limited exposure
CERN developing CROME
CERN/ESS collaboration for PSS1
Future primary RP system for PSS?
Immediate needs and what about the future

## Slide 6: Immediate questions
Started
Synergy with ICS
  Racks
  Cabling (detector dependent)
    SPA6 cable, specialist & tools ?
  Networking
  Power
Site integration
To do
Budget profiling for 2018 and create MTP
Full system specifications PRD
Systemic naming convention
Resources
Supervisory systems

## Slide 7: Supervision
ICS Department
  EPICS
    In-house solution
    ESS control systems experts
    Infrastructure already integrated
    Communications protocols & integration will take time
    Management/budget for external resources
CERN
  REMUS - Radiation and Environment Monitoring Unified Supervision
    Proven system
    Significant library of integrated equipment
    Will require dedicated resources, not the core business of ES&H
    Possible modification to DB structure to meet ESS infrastructure requirements
Industry
  Myriad of options
    Bespoke system
    Will require dedicated resources, not the core business of ES&H
    Procurement could cause significant delays
    Elevated costs
    Greater risk of delay

## Slide 8: Looking forward
Immediate
Define specific requirements with each system responsible
Further meetings with key stakeholders
  Accelerator, target & instrument safety, target cooling, integration
Procurement processes
Collaboration addendum with CERN for CROME and at HSE/ES&H level modify the parent agreement
Longer term
Calibration facilities
Dosimetry synergy or service
Workshop and maintenance facilities
Maintenance contract or in-house services
What else?

## Slide 9: One week in, what have I missed