## Current RR
RISK | [27 empty] | Likelihood | Impact | Score |  |  |  |  | Actions to be placed
Level | Strategy | [26 empty] | Not Credible | Negligible | 1 |  |  |  |  | Avoidance
LOW | S1 | Low = Blue > Actions are evaluated in order to reduce the risk. Possible risk owner and WP leader monitoring | [25 empty] | Unlikely | Low | 2 |  |  |  |  | Mitigation
MINOR | S2 | Minor = Green > Same as previous + mandatory risk owner is appointed to monitor the risk evolution and report to WP leader. Actions are scheduled and evaluated in order to reduce the risk. | [25 empty] | Not likely | Medium | 4 |  |  |  |  | Transfert
MAJOR | S3 | Major = Yellow > Same as previous + Mitigation actions are defined by WP leader and assesed by Porject leader who identifies also possible trigger events to start them. The owner monitors the risks and these trigger events. | [25 empty] | Likely | High | 8 |  |  |  |  | Retention
SEVERE | S4 | Severe = Red > Same as previous + Planned mitigation actions are started as soon as scheduled. The Project leader closely monitors the effectiveness of the mitigation actions at each project progress report | [25 empty] | Very Likely | Very High | 16
Identification | [7 empty] | Rating Pre-Mitigation | [5 empty] | Disposition | [7 empty] | Rating Post-Mitigation
Risk ID | Date | Type | Risk Owner | Risk Label |  |  | Risk occuring 1st date | Likelihood | Impact |  |  | Level |  | Treatment | Mitigation Strategy / main actions | Back-up | Initiation Date | Completion Date | Cost for Action Plan (k€) | Additional manpower (H.an) | Comment | Likelihood | Impact |  |  | Level
|  |  |  | ("As a result of...") | ("There is a risk that...") | ("Resulting in...") |  |  | TECH | COST | SCHED | [11 empty] | TECH | COST | SCHED
|  | - |  | TARGET OPTICAL SYSTEM | [25 empty] | VALUES | TECH | COST | SCHED | Max impact |  | TECH | COST | SCHED | Max impact
1 |  |  |  | Tolerances for initial alignment cannot be met | Loss of light | Reduced performance |  | Unlikely | MEDIUM | LOW | LOW | 8 | MINOR | Mitigation | Test alignment strategy in prototype | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 4 | 2 | 2 | 4 |  | 2 | 2 | 2 | 2
2 |  |  |  | Alignment tolerances for PBIP installation not met | Shift in field of view, region of interest not fully visible. | Reduced performance |  | Unlikely | MEDIUM | LOW | LOW | 8 | MINOR | Mitigation | Fully understand expected errors form installation. Worst case, increase field of view of system. | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 4 | 2 | 2 | 4 |  | 2 | 2 | 2 | 2
3 |  |  |  | Mirrors move during PBIP installation | Loss og light during operation | Reduced or no performance |  | Unlikely | MEDIUM | LOW | MEDIUM | 8 | MINOR | Mitigation | Full test of mirror mount prior to installation | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 4 | 2 | 4 | 4 |  | 2 | 2 | 2 | 2
4 |  |  |  | Alignment tolerances for M1, M2 and M3 cannot be met during operation | Shift of field of view, loss of light | Reduced or no performance |  | Not likely | MEDIUM | LOW | MEDIUM | 16 | MAJOR | Mitigation | Full thermomechanical simulation of PBIP used as imput to optical performance simulations. Adjust system design if tolerances cannot be met in simulation. | [6 empty] | Unlikely | MEDIUM | LOW | LOW | 8 | MINOR |  |  |  | 4 | 2 | 4 | 4 |  | 4 | 2 | 2 | 4
5 |  |  |  | Alignment tolerances for M4, M5, M6 and M7 cannot be met | Loss of light | Reduced performance |  | Unlikely | MEDIUM | MEDIUM | MEDIUM | 8 | MINOR | Mitigation | Study motorized mirror mounts above the PBIP, automatic alignment. | [6 empty] | Unlikely | LOW | LOW | MEDIUM | 8 | MINOR |  |  |  | 4 | 4 | 4 | 4 |  | 2 | 2 | 4 | 4
6 |  |  |  | System cannot collect sufficient light | Sensitivity of imaging system is reduced | Reduced or no performance, reduced lifetime of the system |  | Unlikely | HIGH | LOW | MEDIUM | 16 | MAJOR | Mitigation | Backup option: camera in connection cell. | [6 empty] | Unlikely | MEDIUM | MEDIUM | MEDIUM | 8 | MINOR |  |  |  | 8 | 2 | 4 | 8 |  | 4 | 4 | 4 | 4
7 |  |  |  | Mirror deformations to M1 due to thermal expansions | Reduced resolution, loss of light | Reduced performance |  | Not likely | LOW | LOW | LOW | 8 | MINOR | Mitigation | Heat tests of the mirror. Fiducial tracking. | [6 empty] | Unlikely | LOW | MEDIUM | LOW | 8 | MINOR |  |  |  | 2 | 2 | 2 | 2 |  | 2 | 4 | 2 | 4
8 |  |  |  | Mirror coatings for M2-M5 corroded in target atmosphere. | Loss of light, loss of image quality | Reduced or no performance |  | Likely | HIGH | LOW | MEDIUM | 64 | SEVERE | Mitigation | Mirror coatings will be testes with expected corrosive agents. Most suitable coating will be selected | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 8 | 2 | 4 | 8 |  | 2 | 2 | 2 | 2
9 |  |  |  | Mirror coatings for M1 cannot withstand combination of radiation, heating and corrosive atmosphere | Loss of light, loss of image quality | Reduced or no performance |  | Likely | VERY HIGH | LOW | MEDIUM | 128 | SEVERE | Mitigation | Mirror coating will be tested with thermal fluctuations, irradiation and corrosive agents. Most suitable coating will be selected. | [6 empty] | Not likely | MEDIUM | LOW | LOW | 16 | MAJOR |  |  |  | 16 | 2 | 4 | 16 |  | 4 | 2 | 2 | 4
|  | - |  | TUNING BEAM DUMP OPTICAL SYSTEM | [25 empty] | VALUES | TECH | COST | SCHED | Max impact |  | TECH | COST | SCHED | Max impact
1 |  |  |  | Cameras fail in radiation environment | Too frequent resets, or dead cameras | Reduced or no performance |  | Unlikely | VERY HIGH | LOW | MEDIUM | 32 | MAJOR | Mitigation | Refine radiation calculations. Have radiation hard cameras as backup solution. | [6 empty] | Unlikely | MEDIUM | MEDIUM | LOW | 8 | MINOR |  |  |  | 16 | 2 | 4 | 16 |  | 4 | 4 | 2 | 4
1 |  |  |  | Double mover system inserts both H and V screen at the same time | Damaged or destroyed screens | Reduced or no performance |  | Unlikely | HIGH | LOW | HIGH | 16 | MAJOR | Mitigation | Implement interlock for H and V movers | [6 empty] | Unlikely | MEDIUM | MEDIUM | LOW | 8 | MINOR |  |  |  | 8 | 2 | 8 | 8 |  | 4 | 4 | 2 | 4
|  | - |  | PHOTON SOURCE | [25 empty] | VALUES | TECH | COST | SCHED | Max impact |  | TECH | COST | SCHED | Max impact
9 |  |  |  | Inadqeuate photon yield after high integrated dose | Highly reduced light yield | Reduced or no performance |  | Very Likely | VERY HIGH | LOW | MEDIUM | 256 | SEVERE | Mitigation | Attempt to develop a new coating (eventually based on new chemistry) | [6 empty] | Likely | LOW | MEDIUM | MEDIUM | 32 | MAJOR |  |  |  | 16 | 2 | 4 | 16 |  | 2 | 4 | 4 | 4
10 |  |  |  | Inadequate light yield for comissioning pulses | reduced sensitivity in the comissioning phase | Reduced performance |  | Not likely | HIGH | LOW | MEDIUM | 32 | MAJOR | Mitigation | Extensive testing of coating process before installation | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 8 | 2 | 4 | 8 |  | 2 | 2 | 2 | 2
11 |  |  |  | Competing light sources (e.g from residual gas) | Loss of contrast | Reduced performance |  | Likely | LOW | LOW | LOW | 16 | MAJOR | Mitigation | Attempt to separate light by wavelength | [6 empty] | Not likely | LOW | LOW | Negligible | 16 | MAJOR |  |  |  | 2 | 2 | 2 | 2 |  | 2 | 2 | 1 | 2
12 |  |  |  | Stray light, light from reflections | Image artefacts, loss of contrast | Reduced performance |  | Not likely | LOW | LOW | Negligible | 16 | MAJOR | Mitigation | Sufficient optical coating of PBIP components | [6 empty] | Unlikely | LOW | MEDIUM | LOW | 8 | MINOR |  |  |  | 2 | 2 | 1 | 2 |  | 2 | 4 | 2 | 4
13 |  |  |  | Coating not correctly applied (not uniform, wrong parameters) | IMG resolution or FOV is perturbed | Reduced or no performance |  | Not likely | MEDIUM | MEDIUM | MEDIUM | 16 | MAJOR | Mitigation | Establish and document industrial standard, reproducible coating process | [6 empty] | Unlikely | LOW | LOW | LOW | 4 | MINOR |  |  |  | 4 | 4 | 4 | 4 |  | 2 | 2 | 2 | 2
[31 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF!
ELECTRONICS
13 |  |  |  | Hardware standard for FPGA and other electronics not ready in time | IMG electronics not ready in time | IMG will not run on ESS ICS for commissioning |  | Likely | MEDIUM | LOW | MEDIUM | 32 | MAJOR | Mitigation | Keep dialogue/pressure on ESS ICS | [6 empty] | Unlikely | LOW | LOW | MEDIUM | 8 | MINOR
14 |  |  |  | Final algorithms too slow on specified FPGA to ensure beam synchronicity. | Advanced IMG analysis cannot be done in real tim | Beam synchronous signal will not function properly |  | Unlikely | MEDIUM | LOW | MEDIUM | 8 | MINOR | Mitigation | Prototype, benchmark and adjust algorithms to "fit" | [6 empty] | Unlikely | LOW | LOW | MEDIUM | 8 | MINOR
[29 empty] | Likelihood | Impact | Score
Schedule
15 |  |  |  | Actual schedule surpasses the contractual schedule | Lack of continuity in expertise before the system is finished | Delays in system installation |  | Likely | MEDIUM | LOW | MEDIUM | 32 | MAJOR | Mitigation | Discuss and update milestones as needed, consider updated contracts | [6 empty] | Unlikely | LOW | LOW | MEDIUM | 8 | MINOR
[29 empty] | Unlikely | Low | 2
[29 empty] | not credible | low | 2
[29 empty] | Not Credible | Medium | 4
[29 empty] | Unlikely | low | 4
[29 empty] | not likely | Negligible | 4
[29 empty] | Not Credible | high | 8
[29 empty] | Unlikely | Medium | 8
[29 empty] | not likely | low | 8
[29 empty] | likely | Negligible | 8
[29 empty] | Not Credible | very high | 16
[29 empty] | Unlikely | high | 16
[29 empty] | Likely | Low | 16
[29 empty] | Very likely | Negligible | 16
[29 empty] | Unlikely | very high | 32
[29 empty] | not likely | high | 32
[29 empty] | likely | Medium | 32
[29 empty] | Very likely | low | 32
[29 empty] | not likely | very high | 64
[29 empty] | likely | high | 64
[29 empty] | Very likely | Medium | 64
[29 empty] | likely | very high | 128
[29 empty] | Very likely | high | 128
[29 empty] | Very likely | very high | 256

## Closed risk
Docs #
[22 empty] | DMS # |  | xx
Doc. #
RISK | [25 empty] | Likelihood | Impact | Score |  |  |  |  | Actions to be placed
Level | Strategy | [24 empty] | Not Credible | Negligible | 1 |  |  |  |  | Avoidance
LOW | S1 | Low = Blue > Actions are evaluated in order to reduce the risk. Possible risk owner and WP leader monitoring | [23 empty] | Unlikely | Low | 2 |  |  |  |  | Mitigation
MINOR | S2 | Minor = Green > Same as previous + mandatory risk owner is appointed to monitor the risk evolution and report to WP leader. Actions are scheduled and evaluated in order to reduce the risk. | [23 empty] | Not likely | Medium | 4 |  |  |  |  | Transfert
MAJOR | S3 | Major = Yellow > Same as previous + Mitigation actions are defined by WP leader and assesed by Porject leader who identifies also possible trigger events to start them. The owner monitors the risks and these trigger events. | [23 empty] | Likely | High | 8 |  |  |  |  | Retention
SEVERE | S4 | Severe = Red > Same as previous + Planned mitigation actions are started as soon as scheduled. The Project leader closely monitors the effectiveness of the mitigation actions at each project progress report | [23 empty] | Very Likely | Very High | 16
Identification | [7 empty] | Rating Pre-Mitigation |  |  |  |  | Disposition | [7 empty] | Rating Post-Mitigation
Risk ID | Date | Type | Risk Owner | Risk Label |  |  | Risk occuring 1st date | Likelihood | Impact |  |  | Level | Treatment | Mitigation Strategy / main actions | Back-up | Initiation Date | Completion Date | Cost for Action Plan (k€) | Additional manpower (H.an) | Comment | Likelihood | Impact |  |  | Level
|  |  |  | ("As a result of...") | ("There is a risk that...") | ("Resulting in...") |  |  | TECH | COST | SCHED | [10 empty] | TECH | COST | SCHED
|  | - |  | xx | [23 empty] | VALUES | TECH | COST | SCHED | Max impact |  | TECH | COST | SCHED | Max impact
WP RR status
[21 empty] | Total risks # | Top level risks # | Avreage criticity before | Avreage criticity after
[21 empty] | 0 | 0 | #DIV/0! | #DIV/0!
Assumptions / limit conditions
[27 empty] | Likelihood | Impact | Score
[27 empty] | Not Credible | Negligible | 1
[27 empty] | Unlikely | Low | 2
[27 empty] | not credible | low | 2
[27 empty] | Not Credible | Medium | 4
[27 empty] | Unlikely | low | 4
[27 empty] | not likely | Negligible | 4
[27 empty] | Not Credible | high | 8
[27 empty] | Unlikely | Medium | 8
[27 empty] | not likely | low | 8
[27 empty] | likely | Negligible | 8
[27 empty] | Not Credible | very high | 16
[27 empty] | Unlikely | high | 16
[27 empty] | Likely | Low | 16
[27 empty] | Very likely | Negligible | 16
[27 empty] | Unlikely | very high | 32
[27 empty] | not likely | high | 32
[27 empty] | likely | Medium | 32
[27 empty] | Very likely | low | 32
[27 empty] | not likely | very high | 64
[27 empty] | likely | high | 64
[27 empty] | Very likely | Medium | 64
[27 empty] | likely | very high | 128
[27 empty] | Very likely | high | 128
[27 empty] | Very likely | very high | 256

## Counting
Reference table |  |  |  | Current satus of WP RR
Score | Likelihood | Max impact | Max impact value | Count before | Count after
[6 empty] | Impact | Value
1 | Not Credible | Negligible | 1 | 0 | 0 | Negligible | 1
2 | Unlikely | Negligible | 1 | 0 | 0 | LOW | 2
2 | Not Credible | Low | 2 | 0 | 0 | MEDIUM | 4
4 | Not likely | Negligible | 1 | 0 | 0 | HIGH | 8
4 | Unlikely | Low | 2 | 0 | 6 | VERY HIGH | 16
4 | Not Credible | Medium | 4 | 0 | 0
8 | Likely | Negligible | 1 | 0 | 0
8 | Not likely | Low | 2 | 2 | 1
8 | Unlikely | Medium | 4 | 4 | 7
8 | Not Credible | High | 8 | 0 | 0
16 | Very likely | Negligible | 1 | 0 | 0
16 | Likely | Low | 2 | 1 | 0
16 | Not likely | Medium | 4 | 2 | 1
16 | Unlikely | High | 8 | 2 | 0
16 | Not Credible | Very high | 16 | 0 | 0
32 | Very likely | Low | 2 | 0 | 0
32 | Likely | Medium | 4 | 0 | 1
32 | Not likely | High | 8 | 1 | 0
32 | Unlikely | Very high | 16 | 1 | 0
64 | Very likely | Medium | 4 | 0 | 0
64 | Likely | High | 8 | 1 | 0
64 | Not likely | Very high | 16 | 0 | 0
128 | Very likely | High | 8 | 0 | 0
128 | Likely | Very high | 16 | 1 | 0
256 | Very likely | Very high | 16 | 1 | 0
|  |  |  | 16 | 16

## Rating Information
RISK RATING
LIKELIHOOD of risk occurrence
Value |  | Description
Not Credible | (1) | probability of occurrence < 1%. |  | the probability of the risk is very low
Unlikely | (2) | probability of occurrence > 1% but <10% |  | the probability of the risk is low or if its occurrence is late in relation to the lifetime of the project.
Not likely | (4) | probability of occurrence > 10% but <40%
Likely | (8) | probability of occurrence > 40% but <80% |  | the risk is identified. There exists a high probability that it will occur
Very Likely | (16) | probability of occurrence > 80% |  | the probability of the risk identified is almost certain
TECHNICAL / OTHER IMPACT
Value |  | Impact on
|  | Technical Performance | Human health, safety and well being | Environment | Reputation and Image | Political
Negligible | (1) | Minimal or no consequence to technical performance | No injuries | No environmental impact | No damage to reputation/image | No political/ organizational impact
LOW | (2) | Minor reduction in technical performance or supportability, can be tolerated with little or no impact on program | Minor injuries; no public health risk; short term well being impact | Minor,/recoverable short-term isolated/ localized environmental impact | Recoverable / short term local damage to reputation/image | Local political / organizational impact
MEDIUM | (4) | Moderate reduction in technical performance or supportability with limited impact on program objectives | Limited public health risk &/or injuries requiring medical & mental health treatment | Moderate, medium term, medium spread environmental impact | Medium term / regional damage to reputation/image | Regional political / organizational impact
HIGH | (8) | Significant degradation in technical performance or major shortfall in supportability; may jeopardize program success | Major public health risk &/or major injuries/well being impact | Serious, long term, widespread environmental impact | Long term/ state damage to agency reputation/image | State political / organizational impact
VERY HIGH | (16) | Severe degradation in technical performance; Cannot meet baseline or key technical/ supportability threshold; will jeopardize program success | Significant public health risk &/or human deaths/ long lasting well being issues | Irreversible environmental impact | Long term / (inter) national damage to reputation / image irreversibly impacted | National political / organizational impact
COST IMPACT
Value |  | Budget Change by | seuil en M€
Negligible | (1) | CHANGE < Budget * 0.02 | x<0,3
LOW | (2) | Budget * 0.02 ≤ CHANGE < Budget * 0.05 | 0,3<x<0,6
MEDIUM | (4) | Budget * 0.05 ≤ CHANGE < Budget * 0. 1 | 0,6<x<1,3
HIGH | (8) | Budget * 0.1 ≤ CHANGE < Budget * 0.3 | 1,3<x<4,5
VERY HIGH | (16) | CHANGE ≥ Budget * 0.3 | > 4,5 M€
SCHEDULE IMPACT
Value |  | DELAY on Milestone (at project level Integrated Project Schedule Milestones)
|  | NON Critical Path Milestone |  | Critical Path Milestone
Negligible | (1) | No delays on milestones (< 1 month) |  | No delays on milestones (<1 week)
LOW | (2) | 1 month ≤ DELAY < 3 months |  | DELAY < 1 month
MEDIUM | (4) | 3 month ≤ DELAY < 6 months |  | 1 month ≤ DELAY < 3 months
HIGH | (8) | 6 month ≤ DELAY < 1 year |  | 3 month ≤ DELAY < 6 months
VERY HIGH | (16) | DELAY ≥ 1 year |  | DELAY ≥ 6 moths
LIKELIHOOD
IMPACT